## Overview
Field | Value | Status | Last Updated | Notes
Project Name | Workspace Clone | Done | 2026-09-27 16:20 | Cross-device work-session continuity
Product Category | Developer Tools / Desktop App | Done | 2026-09-27 16:20
Target Platforms | macOS 13+ (built, launched and verified end to end). Windows 11 implemented but unverified - the build, the credential store and mDNS behind a Windows firewall have not been exercised. Linux not started. | Partial | 2026-09-27 17:40 | Changed from 'Done' to 'Partial'. The platform claim was stronger than the evidence: the app had never been run on either platform before 2026-09-27.
Tech Stack | Tauri 2 + React + TypeScript (UI), Rust (Core) | Done | 2026-09-27 16:20 | Per blueprint recommendation
Database | SQLite (local persistence) | Done | 2026-09-27 16:20 | Encrypted sensitive fields
Protocol | Noise_IK over direct TCP, with mDNS discovery | Done | 2026-09-27 16:20 | Direct device-to-device only. There is no relay, so two machines on different networks cannot reach each other yet.
Key Storage | OS credential store (macOS Keychain / Windows Credential Manager), three separate entries | Done | 2026-09-27 16:20 | Each secret is written only to its own entry. The database is not encrypted; manifests are sealed individually with a local key.
Current Phase | Phase 4 - LAN Transfer: receive path complete and workspace files travel and restore; Phase 5 (Linux, relay, team features) not started | In Progress | 2026-09-28 21:45 | Workspace files are now captured, carried and restored end to end. Windows is still implemented but unverified on the hardware; the DMG is built on the Mac.
MVP Scope | Pairing, Capture, Preflight, Restore, LAN Transfer | Done | 2026-09-27 16:20
Repository | TBD | Done | 2026-09-27 16:20
Security Review | Required before Public Beta. No CSP is set. 7 npm audit findings in the dev toolchain. Windows unverified. | Not Started | 2026-09-27 17:40 | Changed from 'Done' to 'Not Started'. Review has not happened; these are the things it would have to cover.
Test Coverage | 419 Rust tests (was 408). The +11: 6 git-adapter tests proving a dirty worktree captures as an appliable patch and restore applies exactly that delta (`git status` matches), a mismatched base reports the checkout remedy, the denylist keeps secrets out of the patch, and a clean worktree carries no patch; 2 planner tests for the extract-skip on patched projects; 1 two-device e2e sending a dirty repo's delta over a real socket and restoring it to exactly 'M note.txt' + '?? new.txt'; 102 frontend tests; 0 build warnings. | Done | 2026-09-30 10:30 | Up from 377/99. The files crate, the wire envelope, and the restore extract path are fully covered; the two-device suite now proves a file changed on the sending machine restores with the changed content on the receiving machine.

## Epics
Epic ID | Epic Name | Description | Phase | Priority | Status | Progress % | Start Date | Target Date | Owner | Dependencies | Notes
EPIC-001 | Project Foundation & Setup | Initialize Tauri 2 + React + TypeScript + Rust workspace, CI/CD, linting, testing infrastructure | Phase 1 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  |  | Foundation for all other work
EPIC-002 | Local Database & Schema | SQLite schema for devices, workspaces, snapshots, restore runs, adapter checks. Encryption for sensitive fields. | Phase 1 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-001
EPIC-003 | Workspace Manifest Model | TypeScript/Rust types, validation, serialization, schema versioning, secret scrubbing, capture preview | Phase 1 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-001
EPIC-004 | Capture Pipeline & Adapters (Core) | Git, VS Code, Browser URLs, Terminal, Runtime/CLI detection adapters. Capture selection UI. | Phase 1 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-003
EPIC-005 | Device Pairing & Trust | Key generation, OS secure storage, pairing ceremony (QR/code), verification, trust scopes, revocation | Phase 2 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-001, EPIC-002 | Critical security component
EPIC-006 | LAN Discovery & Encrypted Transfer | mDNS/DNS-SD discovery, Noise/TLS authenticated channel, manifest transfer with retry/cancel | Phase 2 | P0 | In Progress | 90 | 2026-09-26 | 2026-09-26 |  | Verified end to end by the loopback suite: a real Noise_IK handshake, a byte-for-byte round trip, a digest checked on both sides, a refused handshake against the wrong key, and a refusal to connect to a device that advertised no key. Cancellation was 15 seconds late and is now prompt (BUG-002). | Send, discover, authorize, record and the receive path all work and are covered by 11 two-device tests. Held at 90 rather than Done because no Windows build has been exercised end to end. Was recorded as Done at 100% on 2026-09-26 while the receive path did not exist at all - see BUG-005 and LOG-045.
EPIC-007 | Preflight Engine & Identity Readiness | Check categories: apps, identity, toolchain, repo, env, services, permissions. Readiness states. | Phase 3 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-002, EPIC-003 | Core differentiator
EPIC-008 | Restore Planning & Execution | Plan generation, dependency ordering, user approval, safe actions (open, launch, command recipes), report | Phase 3 | P0 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-007
EPIC-009 | UI/UX - All Screens | Welcome, Devices, Workspaces, Capture, Transfer, Preflight, Prepare, Restore Preview, Report, Settings | Phase 1-3 | P1 | Done | 100 | 2026-09-26 | 2026-09-27 | 2026-09-27 16:20 | All ten screens are driven by real commands. Devices, Prepare, Settings and Welcome were previously on mock data with stubbed handlers and were rebuilt this session; the other six were rebuilt earlier. The mock flows were not cosmetic: Devices asked for a pairing code that no command accepts, Prepare listed nine invented actions, and Settings offered 22 toggles that changed nothing. | Iterate with user testing
EPIC-010 | Cross-Platform Path Mapping | Named destination roots, OS-specific path translation, project location rules | Phase 3 | P1 | Done | 100 | 2026-09-26 | 2026-09-26 |  | EPIC-003
EPIC-011 | Security Hardening & Review | Threat model validation, penetration testing, signed releases, crash resilience, diagnostics | Phase 4 | P0 | Not Started | 0 |  |  |  | Not started, but three findings already exist: BUG-003 (the key storage layout contradicted its own documentation), BUG-004 (the identifier mismatch, fixed), and tauri.conf.json still sets security.csp to null, which disables the Content-Security-Policy header entirely. | Independent review required
EPIC-012 | Post-MVP: Linux, Relay, Team Features | Linux support, optional encrypted relay, team manifests, policy, additional adapters | Phase 5 | P2 | Not Started | 0 |  |  |  | EPIC-011

## Features
Feature ID | Epic ID | Feature Name | Description | Component | Priority | Status | Progress % | Est. Days | Actual Days | Start Date | End Date | Assignee | Dependencies | Acceptance Criteria | Notes
FEAT-001 | EPIC-001 | Tauri 2 Workspace Init | Create Tauri 2 project with React + TypeScript + Rust workspace structure | Core/Infra | P0 | In Progress | 95 | 2 | 2 | 2026-09-26 | 2026-09-27 17:40 |  |  | Builds successfully, dev server runs | 2026-09-27: three bugs in this area were found only by starting the application. tauri dev could not find the app at all (BUG-009), the app shipped with zero capabilities (BUG-010), and the app panicked on launch (BUG-011). All three were silent to a fully green cargo build and test suite. npx tauri dev now works from the project root. See DEC-017.
FEAT-002 | EPIC-001 | CI/CD Pipeline | GitHub Actions: lint, typecheck, test, build (Windows/macOS), release signing | Core/Infra | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-001 | All checks pass on PR
FEAT-003 | EPIC-001 | Development Tooling | ESLint, Prettier, Rustfmt, Clippy, pre-commit hooks, VS Code settings | Core/Infra | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-001 | Consistent code style
FEAT-004 | EPIC-001 | Testing Infrastructure | Vitest (unit), Playwright (e2e), Rust unit/integration tests, test utilities | Core/Infra | P1 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-001 | Coverage > 80% critical paths
FEAT-005 | EPIC-002 | SQLite Schema & Migrations | Devices, Workspaces, Snapshots, RestoreRuns, AdapterChecks tables + migrations | Core/DB | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-001 | Schema matches blueprint §15
FEAT-006 | EPIC-002 | Database Encryption | Encrypt sensitive fields (device keys, workspace metadata) using SQLCipher or app-level | Core/DB | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-005 | Keys in OS secure storage
FEAT-007 | EPIC-002 | Repository Pattern (Rust) | Type-safe DB access layer with connection pooling, transactions | Core/DB | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-005 | sqlx or rusqlite
FEAT-008 | EPIC-002 | Tauri Commands for DB | Expose DB operations to frontend via Tauri commands | Core/DB | P0 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-007
FEAT-009 | EPIC-003 | Manifest Type Definitions | TypeScript + Rust shared types for workspace manifest (schema v1) | Core/Model | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-001 | Matches blueprint §7 example
FEAT-010 | EPIC-003 | Schema Validation | JSON Schema + runtime validation (zod/serde), version migration | Core/Model | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Reject unknown critical fields
FEAT-011 | EPIC-003 | Secret Scrubber | Redact credentials from URLs, scan for secret patterns, reject secret-bearing fields | Core/Model | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Defense in depth per §8.5
FEAT-012 | EPIC-003 | Capture Preview UI | Show included/excluded fields, toggles for sensitive hints before transfer | UI/Capture | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-011 | Per blueprint §8.6
FEAT-013 | EPIC-003 | Manifest Versioning & Snapshots | Local snapshots, capture timestamps, no silent overwrites | Core/Model | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Per blueprint §8.7
FEAT-014 | EPIC-004 | Git Adapter | Detect repo root, branch, remote, dirty status, commit hash. No credential access. | Adapters/Git | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Per blueprint §11 | Git Adapter now captures the dirty worktree as a git-applyable patch (GitInfo.patch) and applies it on restore via `git apply --binary`; the whole-tree overwrite for dirty repos is gone. 2026-09-30, BUG-037.
FEAT-015 | EPIC-004 | VS Code Adapter | Detect install, workspace file/folder, optional extension list (opt-in) | Adapters/VSCode | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | No settings/auth copy
FEAT-016 | EPIC-004 | Browser URL Adapter | Capture selected URLs (extension or manual), open URLs in target browser | Adapters/Browser | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | No profile scraping
FEAT-017 | EPIC-004 | Terminal Adapter | Detect terminal, cwd, launch recipes (no scrollback/session capture) | Adapters/Terminal | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Commands inert until approved
FEAT-018 | EPIC-004 | Runtime/CLI Adapter | Detect Node, pnpm, Git, Docker, provider CLIs versions via bounded commands | Adapters/Runtime | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-009 | Sanitize outputs
FEAT-019 | EPIC-004 | Capture Selection UI | Select projects, apps, URLs, optional clipboard/files. Preview before capture. | UI/Capture | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-014..018 | Per blueprint §8.1
FEAT-020 | EPIC-005 | Device Key Generation | Ed25519 keypair, store private key in OS secure storage (non-exportable) | Core/Crypto | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-006 | Per blueprint §6, §17
FEAT-021 | EPIC-005 | Pairing Ceremony | QR code + human-readable code, 5-min expiry, mutual key exchange, safety number verification | Core/Pairing | P0 | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | FEAT-020 | Per blueprint §6.1
FEAT-022 | EPIC-005 | Trust Scopes & Permissions | Receive/send workspaces, optional file transfer, optional clipboard transfer | Core/Pairing | P0 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-021 | Per blueprint §6.1 step 5
FEAT-023 | EPIC-005 | Device Management UI | List paired devices, online/offline, rename, revoke, last seen, fingerprint | UI/Devices | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-021 | Per blueprint §14.2
FEAT-024 | EPIC-005 | Revocation & Deny-List | Local revoke, signed revocation notice, offline deny-list, re-confirm on key change | Core/Pairing | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-021 | Per blueprint §6.2
FEAT-025 | EPIC-005 | Rate Limiting & Attempt Limits | Limit pairing attempts, expire codes, rate-limit discovery/handshake | Core/Pairing | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-021 | Per blueprint §6.2
FEAT-026 | EPIC-006 | mDNS/DNS-SD Discovery | Advertise rotating device ID + protocol version. No trust from discovery. | Network/Discovery | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-020 | Per blueprint §6.3, §15
FEAT-027 | EPIC-006 | Authenticated Encrypted Channel | Noise protocol or TLS 1.3 with mutual auth. Replay protection, sequence/nonce. | Network/Transport | P0 | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | FEAT-020 | Per blueprint §5, §15
FEAT-028 | EPIC-006 | Manifest Transfer Protocol | Chunked transfer, progress, cancel, resume after re-auth, idempotent duplicate handling | Network/Transfer | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-27 17:40 |  | FEAT-027 | Per blueprint §8.8, §15 | Verified 2026-09-27. Was already recorded Done at 100% on 2026-09-26, but the payload was the SENDER's sealed manifest, which no peer can open (BUG-006), and the receive path did not exist (BUG-005). Both ends now work and are covered by commands/tests/two_device_transfer.rs. See DEC-012.
FEAT-029 | EPIC-006 | Manual Address Fallback | Enter device address manually when LAN discovery fails | Network/Discovery | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-27 17:40 |  | FEAT-026 | Per blueprint §6.3 | Verified 2026-09-27 by RUN-010: a raw socket connected to the running app's advertised port was accepted and logged. Discovery and the manual fallback were already Done; this confirms the advertised port is one something actually listens on, which is the first time that has been true.
FEAT-030 | EPIC-006 | Transfer UI | Select paired destination, show encryption/trust status, progress, cancel | UI/Transfer | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-27 17:40 |  | FEAT-028 | Per blueprint §14.5 | Verified 2026-09-27. The send button was wired but there was no arrival UI and no refusal reporting, so a transfer that failed produced no message on either machine. Added the arrivals banner, refusal reporting with reasons, transfer history and the Received badge (FEAT-064 to FEAT-066). See BUG-005 and BUG-007.
FEAT-031 | EPIC-007 | Preflight Engine Core | Run all check categories, aggregate results, compute readiness (informational only) | Core/Preflight | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-005, FEAT-009 | Per blueprint §9
FEAT-032 | EPIC-007 | App/Tool Detection Checks | Verify required apps installed, versions, OS compatibility | Adapters/Preflight | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-031
FEAT-033 | EPIC-007 | Identity Readiness Adapters | GitHub (gh auth status), AWS (sts), Supabase, etc. Confidence states. | Adapters/Identity | P0 | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §9.2-9.3
FEAT-034 | EPIC-007 | Repository & File Checks | Project root mapping, remote identity, branch state, dirty changes, expected files | Adapters/Preflight | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-031
FEAT-035 | EPIC-007 | Environment Presence Checks | Check named env vars exist (values never read), from safe sources only | Adapters/Preflight | P0 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §9.5
FEAT-036 | EPIC-007 | Service & Port Checks | Local service availability (Docker, DB), port status. No network scanning. | Adapters/Preflight | P1 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §9.6
FEAT-037 | EPIC-007 | Permission Checks | OS permissions for features (Accessibility for window layout) | Adapters/Preflight | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §9.7
FEAT-038 | EPIC-007 | Preflight Report UI | Grouped ready/missing/mismatch/unknown with evidence freshness. Rerun individual checks. | UI/Preflight | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §14.6
FEAT-039 | EPIC-007 | Prepare Destination UI | Official install links, launch provider login flows, rerun checks | UI/Preflight | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-038 | Per blueprint §9.8
FEAT-040 | EPIC-008 | Restore Plan Generator | Map source paths → destination roots, inspect Git state, dependency ordering | Core/Restore | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-031 | Per blueprint §10
FEAT-041 | EPIC-008 | Safe Action Framework | Allow-listed executables, typed args, constrained vars, preview, approval, timeouts | Core/Restore | P0 | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | FEAT-040 | Per blueprint §10.2
FEAT-042 | EPIC-008 | Git Safe Restore | Never auto-stash/reset/clean. Offer open-as-is, choose path, reviewed Git action | Adapters/Git | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-040 | Per blueprint §10.4 | Git Safe Restore: patched projects restore via a git-apply step instead of whole-tree extraction, so the destination's `git status` shows exactly the source's uncommitted delta. 2026-09-30, BUG-037.
FEAT-043 | EPIC-008 | App Launch & URL Open Actions | Open editor, browser URLs (domain preview, block dangerous schemes) | Adapters/Restore | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-040 | Per blueprint §10.2
FEAT-044 | EPIC-008 | Command Recipe Execution | Visible terminal, typed recipes, explicit approval, per-step timeout, no background | Adapters/Terminal | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-041 | Per blueprint §10.2
FEAT-045 | EPIC-008 | File Transfer (Optional) | Explicit, path-scoped, size-limited, symlink-safe, preview, conflict handling | Core/Transfer | P1 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-041 | Post-MVP per blueprint | [Corrected 2026-09-28] This row stood for the manifest *policy flag* only. The real transport is FEAT-076 (snapshot), FEAT-077 (wire), FEAT-078 (storage) and FEAT-079 (restore); the UI wiring is FEAT-080. See LOG-085.
FEAT-046 | EPIC-008 | Clipboard Restore (Opt-in) | Off by default, preview, never silent replace | Core/Transfer | P2 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-041 | Per blueprint §10.2
FEAT-047 | EPIC-008 | Restore Preview UI | Ordered actions, exact paths, commands, conflicts, approval controls | UI/Restore | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-040 | Per blueprint §14.8
FEAT-048 | EPIC-008 | Restore Execution & Report | Execute in order, cancellation, per-step timeout, success/skipped/failed report, retry | UI/Restore | P0 | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | FEAT-047 | Per blueprint §14.9
FEAT-049 | EPIC-009 | Welcome / Permissions Screen | Explain local operation, install on each device, request OS permissions on demand | UI/Welcome | P0 | Done | 100 | 1 | 1 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-001 | Per blueprint §14.1 | Rebuilt 2026-09-27. Removed claims of QR codes, browser tab capture and a Phase 0 development status; this build does none of those. Now reports the real version, platform and paired-device count.
FEAT-050 | EPIC-009 | Devices Screen | Paired devices, online/offline, trust scopes, version, revoke/rename | UI/Devices | P0 | Done | 100 | 2 | 2 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-023 | Per blueprint §14.2 | Rebuilt 2026-09-27 from mockDevices (6 hardcoded refs) to listPairedDevices, createPairingInvitation, getSafetyNumber, verifyPairing, revokePairedDevice, deletePairedDevice and updatePairedDevice. See DEC-011: the previous code-based flow had no backend behind it.
FEAT-051 | EPIC-009 | Workspaces Screen | Recent captures, timestamp, source machine, readiness, version history | UI/Workspaces | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-013 | Per blueprint §14.3
FEAT-052 | EPIC-009 | Capture Screen | Select project/app context, inspect included/excluded data | UI/Capture | P0 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-019 | Per blueprint §14.4
FEAT-053 | EPIC-009 | Transfer Screen | Select destination, encryption status, progress | UI/Transfer | P0 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-030 | Per blueprint §14.5
FEAT-054 | EPIC-009 | Preflight Screen | Grouped checks with evidence, rerun, prepare actions | UI/Preflight | P0 | Done | 100 | 2 | 2 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-038 | Per blueprint §14.6 | Verified 2026-09-27 by BUG-001's route test. Preflight categories derive from check.adapter_id; unrecognised statuses render as themselves rather than as ready.
FEAT-055 | EPIC-009 | Prepare Screen | Install links, login buttons, rerun checks | UI/Preflight | P0 | Done | 100 | 1 | 1 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-039 | Per blueprint §14.7 | Rebuilt 2026-09-27 from 9 mockActions to the unmet subset of the real preflight report, grouped by adapter, each row offering the action the adapter recorded and a rerun.
FEAT-056 | EPIC-009 | Restore Preview Screen | Ordered actions, paths, commands, conflicts, approvals | UI/Restore | P0 | Done | 100 | 2 | 2 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-047 | Per blueprint §14.8 | Verified 2026-09-27 by BUG-001's route test.
FEAT-057 | EPIC-009 | Restore Report Screen | Success/skipped/failed, actions taken, retry options | UI/Restore | P0 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-048 | Per blueprint §14.9
FEAT-058 | EPIC-009 | Settings / Privacy Screen | Capture defaults, clipboard policy, retention, permissions, network, diagnostics, revocation | UI/Settings | P1 | Done | 100 | 2 | 2 | 2026-09-27 | 2026-09-27 16:20 |  | FEAT-001 | Per blueprint §14.10 | Rebuilt 2026-09-27. 22 toggles that called a command which does not exist, and 5 alert() stubs saying 'will be implemented in Phase 1', replaced by the real persisted surface: identity, project roots, settings export/import.
FEAT-059 | EPIC-010 | Named Destination Roots | Configure per-device project root mappings (e.g., ~/projects, ~/code) | Core/PathMap | P1 | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | FEAT-005 | Per blueprint §10.3
FEAT-060 | EPIC-010 | Cross-Platform Path Translation | Windows ↔ macOS path mapping, home directory expansion | Core/PathMap | P1 | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | FEAT-059
FEAT-061 | EPIC-011 | Security Audit & Pen Testing | Independent review of pairing, key storage, manifest parsing, command execution | Security | P0 | Not Started | 0 | 5 | 0 |  |  |  | EPIC-008 done | Per blueprint §16, §17
FEAT-062 | EPIC-011 | Signed Releases & Updates | Code signing (Windows/macOS), auto-update with rollback protection | Core/Infra | P0 | Not Started | 0 | 3 | 0 |  |  |  | FEAT-002 | Per blueprint §5.16
FEAT-063 | EPIC-011 | Crash Resilience & Diagnostics | Graceful degradation, user-controlled diagnostics, redacted error reports | Core/Infra | P1 | Not Started | 0 | 2 | 0 |  |  |  | FEAT-001 | Per blueprint §12.4
FEAT-064 | EPIC-006 | Receive Path (Accept, Authorize, Store, Report) | The receiving half of a transfer: an accept loop started at init, per-connection handling, authorization against the pairing record, manifest validation, re-sealing with the local storage key, a transfer_sessions record, and an arrival the window can read. Commands: get_incoming_transfers, dismiss_incoming_transfer, get_transfer_history. | Tauri Commands / Network Crate | Critical | Done | 100 | 3 | 2 | 2026-09-27 | 2026-09-27 17:40 | Assistant | FEAT-027, FEAT-028 | A workspace sent from one machine is stored on the other, readable with the receiver's own key, and reported to the window with the sender's name and, on refusal, the reason it was refused. 11 two-device tests pass. | This was the missing half of EPIC-006, which was recorded as Done while nothing accepted a connection. See BUG-005.
FEAT-065 | EPIC-006 | Transfer History | A durable record of every transfer this device took part in, written by both ends, surfaced per workspace on the History tab. Answers 'did that actually get there?' after the sending window has closed, and shows a refusal with its reason. | Tauri Commands / DB Crate | High | Done | 100 | 1 | 1 | 2026-09-27 | 2026-09-27 17:40 | Assistant | FEAT-064 | transfer_sessions is written by the sender and the receiver, and the History tab shows both directions of a workspace with status and any recorded error. | transfer_sessions existed since migration 001 with nothing writing to it, so an arriving transfer left no trace. Both ends now record their outcome.
FEAT-066 | EPIC-009 | Arrivals Banner and Refusal Reporting | An arrivals banner on the Workspaces screen showing each arrival with the sender's NAME, not a fingerprint; a refusal shown as prominently as an acceptance and carrying the reason; a dismiss action that clears the notification without touching the stored workspace; and a 'Received' badge distinguishing an arrived workspace from a captured one. | UI - Screens | High | Done | 100 | 1 | 1 | 2026-09-27 | 2026-09-27 17:40 | Assistant | FEAT-064 | 18 tests. Both outcomes are rendered, the sender is named, a refusal announces assertively and an acceptance politely, dismissal sends the transfer id rather than the workspace id, and a failure to read the arrivals list leaves the workspace list intact. | The receiving machine is where the truth about a transfer lives: the sender reports success as soon as the bytes are delivered, so a refusal here is the only place a user can learn the workspace did not land.
FEAT-067 | EPIC-006 | Desktop UI redesign (light + dark) | Rebuilt the window as a desktop app: a real shell (collapsible sidebar, toolbar, status bar), a two-mode token system, a compact type and density scale, and shared primitives. Designed against a Stitch project for DESKTOP device type, with its generated colours rejected on functional grounds and its structure kept. | Frontend / Design System | P1 | Done | 100 | 3 | 3 | 2026-09-27 | 2026-09-28 14:20 | Assistant | None | Both appearances designed and legible; no raw palette colours; one title per page; navigation reachable at the minimum window size; all suites green. | Verified by measurement rather than by eye, because the GUI cannot be captured in this environment: computed styles, contrast ratios and layout geometry were read from a live browser. See LOG-052.
FEAT-068 | EPIC-006 | Design tokens, theme store, and token-migration guard | src/styles/index.css as the single token source (two modes), tailwind.config.js mapped to it with darkMode:'class', src/store/useThemeStore.ts holding theme and sidebar state, a pre-paint script in index.html, and scripts/apply_design_tokens.py to perform and then police the palette migration. | Frontend / Design System | P1 | Done | 100 | 1.5 | 1.5 | 2026-09-28 | 2026-09-28 14:20 | Assistant | FEAT-067 | A new raw palette colour in src/ fails `apply_design_tokens.py --check`. | The --check mode is the point: token drift is invisible in review and trivial to catch in CI once the script is a gate.
FEAT-069 | EPIC-006 | Component primitives rebuilt against the tokens | AppearanceControl (three-state theme selector, shared by the sidebar and Settings), EmptyState/EmptyStateCard, and rebuilt Badge, Button, Card, Dialog and Tabs. Density targets a desktop tool: 28px buttons, 20px badges with 4px corners, cards with a hairline and no decorative shadow. | Frontend / Components | P1 | Done | 100 | 1.5 | 1.5 | 2026-09-28 | 2026-09-28 14:20 | Assistant | FEAT-068 | Every status variant legible in both modes; 64px empty-state circles replaced with a 20px glyph; no shadow-sm on cards. | Badges are rounded, never pill-shaped: a pill on a 20px badge is the visual signature of a web badge rather than a macOS one.
FEAT-070 | EPIC-010 | Windows installer build (on a Windows machine) | `scripts/build_windows.sh` builds a shareable NSIS .exe and .msi on a Windows host. It refuses to run on macOS with an explanation rather than producing nothing, verifies the MSVC host toolchain (cargo defaults to GNU on Windows and fails at link time with an unrelated error), runs `npm ci` so dist/ cannot be stale, checks the inputs the Windows bundle needs, and re-checks that .cargo/config.toml has not regained a build target. | Build / Tooling | P1 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 16:10 | Assistant |  | Script exists, is executable, passes `bash -n`, and its macOS guard and target-pin guard were both tested against fixtures. | Written and guarded, never executed end to end - it cannot be, since the only available machine is a Mac. The guards are the deliverable; the build itself is unproven.
FEAT-071 | EPIC-010 | GitHub Actions Windows installer workflow | `.github/workflows/windows-installer.yml` builds the same installers on windows-latest and uploads them as artifacts, for machines that should not carry a Rust toolchain. Triggers on a `v*` tag or manual dispatch. Passes `tauriConfPath` explicitly, because the config sits beside src-tauri/app/Cargo.toml rather than at the repo root or in src-tauri/, and the action searches only those two default locations. | Build / CI | P2 | In Progress | 50 | 1 | 0 | 2026-09-28 |  | Assistant |  | Not met: the workflow has never been executed. | Deliberately left In Progress at 50% rather than marked Done. It was authored on a machine that could not reach github.com, so not one line of it has run. FEAT-067 was a real case of a tracker row claiming Done while the underlying thing was unverified.
FEAT-072 | EPIC-010 | .gitignore | The project had no .gitignore at all. src-tauri/target is 17 GB and node_modules 257 MB, so the first `git push` - required before CI can run - would have pushed 18 GB. Covers build output, caches, the tracker manifest, and SQLite databases including WAL sidecars. | Build / Tooling | P1 | Done | 100 | 0 | 0 | 2026-09-28 | 2026-09-28 16:10 | Assistant |  | Build output, node_modules, dist and *.db are all ignored. | Found only because CI needed it. The databases matter independently: they hold the user's own manifests.
FEAT-073 | EPIC-010 | macOS release build, DMG, and local install | Produced a native arm64 release build and a DMG, installed the app to /Applications, and got it running with a live transfer listener. Included fixing the bundle signature (BUG-023) and confirming the first successful cross-machine discovery. | Build / Release | P1 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 18:30 | Assistant |  | DMG at src-tauri/target/release/bundle/dmg/, app installed to /Applications, process running, TCP listener bound, zero errors in the app log. | All met. One caveat carried in BUG-023: the DMG on disk predates the signature fix, so it should be rebuilt before being shared anywhere.
FEAT-074 | EPIC-004 | Pairing confirmation without retyping the safety number | Replaced the 45-digit transcription step with a visual comparison: both screens show the number, the user confirms with one button. The screen now also spells out the half the user has to perform on the *other* machine, which is the step that was actually missing during the first live pairing attempt. | Devices / Pairing | P1 | Done | 100 | 0.5 | 0.5 | 2026-09-28 | 2026-09-28 18:45 | Assistant | FEAT-013 | No text input in the pairing dialog; both screens display the number; one button completes pairing; a supplied-but-wrong number is still refused. | Done. The mismatch refusal was kept deliberately: the relaxation is 'no number required', not 'no number checked'. The dialog now also tells the user to start a pairing from the other machine, which is what the first live attempt was missing - that was read as a missing feature rather than a two-sided ceremony, so the instruction is now on screen instead of only in the guide.
FEAT-075 | EPIC-003 | Cross-language field-name contract for IPC payloads | A test that reads the real TypeScript interfaces and compares them against the names serde will accept, so a field renamed in either language fails the build instead of silently producing an empty capture. | IPC / Capture | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 19:40 | Assistant | BUG-024 | Renaming or adding a field in either src/types/index.ts or the Rust IPC structs fails the test suite. Verified by reverting the fix and confirming 3 tests fail, reproducing the user's exact error text. | Done. Added in adapters/tests/ipc_selection_contract.rs, 6 tests: the real UI payload deserializes completely; a misspelled key is refused; Policy reads camelCase and still writes snake_case; a manifest round-trips unchanged; the camelCase convention itself is pinned; and TypeScript field names are compared against serde. The gate exists because BUG-024 was invisible to every check in the build. Honest limit recorded in BUG-024: the field-name comparison alone does not catch removal of the rename_all attribute, which is why the convention has its own test. Both confirmed by revert rather than assumed.
FEAT-076 | EPIC-008 | File snapshot at capture (denylist + size caps) | At capture time every selected project's folder is walked and built into one sorted tar containing everything minus the denylist: version-control internals (.git, .svn), dependency and build output (node_modules, target, dist, build, .next, .nuxt, .output, .turbo, .parcel-cache), caches (.cache, __pycache__), virtualenvs (.venv, venv), Pods, DerivedData, coverage, plus the secret files: .env and .env.*, *.pem, *.key, id_rsa/id_ed25519/id_ecdsa/id_dsa, Thumbs.db, desktop.ini, databases (*.db/-shm/-wal, *.sqlite/*.sqlite3) and logs (*.log), all matched at any depth. Symlinks are skipped. A single file over 128 MiB is skipped with a reason; once the total reaches 512 MiB the walk stops and reports the overflow. The snapshot is the copy that will be re-sent, so re-sending is idempotent. | Core / Files | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 21:30 | Assistant | DEC-031 | Equal folders produce byte-identical archives (sorted entry order, no compression). Every denylisted name is excluded at any depth. An over-cap file is skipped and named. The total cap stops the walk and sets overflow. Every skip and the overflow surface as capture warnings. | New crate src-tauri/files. The capture screen's 'what is never captured' notice and the developer guide now state the denylist explicitly; what is excluded is regenerable build output or secrets.
FEAT-077 | EPIC-006 | File archive on the wire (opaque envelope, chunking unchanged) | send_workspace now wraps the payload: MAGIC (WCFB1) then a u32 LE manifest length, then the manifest JSON, then the archive tar, sent inside the existing framed, acked, encrypted channel. The wire envelope is opaque to transport; nothing about chunk framing or the Noise channel changed. Payloads without the magic read back as manifest-only, so every pre-feature transfer still arrives exactly as before. The accept side's incoming budget is raised to the 512 MiB total cap plus 32 MiB of headroom. | Network / Transfer | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 21:30 | Assistant | DEC-032 | A workspace with files arrives and opens with the receiver's key; a legacy manifest-only payload arrives byte-for-byte as before. The e2e suite proves both directions. | The receive side unseals the archive with its own key, so a received workspace is indistinguishable from a local capture. No relay or additional key exchange was introduced.
FEAT-078 | EPIC-006 | Sealed archive storage + workspace_files table | The sealed archive lives at <data_dir>/files/{id}.files.sealed, sealed with the storage key like the manifest. Migration 003 adds the workspace_files table; the repository records the sealed path, file count, byte count and archive format. The receive path unseals the arrived archive with the receiving machine's own key and stores it the same way, and restore reads it back by workspace id through the same repository. | Tauri Commands / DB | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 21:30 | Assistant | DEC-032 | A captured workspace and a received workspace are stored identically; the files restore by workspace id with no extra configuration. | The archive for a workspace the denylist emptied or that overflowed is still recorded, so the board and the restore report can say what a workspace carries.
FEAT-079 | EPIC-008 | Restore extracts project files | The restore planner adds a required extract-files step for every project with a destination, dependent on its map-path step and ordered before anything that inspects or opens the project. The executor hands the unsealed tar to the archive extractor, which writes each project's entries into its mapped folder overwriting what is there (the snapshot is authoritative), refuses traversal names, absolute paths, backslashes, drive letters, symlinks, reserved Windows device names and oversized entries, and caps the total. The step message reports files written, bytes, refusals and overflow; a workspace captured without files reports an honest success. | Core / Restore | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 21:30 | Assistant | DEC-032 | A project's changed file restores over an existing file. Unsafe entries are refused, not followed or written. 43 restore tests incl. 2 extract tests; the two-device e2e asserts the changed file's content on the receiving machine. | ExtractFiles is a distinct RestoreActionType, so the preview and report render and gate it like any other step instead of it being a hidden side effect. ¦ Restore extracts only for projects without a captured git patch (clean repos keep the archive copy); dirty repos apply their delta instead. 2026-09-30, BUG-037.
FEAT-080 | EPIC-009 | File transfer defaulted on; restore steps rendered | New captures default to file transfer policy 'all' -- the capture screen is the single place the decision is made, and a fresh capture that silently reverted to manifest-only would defeat the feature no matter what the screen said. The restore preview and restore report render the extract-files step with its own icon and status, and classify it as an execution step so the 'commands will run' warning stays honest. The capture screen's 'What is never captured' notice now states the file snapshot's denylist and corrects the stale claim that working-tree files are never copied. | Frontend / Screens | P0 | Done | 100 | 1 | 1 | 2026-09-28 | 2026-09-28 21:30 | Assistant | FEAT-076,FEAT-079 | A capture built from a fresh selection carries files by default. RestoreActionType includes extract_files; preview and report render it; 'commands will run' covers it. | The size caps and the denylist are what keep 'all' safe; manifest-only remains available in the policy type for when per-project selection or a no-files choice is built into the UI.

## Tasks
Task ID | Feature ID | Task Name | Description | Type | Status | Progress % | Est. Hours | Actual Hours | Start Date | End Date | Assignee | Dependencies | Blockers | Error/Issue | Solution/Resolution | Notes
TASK-001 | FEAT-001 | Install Tauri CLI | Install @tauri-apps/cli and initialize project | Setup | Done | 100 | 0.5 | 0.5 | 2026-09-26 | 2026-09-26
TASK-002 | FEAT-001 | Create Tauri 2 Project | Run `cargo tauri init` with React + TypeScript template | Setup | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-001
TASK-003 | FEAT-001 | Configure Rust Workspace | Set up Cargo workspace with core, adapters, crypto, network crates | Setup | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-002
TASK-004 | FEAT-001 | Configure Frontend | Vite + React + TypeScript + Tailwind CSS setup | Setup | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-002
TASK-005 | FEAT-001 | Verify Build (Windows/macOS) | Run `cargo tauri build` on both platforms, fix any issues | Build | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-003, TASK-004
TASK-006 | FEAT-002 | GitHub Actions Workflow | Create CI workflow: lint, typecheck, test, build matrix | CI/CD | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-005
TASK-007 | FEAT-002 | Release Workflow | Automated release on tag: build, sign, package, publish | CI/CD | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-006
TASK-008 | FEAT-003 | ESLint + Prettier Config | Shared config for TS/JS, Rustfmt for Rust | Tooling | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-001
TASK-009 | FEAT-003 | Pre-commit Hooks | Husky + lint-staged for staged files | Tooling | Done | 100 | 0.5 | 0.5 | 2026-09-26 | 2026-09-26 |  | TASK-008
TASK-010 | FEAT-004 | Vitest Setup | Unit test config, React Testing Library, coverage thresholds | Testing | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-004
TASK-011 | FEAT-004 | Playwright Setup | E2E test config for Tauri app | Testing | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-010
TASK-012 | FEAT-004 | Rust Test Setup | cargo test with testcontainers or mock for integration | Testing | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-003
TASK-013 | FEAT-005 | SQLite Schema Design | Design tables for devices, workspaces, snapshots, restore runs, adapter checks | Core/DB | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26
TASK-014 | FEAT-005 | SQLx Migrations | Create migration files for all tables | Core/DB | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-013
TASK-015 | FEAT-006 | Database Encryption | Implement field-level encryption for sensitive data | Core/DB | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-014
TASK-016 | FEAT-007 | Repository Pattern | Type-safe DB access layer with connection pooling, transactions | Core/DB | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-014
TASK-017 | FEAT-008 | Tauri DB Commands | Expose DB operations to frontend via Tauri commands | Core/DB | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-016
TASK-018 | FEAT-009 | Manifest Types | TypeScript + Rust shared types for workspace manifest | Core/Model | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-001
TASK-019 | FEAT-010 | Schema Validation | JSON Schema + runtime validation, version migration | Core/Model | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-020 | FEAT-011 | Secret Scrubber | Redact credentials from URLs, scan for secret patterns | Core/Model | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-021 | FEAT-012 | Capture Preview UI | Show included/excluded fields, toggles for sensitive hints | UI/Capture | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-020
TASK-022 | FEAT-013 | Manifest Versioning | Local snapshots, capture timestamps, no silent overwrites | Core/Model | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-023 | FEAT-014 | Git Adapter | Detect repo root, branch, remote, dirty status, commit hash | Adapters/Git | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-024 | FEAT-015 | VS Code Adapter | Detect install, workspace file/folder, optional extension list | Adapters/VSCode | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-025 | FEAT-016 | Browser URL Adapter | Capture selected URLs, open URLs in target browser | Adapters/Browser | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-026 | FEAT-017 | Terminal Adapter | Detect terminal, cwd, launch recipes | Adapters/Terminal | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-027 | FEAT-018 | Runtime/CLI Adapter | Detect Node, pnpm, Git, Docker, provider CLIs versions | Adapters/Runtime | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-018
TASK-028 | FEAT-019 | Capture Selection UI | Select projects, apps, URLs, optional clipboard/files | UI/Capture | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-023..027
TASK-029 | FEAT-020 | Device Key Generation | Ed25519 keypair, store private key in OS secure storage | Core/Crypto | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-014
TASK-030 | FEAT-021 | Pairing Ceremony | QR code + human-readable code, 5-min expiry, safety number | Core/Pairing | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | TASK-029
TASK-031 | FEAT-022 | Trust Scopes | Receive/send workspaces, optional file transfer, clipboard | Core/Pairing | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-030
TASK-032 | FEAT-023 | Device Management UI | List paired devices, online/offline, rename, revoke | UI/Devices | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-030
TASK-033 | FEAT-024 | Revocation & Deny-List | Local revoke, signed revocation notice, offline deny-list | Core/Pairing | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-030
TASK-034 | FEAT-025 | Rate Limiting | Limit pairing attempts, expire codes, rate-limit discovery | Core/Pairing | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-030
TASK-035 | FEAT-026 | mDNS/DNS-SD Discovery | Advertise rotating device ID + protocol version | Network/Discovery | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-029
TASK-036 | FEAT-027 | Authenticated Channel | Noise protocol with mutual auth, replay protection | Network/Transport | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | TASK-029
TASK-037 | FEAT-028 | Manifest Transfer Protocol | Chunked transfer, progress, cancel, resume | Network/Transfer | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-036
TASK-038 | FEAT-029 | Manual Address Fallback | Enter device address manually | Network/Discovery | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-035
TASK-039 | FEAT-030 | Transfer UI | Select destination, encryption status, progress, cancel | UI/Transfer | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-037
TASK-040 | FEAT-031 | Preflight Engine | Run all check categories, aggregate results | Core/Preflight | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-033, TASK-018
TASK-041 | FEAT-032 | App/Tool Detection | Verify required apps installed, versions | Adapters/Preflight | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-042 | FEAT-033 | Identity Readiness Adapters | GitHub, AWS, Supabase CLI checks | Adapters/Identity | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-043 | FEAT-034 | Repository Checks | Project root mapping, branch state, dirty changes | Adapters/Preflight | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-044 | FEAT-035 | Environment Checks | Check named env vars exist (values never read) | Adapters/Preflight | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-045 | FEAT-036 | Service & Port Checks | Local service availability, port status | Adapters/Preflight | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-046 | FEAT-037 | Permission Checks | OS permissions for features | Adapters/Preflight | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-047 | FEAT-038 | Preflight Report UI | Grouped checks, rerun, prepare actions | UI/Preflight | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-048 | FEAT-039 | Prepare Destination UI | Install links, login buttons, rerun checks | UI/Preflight | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-049 | FEAT-040 | Restore Plan Generator | Map paths, inspect Git, dependency ordering | Core/Restore | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-050 | FEAT-041 | Safe Action Framework | Allow-listed executables, typed args, approval, timeouts | Core/Restore | Done | 100 | 4 | 4 | 2026-09-26 | 2026-09-26 |  | TASK-037
TASK-051 | FEAT-042 | Git Safe Restore | Never auto-stash/reset/clean | Adapters/Git | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-037
TASK-052 | FEAT-043 | App Launch & URL Actions | Open editor, browser URLs (domain preview) | Adapters/Restore | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-037
TASK-053 | FEAT-044 | Command Recipe Execution | Visible terminal, typed recipes, approval, timeouts | Adapters/Terminal | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-038
TASK-054 | FEAT-045 | File Transfer (Optional) | Explicit, path-scoped, size-limited | Core/Transfer | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-038
TASK-055 | FEAT-046 | Clipboard Restore | Off by default, preview, never silent replace | Core/Transfer | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-038
TASK-056 | FEAT-047 | Restore Preview UI | Ordered actions, paths, commands, conflicts, approvals | UI/Restore | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-037
TASK-057 | FEAT-048 | Restore Execution & Report | Execute in order, cancellation, report, retry | UI/Restore | Done | 100 | 3 | 3 | 2026-09-26 | 2026-09-26 |  | TASK-056
TASK-058 | FEAT-049 | Welcome Screen | Explain local operation, install on each device | UI/Welcome | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-001
TASK-059 | FEAT-050 | Devices Screen | Paired devices, online/offline, revoke/rename | UI/Devices | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-032
TASK-060 | FEAT-051 | Workspaces Screen | Recent captures, timestamp, source machine, readiness | UI/Workspaces | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-022
TASK-061 | FEAT-052 | Capture Screen | Select project/app context, inspect included/excluded | UI/Capture | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-028
TASK-062 | FEAT-053 | Transfer Screen | Select destination, encryption status, progress | UI/Transfer | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-039
TASK-063 | FEAT-054 | Preflight Screen | Grouped checks with evidence, rerun, prepare | UI/Preflight | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-064 | FEAT-055 | Prepare Screen | Install links, login buttons, rerun checks | UI/Preflight | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-040
TASK-065 | FEAT-056 | Restore Preview Screen | Ordered actions, paths, commands, conflicts, approvals | UI/Restore | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-061
TASK-066 | FEAT-057 | Restore Report Screen | Success/skipped/failed, actions taken, retry | UI/Restore | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-062
TASK-067 | FEAT-058 | Settings Screen | Capture defaults, clipboard policy, retention, network | UI/Settings | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-001
TASK-068 | FEAT-059 | Named Destination Roots | Configure per-device project root mappings | Core/PathMap | Done | 100 | 2 | 2 | 2026-09-26 | 2026-09-26 |  | TASK-014
TASK-069 | FEAT-060 | Cross-Platform Path Translation | Windows ↔ macOS path mapping, home directory expansion | Core/PathMap | Done | 100 | 1 | 1 | 2026-09-26 | 2026-09-26 |  | TASK-068
TASK-070 | FEAT-061 | Security Audit | Independent review of pairing, key storage, manifest parsing | Security | Not Started | 0 | 5 | 0 |  |  |  | All features done
TASK-071 | FEAT-062 | Signed Releases | Code signing (Windows/macOS), auto-update with rollback | Core/Infra | Not Started | 0 | 3 | 0 |  |  |  | TASK-006
TASK-072 | FEAT-063 | Crash Resilience | Graceful degradation, user-controlled diagnostics | Core/Infra | Not Started | 0 | 2 | 0 |  |  |  | TASK-001

## Bugs
Bug ID | Feature/Task ID | Title | Description | Severity | Priority | Status | Repro Steps | Expected | Actual | Root Cause | Fix | Verified | Reported Date | Resolved Date | Assignee | Notes
BUG-001 | FEAT-054,FEAT-055,FEAT-056 | Route parameter name did not match the name the screens read, so three screens could not load a workspace | App.tsx declared preflight/:transferId, prepare/:transferId and restore-preview/:transferId, while PreflightScreen, PrepareScreen and RestorePreviewScreen all read useParams<{ workspaceId }>(). useParams is generic, so params.workspaceId typed as string and compiled cleanly while resolving to undefined at runtime. All three screens opened showing 'the workspace could not be read'. | Critical | P0 | Fixed | Run the app, open any workspace, and choose Preflight, Prepare or Review restore plan. | Each screen loads the workspace named in the address bar. | The screens rendered their error state: get_manifest was called with workspaceId = undefined. | The param is the workspace id, not a transfer id. The transfer is complete by the time any of these screens is reachable, and on the sending machine none of them apply. A mismatch between a route pattern and a param name is invisible to the type system, to the linter, and to any unit test of a screen in isolation - a screen test mounts the screen directly, so the router is never involved. | Renamed the three route patterns to :workspaceId and documented why the param is a workspace id. Added src/test/routes.test.tsx, which loads the real <App /> at a real URL and asserts the id in the address bar reached the backend. Confirmed the test has teeth by reverting one route pattern: exactly the two preflight tests failed and the prepare and restore-preview tests, whose patterns were untouched, passed. | Yes - 9 route tests pass; tsc --noEmit clean | 2026-09-26 | 2026-09-27 16:20 | Assistant | Found while rewriting the three screens off mock data.
BUG-002 | FEAT-053 | Cancelling a transfer could take fifteen seconds to take effect | The cancel flag was an AtomicBool that the send loop only read at a frame boundary. A send spends nearly all of its time blocked in a read, so cancelling one that was waiting on a silent peer was not noticed until the handshake timeout expired - fifteen seconds - and up to thirty if a frame stalled mid-transfer. The Cancel button appeared to do nothing for as long as the user could bear to look at it. | Major | P0 | Fixed | Start a send to a host that accepts the TCP connection but never answers, then call cancel() on the service after 2ms. Measured how long the send takes to return. | The send returns promptly, reporting Cancelled with a reason. | The send returned after 15.005s, the full HANDSHAKE_TIMEOUT. The loopback test that found this took 15.05s; the other seven took 0.08s combined. | Cancellation was only observed where the code happened to check it, which was between frames, not where the send actually spent its time. A poll on a flag cannot interrupt a blocking read. | Added a tokio::sync::watch channel carrying the cancel flag, and raced every blocking operation in send_inner against it: the connect, the handshake reply, each per-frame acknowledgement, and the final confirmation. A watch rather than a Notify because the flag is resettable and a service is reused for a second workspace - a Notify stores a permit that reset_cancel cannot take back, which made the *next* transfer cancel itself and hung resetting_the_cancel_flag_allows_another_transfer. The test now asserts a latency budget of under two seconds, verified to fail at 15.005s when the notification is removed. | Yes - 64 network lib tests and 8 loopback tests pass; the cancel test reports the old 15s when the fix is reverted | 2026-09-27 | 2026-09-27 16:20 | Assistant | Found by the new loopback transfer test, which is what it was written to find.
BUG-003 | EPIC-005 | Key storage wrote all three secrets under all three credential names, contradicting its own documentation | store_local_keys documented that the three secrets were kept 'each under its own credential so that reading one does not imply access to another', then serialised the whole LocalKeyBundle and wrote that same JSON to device-identity, device-noise and storage-key. Reading any one of the three returned the Ed25519 identity key, the Noise transport key and the manifest storage key together. It also made a partial write - one of the three set_password calls failing - look like a success and yield a device whose identity key was also its transport key. | Minor | P1 | Fixed | Inspect the three credentials named under the workspace-clone service and compare their contents. | Each credential contains one secret, and reading one does not reveal the other two. | All three credentials held byte-identical JSON containing all three secrets. | The implementation was written for an earlier layout and the comment was never updated to match it. The practical exposure on macOS is limited - all three sit in the same Keychain under the same ACL, so a process able to read one can read all three anyway - but the code claimed a separation it did not have, and a comment that is wrong about security is worse than none. | store_local_keys now writes each field to its own credential under its own username and to no other. load_local_keys tolerates the old all-three-identical layout by detecting a leading '{' and parsing the bundle, so an existing installation keeps its identity and does not have to pair every peer again. delete_local_keys was already correct for the new layout. | Yes - 23 crypto tests pass; verified against the live Keychain, which kept the same device id across a relaunch | 2026-09-27 | 2026-09-27 16:20 | Assistant | Found while rewriting the Settings screen, which asserts to the user where their keys are.
BUG-004 | EPIC-011 | Application identifier was the default com.tauri.dev while the database path used a different one | tauri.conf.json carried the default identifier from scaffolding. The database is located through ProjectDirs::from("com", "workspaceclone", "WorkspaceClone"), so the app's data directory and its macOS bundle identity did not match. Nothing failed, because the path is hardcoded rather than derived from the identifier - which is why the mismatch was invisible until something needed the two to agree. | Minor | P1 | Fixed | Compare tauri.conf.json's identifier with the string passed to ProjectDirs. | The two agree, so a bundled or signed build has the identity its data and credentials are filed under. | identifier = com.tauri.dev, data directory com.workspaceclone.WorkspaceClone. | The scaffolded default was never changed, and nothing in the build compared it with the hardcoded path. | Set identifier to com.workspaceclone.WorkspaceClone. Verified the change is safe for an existing installation: the device id was identical before and after, because the Keychain credential is keyed on the service name workspace-clone and not on the bundle id. | Yes - rebuilt and relaunched; same device id, migrations applied, transfer listener bound | 2026-09-27 | 2026-09-27 16:20 | Assistant | Surfaces at signing or notarisation time rather than in development, so it is cheap now and not later.
BUG-005 | FEAT-028,FEAT-030 | There was no receive path at all: the listener was bound and advertised, and nothing ever accepted a connection | The transfer listener was started in init and its port published over mDNS, and no task ever called accept_once. A peer that connected had its socket sit in the kernel accept queue, unauthenticated and unhandled, until the sender's 30-second frame timeout. No payload was read, no workspace row written, and no indication on the receiving machine that anything had happened. Sending a workspace from one machine to another did not work at all, while every existing test passed because all of them drove the sending side. | Critical | P0 | Fixed | 1. Start the app. Note the port in the log: 'Transfer listener bound on port NNNNN'. 2. On another machine, or with a socket client, connect to that port and send a workspace. 3. Observe: the sender eventually reports a frame timeout, and the receiving machine stores nothing. | The receiving machine authenticates the peer, stores the manifest, and shows that a workspace arrived. | The sender times out after about 30 seconds. The receiving machine has no new workspace and no notification. | init bound the listener and advertised the port but never started a task that accepted from it. The receive side of the transfer had never been written; only the send side had. | Added commands/src/receive.rs with a background accept loop started from init. Each arrival is authenticated, authorized, validated, stored sealed with this device's own key, recorded in transfer_sessions, and surfaced to the window through get_incoming_transfers. Covered by commands/tests/two_device_transfer.rs and verified against the running app by RUN-010. | Yes - 11 two-device tests, plus a raw socket connected to the running application was accepted and logged | 2026-09-27 | 2026-09-27 | Assistant | transfer,network,receive,critical,found-by-running-the-app
BUG-006 | FEAT-028 | The payload sent was the sender's sealed manifest, which the receiver holds no key to open | send_workspace transmitted the sealed manifest file, which is encrypted with the SENDING device's storage key. That key never leaves the sender and no peer has it, so the receiver stored bytes it could not read: the workspace appeared in the list and then failed at preflight, with the real cause several steps away from the symptom. A receive path that had existed would have turned a transfer that failed at the protocol level into a failure that looked like data corruption. | Critical | P0 | Fixed | 1. Capture a workspace on device A. 2. Send it to device B. 3. On B, open the workspace and run preflight. Attempt the same read on A, using B's storage key. | The manifest is readable on whichever device stored it, and each device's stored copy opens with that device's own key. | Readable on the sender. On the receiver, the manifest is the sender's ciphertext, and B's storage key cannot open it. | Sealing is protection at rest using the device's own storage key. Sending the sealed file therefore sent bytes no peer can open. Confidentiality in transit is the Noise channel's job, and the receiver re-seals with its own key on arrival. | send_workspace now opens the manifest locally, re-serialises it as JSON, and sends that inside the encrypted channel. The receiver seals it with its own key. See DEC-012. The two-device suite asserts the stored manifest opens with the receiver's key and NOT with the sender's. | Yes - asserted explicitly in two_device_transfer.rs, including a negative assertion on the sender's key | 2026-09-27 | 2026-09-27 | Assistant | transfer,crypto,critical,design-error
BUG-007 | FEAT-028,FEAT-030 | No authorization on either direction: any peer that completed a handshake could send, and any paired device could be sent to | Neither end checked that the other was permitted. A successful Noise handshake established that the peer held a private key; it did not establish that this device had decided to trust that key, or that the peer had been granted the right to push. Likewise send_workspace offered any device, paired or not. The pair row carried trust_scopes and nothing read them. | Major | P0 | Fixed | 1. Pair a device, then clear its scopes. 2. Send it a workspace: the send proceeds. 3. From that device, send a workspace back: it is accepted and stored. | Sending requires the destination to be paired, not revoked, and to hold the receive scope. Receiving requires the sender to be paired on this device, not revoked, and to hold the send scope. | Both directions proceed. A device trusted for nothing can both receive and push. | The trust model was carried in the database but never enforced at either gate. The identity checked is the Noise static key the handshake authenticated, never the device id in a frame header, which is an unauthenticated string anything on the network could set. | Added authorize_destination on the send side and a paired/not-revoked/scope gate in accept_or_refuse on the receive side. Both are covered: an unpaired sender, a sender trusted only to receive, and a revoked sender are each refused for a distinct reason, and the loop survives the refusal. | Yes - four two-device tests, one per gate plus one proving the loop survives | 2026-09-27 | 2026-09-27 | Assistant | transfer,security,authorization
BUG-008 | FEAT-028 | One silent peer delayed every later peer by the full 15-second handshake timeout | The accept loop handled each connection inline, on the listener's own task. Handshake handling is bounded by a 15-second timeout, so a peer that connected and then said nothing held the loop for that whole period. Every other peer that arrived in the meantime queued behind it. Measured, not theorised: the test that exposes this connected a silent socket and watched a legitimate transfer behind it complete in 15.03 seconds instead of immediately. | Major | P1 | Fixed | 1. Connect a socket to the listening port and send nothing. 2. Immediately complete a real transfer from a second peer. 3. Observe it waits for the first connection to time out. | A peer that connects and says nothing affects only its own connection. | Every later peer waits behind the silent one for the handshake timeout. | accept was awaited inline in the loop, so a single slow connection serialised the whole listener. | TransferReceiver was made Clone and gained accept_connection(); the loop now accepts, then hands the connection to its own task and immediately returns to accepting. accept_once and accept_once_with_progress delegate to it, so the single-connection entry points behave the same. See DEC-014. | Yes - a_connection_that_never_speaks_noise_does_not_stall_the_loop, which measured 15.03s before the fix | 2026-09-27 | 2026-09-27 | Assistant | transfer,network,concurrency,found-by-a-test
BUG-009 | FEAT-001,FEAT-049 | The Tauri CLI could not find the application: tauri dev failed with 'No package info in the config file' | tauri.conf.json lived in src-tauri/, whose sibling Cargo.toml is a virtual workspace manifest with no [package] section. The Tauri CLI requires the config's directory to have a sibling Cargo.toml that does have one, so it aborted. The Rust build script disagreed with the CLI: it had an explicit config_path pointing one level up, so cargo build found the config and succeeded. The application therefore compiled and could not be run in development, and the two tools had different ideas about the project layout. | Critical | P0 | Fixed | 1. cd to the project root. 2. Run npx tauri dev. 3. Observe: 'Error: No package info in the config file'. | npx tauri dev starts Vite, compiles the app, and opens the window. | The CLI exits immediately. cargo build works, so the failure looks like a CLI problem rather than a layout one. | The config was in the virtual workspace root while the app crate was in src-tauri/app/. An explicit config_path in build.rs masked the disagreement from the Rust side. | Moved tauri.conf.json to src-tauri/app/, beside the Cargo.toml that has [package]. Removed the config_path override from build.rs, and the path argument from generate_context!, so all three agree on one location. Re-expressed the config's relative paths (frontendDist ../../dist, icons ../icons/...). See DEC-017. | Yes - npx tauri dev starts, compiles, and opens the window | 2026-09-27 | 2026-09-27 | Assistant | build,tooling,critical,found-by-running-the-app
BUG-010 | FEAT-001,FEAT-049 | The application compiled with zero capabilities: the declared permission set was silently discarded | capabilities/default.json existed and declared core:default, but tauri-build globs ./capabilities/**/* relative to the BUILD SCRIPT's directory, which was src-tauri/app/. The file was in src-tauri/capabilities/, so the glob matched nothing. A glob that matches nothing is not an error. The generated app/gen/schemas/capabilities.json was an empty object, so the app shipped declaring no frontend permissions at all, and nothing in the build, the type checker or the test suite said so. | Critical | P0 | Fixed | 1. Read src-tauri/app/gen/schemas/capabilities.json, the file the build writes from the parsed capabilities. 2. Observe: {}. 3. Note that src-tauri/capabilities/default.json declares core:default. | The generated file contains the 'default' capability with core:default. | {} - the app is built with no capabilities. | Same layout divergence as BUG-009: the build script's directory and the directories the other Tauri tooling assumes were different, and a glob silently accepts a directory that does not exist. | Moved capabilities/ to src-tauri/app/capabilities/, beside the build script. The generated file now contains the default capability. The DEVELOPER_GUIDE records that an empty {} there is a bug, not a neutral state. | Yes - app/gen/schemas/capabilities.json contains the default capability with core:default | 2026-09-27 | 2026-09-27 | Assistant | build,security,permissions,silent-failure,found-by-running-the-app
BUG-011 | FEAT-001,FEAT-030 | The application panicked on launch and never opened its window, after advertising itself on the network | serve_forever called tokio::spawn. It is called from Tauri's setup hook, which runs on the main thread with no Tokio runtime entered, and tokio::spawn panics there: 'there is no reactor running, must be called from the context of a Tokio 1.x runtime'. setup is on the startup path, so the panic killed the application on every launch - and after the listener had bound and this device had already announced itself over mDNS, so a peer could discover it, connect to it, and get nothing. Every test in the suite enters a runtime via #[tokio::test], so all of them passed. | Critical | P0 | Fixed | 1. Fix BUG-009 so the app can start at all. 2. Run npx tauri dev. 3. Observe the process exit with the panic above, and no window. | The application starts, opens its window, and logs 'Listening for incoming transfers on port NNNNN'. | Panic during setup. No window. The transfer port was already advertised, so the device looked reachable and was not. | tokio::spawn requires an entered runtime. Tauri's setup hook has none; tauri::async_runtime::spawn enters Tauri's global runtime and works from either context. | Changed the outer spawn to tauri::async_runtime::spawn. The inner per-connection spawn stays tokio::spawn, with a comment recording why the difference is deliberate. Added a plain #[test] that reproduces the startup condition by binding the listener on Tauri's runtime and calling serve_forever with no reactor in scope. | Yes - the regression test panics with the exact production message when the fix is reverted (verified), and the running app starts clean | 2026-09-27 | 2026-09-27 | Assistant | startup,async,critical,found-by-running-the-app,regression-tested
BUG-012 | FEAT-066,COMP-001 | Sidebar was invisible at the shipped window size | Layout.tsx styled the nav `hidden lg:flex`. Tailwind's lg breakpoint is 1024px; the window opened at 800x600 and minWidth was unset, so the sidebar never rendered. The hamburger that was supposed to stand in for it had no onClick at all, so there was no navigation to any screen except /workspaces. | Critical | P0 | Fixed | Open the app at the default window size. Resize below 1024px wide. Observe no sidebar and no working menu button. | Navigation is reachable at every window size the app allows. | Entire nav hidden below 1024px; the fallback control was inert. | A responsive web breakpoint was applied to a fixed-size desktop window, and the window's own default width was never checked against it. | Sidebar always visible, collapsing to a 44px icon rail via a real toggle (persisted to localStorage `wc.sidebar.collapsed`). Window default raised to 1180x780 with minWidth 900 / minHeight 600 and centered, so the window cannot be sized into a state the UI does not handle. | Yes - 2 tests in theme.test.tsx (collapse/expand, persistence) plus a live browser check at 900/1000/1180px: sidebar 208px and all 3 links visible at every width, no element overflowing at 900px. | 2026-09-28 | 2026-09-28 14:20 | Assistant | Found because the window was being resized as part of this redesign, not by any test: every test rendered at jsdom's default 1024px, which is exactly the width where the bug does not appear.
BUG-013 | FEAT-066,COMP-001 | Dark mode was dead CSS - the `dark` class was never applied | index.css carried a full `.dark` block, but nothing ever added the class to <html>. There was no theme state, no toggle and no persistence, so the dark styles could not take effect and the settings screen correctly listed theme as unimplemented. | Major | P1 | Fixed | Inspect the DOM: documentElement.className is always empty. Read styles/index.css: a .dark block exists. | A dark appearance the user can select, and which survives a relaunch. | No theme control and no dark rendering, despite the CSS being written. | The CSS was authored as if a class-based dark mode were already wired up. Nothing generated the class, and nothing tested for it. | New src/store/useThemeStore.ts with a three-state mode (light/dark/system), persisted to localStorage `wc.theme`. applyTheme() toggles `.dark` on <html> and sets colorScheme so macOS scrollbars match. A pre-paint script is inlined in index.html so the choice is applied before first paint. The control appears in the sidebar and in Settings, which no longer claims theme is unimplemented. | Yes - 19 tests in theme.test.tsx, plus live computed-style measurement of all five status families in both modes: fg-on-bg contrast 5.79-9.48 dark, 5.48-6.63 light, all clearing WCAG AA (4.5). Persistence verified by reload in both directions. | 2026-09-28 | 2026-09-28 14:20 | Assistant | Three states rather than a switch: a boolean light/dark toggle makes 'follow the system' unreachable once touched, and a user who wants the OS default back cannot get it.
BUG-014 | FEAT-066 | 84 raw Tailwind palette colours were unreadable on a dark canvas | Screens were styled with the stock palette (bg-yellow-50, text-yellow-800, bg-green-100 and so on). Those are light-mode tints. On the dark surface a light tint behind dark text, or a deep text colour on a dark fill, fails contrast outright - and 'ready', 'needs you' and 'failed' are exactly the colours that carry meaning in the preflight and restore step lists. | Major | P1 | Fixed | Read any preflight step list: status text is set with text-yellow-800 etc. | Status colours are legible in both appearances. | Status colours legible in light mode, effectively invisible in dark. | No token layer existed, so every screen picked colours by hand from the default palette. | Two-mode token set in styles/index.css: five-step surface ladder, four text tiers, two line weights, indigo accent, and four status families (success, warning, danger, neutral) each with fg/bg/border in both modes. All 84 raw colours replaced across 10 files by scripts/apply_design_tokens.py, which is idempotent and has a --check mode that exits non-zero on any leftover. | Yes - apply_design_tokens.py --check reports 0 raw palette colours in src/; a dump of every colour utility in the built CSS bundle shows only token families plus black/white/transparent; contrast measured live in both modes. | 2026-09-28 | 2026-09-28 14:20 | Assistant | Green/amber/red are reserved for status. Stitch's generated palette was rejected on these functional grounds: it spent a green secondary and a brown tertiary on decoration, which would make the status colours ambiguous.
BUG-015 | FEAT-066 | Every screen showed its title twice | The toolbar rendered a title and each screen rendered its own heading with the same words, 20px apart, on all nine routes. On /capture and /restore-report the two matched character for character, so no styling could hide it. A toolbar <h1> alongside a screen <h1> also gave two elements the same accessible name, which is what broke a real getByRole('heading') query in routes.test.tsx. | Minor | P2 | Fixed | Open any route. The title appears in the toolbar and again at the top of the content. | One title per page. | Two, identical, on every route. | The toolbar and the content were each given a title independently, with nothing checking the overlap. | The toolbar owns the page title and is the app's only <h1>, on every route. Screens keep the explanatory line where the heading was. | Yes - 9 parameterized tests in routes.test.tsx assert exactly one <h1> per route and that no h1/h2/h3/h4 in <main> repeats the toolbar title; confirmed live on 6 routes. | 2026-09-28 | 2026-09-28 14:20 | Assistant | Tried a section-vs-step split first (h1 in the toolbar for sections, a breadcrumb for steps). The new test caught that the breadcrumb's last crumb was still identical to the step's own h1 on two routes, so the simpler rule replaced it.
BUG-016 | FEAT-066 | Dialog: Escape never closed it, and className was applied twice | Three defects in one component. handleKeyDown was declared but the effect registered a different closure, so Escape did nothing. className was spread onto both the scrim and the panel, so a caller's padding landed on the overlay as well. And `if (!open) return null` sat above a useEffect, a hooks-order violation that would throw if a dialog were ever opened and closed. | Major | P1 | Fixed | Open any dialog, press Escape. Nothing happens. | Escape closes the dialog. | Escape is ignored. | The handler was written once and a different inline closure wired to the listener. | Rewrote Dialog.tsx: one handler actually registered, className on the panel only, early return moved below every hook. | Yes - tsc clean, 83 frontend tests pass, dialogs exercised in the live browser with zero console errors. | 2026-09-28 | 2026-09-28 14:20 | Assistant | Found by reading the component while restyling it, not by a failing test.
BUG-017 | FEAT-070,FEAT-071 | A pinned build target made every cargo command fail on Windows | `.cargo/config.toml` at the project root set `[build] target = "aarch64-apple-darwin"`. Cargo applies that setting to every invocation from anywhere inside the repository, on every host -- it is not scoped to the machine it was written on. On the Windows laptop, `cargo build` would attempt to compile for Apple Silicon and fail before compiling a single crate. The same setting also forced build output into a triple-named subdirectory, which made the whole tree look hand-pinned for macOS. | Critical | P0 | Fixed | On any machine that is not an Apple Silicon Mac, run `cargo build` from anywhere in the project. It targets aarch64-apple-darwin. | A build on any host produces a binary that host can run. | Every cargo command on a non-Apple-Silicon host failed at the target-selection step. | A host-specific assumption was committed as a global, silently-inherited setting. It was correct on the one machine it was written on, which is exactly why it survived. | Removed `[build] target` from .cargo/config.toml, leaving a comment explaining why the absence is deliberate. Documented passing the triple explicitly (`cargo build --target ...`) as the supported alternative, added a section 15 convention, and added a guard to scripts/build_windows.sh that strips comments before testing for a reintroduced pin and refuses to run if one is present. | Yes for the mechanism: `cargo build --workspace` on the Mac produces target/debug/app, and the guard was tested against three fixtures - a pinned file blocks, a clean file passes, and a file whose *comment* mentions the setting passes. The Windows failure it prevents is by construction, not observed. | 2026-09-28 | 2026-09-28 16:10 | Assistant | The only one of the five that is provably correct without a Windows machine: the behaviour it removes is host-independent by definition.
BUG-018 | FEAT-070 | A Windows machine named itself "This Mac" | `hostname()` in commands/src/lib.rs read the HOSTNAME environment variable, then fell back to `uname -n`, then to the literal string "This Mac". HOSTNAME is a bash export and is not set on Windows; `uname` is not a Windows executable. So every Windows machine reached the final fallback and was listed as a Mac. The function's own doc comment states the fallback exists so that two machines are distinguishable in a device list, which is the whole task this app performs. | High | P1 | Fixed | Build and pair on Windows. Both devices show the name "This Mac". | A Windows laptop names itself, e.g. from COMPUTERNAME. | Named "This Mac", identically on both machines. | Platform-specific knowledge encoded as a string literal instead of a lookup, with no test covering the non-macOS path because the suite only ever runs on macOS. | Read COMPUTERNAME as well, and split the platform-independent selection into `resolve_hostname(hostname_env, uname_output, computer_name_env)`. The split is what makes it testable: reading the process environment is global mutable state, and a test that set HOSTNAME to prove the Windows path would race every other test in the binary. The final fallback is now "This device" so it cannot claim an OS. | Yes, on a real machine. The Windows laptop advertises itself as 'BISWAJITA' in its mDNS record, which is COMPUTERNAME. Before the fix it would have announced 'This Mac'. The 7 unit tests cover the selection logic; this line is the field evidence that the fix reaches the wire. | 2026-09-28 | 2026-09-28 16:10 | Assistant | Was written as 'by inspection only'. Now confirmed: the device name on the laptop is its real computer name. Corrected 2026-09-28 after the first live two-machine discovery.
BUG-019 | FEAT-070 | Per-user VS Code installs on Windows were reported as absent | The VS Code adapter's Windows fallback list contained the path `C:\Users\USERNAME\AppData\Local\Programs\Microsoft VS Code\bin\code.cmd`, with USERNAME as a stand-in for the account name. Nothing expands it: `Path::exists()` reads it as a real directory literally named USERNAME. The check always failed, so the per-user install - which is VS Code's default when the account has no administrator rights, i.e. most laptops - was never detected. | High | P1 | Fixed | On a Windows machine where VS Code is installed per-user and not on PATH, run a capture. The manifest records the editor as unavailable. | A per-user VS Code install is found and recorded in the manifest. | Recorded as absent; the preflight screen then instructed the user to install an editor they already had. | A documentation-style placeholder was written into a literal that a filesystem call treats as data. The failure mode is a false negative in a probe, which is worse than a crash: it produces a confidently wrong instruction instead of an error. | Split the fallback into `find_vscode_well_known()` per platform. The Windows version checks Program Files and Program Files (x86), then builds the per-user path from %LOCALAPPDATA% and %APPDATA% via `env::var_os`, so no account name is ever embedded in a literal. | Still partial. The Windows branch now compiles and the build completes, so the earlier 'cannot even be compiled here' caveat is gone. But the probe's result is unverified until a capture is actually run on the laptop - a build that succeeds says nothing about whether Path::exists() finds the per-user VS Code path. | 2026-09-28 | 2026-09-28 16:10 | Assistant | The claim to test is still the one that matters: capture on the laptop and check whether the manifest reports its editor as present.
BUG-020 | FEAT-070 | OS version degraded to the bare string "windows" | Two independent `os_version()` implementations - one in commands, one in adapters/traits - had macOS and Linux branches and no Windows branch, so on Windows both returned `std::env::consts::OS`, the literal "windows". The adapters copy feeds the manifest, and its doc comment warns that an unknown value 'would silently weaken every portability decision made later'. | Low | P2 | Fixed | Capture a workspace on Windows; the manifest's os_version reads "windows". | A recognisable version, e.g. "Windows (build 22631)". | The literal string "windows", with no version information at all. | Platform branches were added per platform as each platform was worked on; Windows was never worked on. | Both functions now read RUSTVERSION, which is a real Windows environment variable, and format it as "Windows (build NNNNN)". Read from the environment rather than compiled in, because the OS is upgraded underneath a running app and a constant would go stale. | Partially. The laptop's mDNS record carries os=windows, so the branch compiles and runs. Whether the os_version() field itself reads a build number rather than the bare string is not yet observable from here - the TXT record uses a different, lowercase field. | 2026-09-28 | 2026-09-28 16:10 | Assistant | Two separate fields both claim to be the OS name. The mDNS TXT 'os' is a lowercase slug and is not the same value as os_version(); worth reconciling so a manifest and a discovery record agree.
BUG-021 | FEAT-070 | Edge was absent from the Windows browser probe | The browser adapter's Windows candidate list contained Chrome and Firefox but not Edge, which is installed on every supported Windows release and is the system default. A machine with only Edge would be recorded as having no browser installed. | Low | P2 | Fixed | On a Windows machine with only Edge, capture a workspace. | Edge is detected as an available browser. | No browser found, and the manifest said so. | The browser list was written per platform from developer machines, and no developer machine had only Edge. | Added both Edge install paths (x86 and native). Edge is Chromium-based, so it stands in wherever only the path scheme matters. | No. Edge detection is only exercised by a capture on the laptop. The build success is not evidence about it. | 2026-09-28 | 2026-09-28 16:10 | Assistant | Unchanged in substance: still waiting on a capture on Windows.
BUG-022 |  | Tasks sheet has 10 duplicated IDs and 67 rows with dependencies in the wrong column | Two independent defects in the Tasks sheet, both pre-existing and neither caused by this round. (1) Ten task IDs are each used twice. Rows 2-41 are TASK-001..TASK-040 against FEAT-001..FEAT-031; rows 42-73 restart at TASK-031 and run to TASK-060 against FEAT-032..FEAT-063. The 14 rows in the overlap therefore name two different tasks each -- TASK-031 is both 'Trust Scopes' (FEAT-022) and 'App/Tool Detection' (FEAT-032). (2) In 67 rows, a dependency list such as 'TASK-003, TASK-004' sits in the Assignee column while the Dependencies column is empty; only 3 rows have it correctly placed. TASK-049 and TASK-051 do not exist in either batch. | Medium | P2 | Fixed | Open the Tasks sheet. Sort by Task ID, or follow any dependency pointing at TASK-031..TASK-040 -- both are ambiguous. | Every task ID unique; dependency lists in the Dependencies column. | 14 rows share an ID with another row, and 67 rows carry their dependencies under the Assignee header. | Rows were added in at least two passes and the second pass restarted its numbering at 031 instead of continuing at 041, with no uniqueness check. The column offset comes from a writer whose field order differs from the generator's by one position. create_tracking.py is not the source of truth here: it only emits 12 task rows, so the other 60 were added by something else and left no artifact to reconcile against. | Rows 42-73 renumbered TASK-031..TASK-060 -> TASK-041..TASK-072 in row order, so every ID is unique. The 67 dependency lists sitting in the Assignee column moved to the Dependencies column (38 first-block + 29 second-block rows; the sheet already had 3 in the right column). References remapped by the first-occurrence rule: labels only present in the second block (TASK-041..060) resolve to their renumbered first occurrence; ambiguous labels present in both blocks resolve to the canonical first block and stay as written. | ID uniqueness, column placement and reference remap all re-checked by script asserts on 2026-09-28. Residual caveat recorded in LOG-087: the dependency VALUES were bulk-populated and their semantics remain the author's intent, not a derived DAG. | 2026-09-28 | 2026-09-28 | Assistant | Consequence for anyone using the tracker: a dependency chain read off this sheet can be silently wrong, so do not plan work from the Tasks graph until this is repaired. Needs a decision on the intended numbering, not a cleverer script.
BUG-023 | FEAT-073 | Bundled .app had no bundle-level signature, so its resource seal was invalid | `npx tauri build` produced a .app whose Mach-O was linker-signed (ad-hoc) but which had no Contents/_CodeSignature directory at all. The binary's own CodeDirectory claimed resources were sealed, while the bundle carried no resource envelope to match, so `spctl -a -vvv` reported 'code has no resources but signature indicates they must be present'. | Medium | P1 | Fixed | Build with `npx tauri build` on a machine with no code signing identity, then run spctl -a -vvv on the resulting .app. | A bundle whose resource seal is internally consistent. | A broken seal, and the failure mode users report as 'the app is damaged and cannot be opened'. | No signing identity is configured on this machine (0 valid identities), and the bundler did not fall back to sealing the bundle ad-hoc even though it had no choice but to leave it unsigned. | Fixed at source by setting `bundle.macOS.signingIdentity` to `"-"` in src-tauri/app/tauri.conf.json, which tells Tauri to ad-hoc sign. The bundler now emits Contents/_CodeSignature/CodeResources on its own and logs 'replacing existing signature'; `codesign -v` passes on a freshly built bundle with no manual step. The earlier `codesign --force --sign -` on the installed copy was the manual workaround and is no longer needed. | Yes, and this time at source rather than by hand. After adding the config, a clean `tauri build` produced a bundle whose _CodeSignature exists and whose `codesign -v` passes, with no manual codesign step. The original symptom is gone: spctl no longer reports 'code has no resources but signature indicates they must be present', only the expected 'rejected', which is the distribution verdict for an ad-hoc signed unnotarized app and does not affect local launch. | 2026-09-28 | 2026-09-28 18:30 | Assistant | Was written as 'not yet fixed at source - the DMG predates the fix'. Both statements were superseded within the hour by the signingIdentity change, and the DMG has been rebuilt since. Corrected 2026-09-28. What remains true: this is ad-hoc signing, so a DMG copied to a different Mac is still quarantined by Gatekeeper and needs right-click -> Open. Ad-hoc signing cannot fix that; only notarisation would.
BUG-024 | FEAT-075 | Sending a workspace failed: missing field `file_transfer` | The first capture-to-send attempt between the two real machines failed with `invalid args `selection` for command `capture_workspace`: missing field `file_transfer``. The error names a field the UI was in fact sending, so fixing that one field would have produced a second error immediately after. | Critical | P0 | Fixed | On the Mac, capture a workspace and send it to the paired laptop. The command rejects the payload before the capture begins. | The selection deserializes and the workspace transfers. | The command was rejected before the capture began, with a message naming `file_transfer` -- a field the UI was sending, under the name it was also sending. Every misnamed list field would have arrived empty, so a capture that got past this would have silently dropped selected projects and pasted URLs while still reporting success; the URLs vanishing would have pointed at the browser adapter, four functions from the actual cause. | The capture never started. Rust read the selection as snake_case (`include_applications`, `browser_urls`, `source_path`) and the UI wrote it as camelCase (`includeApplications`, `browserUrls`, `sourcePath`). `CaptureSelection` in adapters/src/traits.rs was the one IPC-boundary type missing `#[serde(rename_all = "camelCase")]`; that convention is applied in 9 other places, all in commands/src/. Because serde ignores unknown keys, all five misnamed fields arrived as empty lists rather than errors, and only the nested `Policy` failing on the first missing field in its declaration order stopped the command -- so the error named a field the caller was also sending. | Added `#[serde(rename_all = "camelCase", deny_unknown_fields)]` to `CaptureSelection`, `SelectedProject` and `ApprovedCommand` -- all eleven affected fields across all four types, not only the one reported. `Policy` took per-field `alias`es instead (DEC-029), because it is also the manifest's policy: a blanket rename would have fixed the input and silently rewritten the manifest wire format. `deny_unknown_fields` closes the worse half of the bug (DEC-030). | Yes, at source. Confirmed by reverting the fix and re-running the new contract test: 3 of 6 tests fail, reproducing the user's exact error text, `missing field `file_transfer``. | 2026-09-28 | 2026-09-28 19:40 | Assistant | Three gates were green while this was live: tsc checks TypeScript against its own types, cargo test builds the struct in Rust where naming is irrelevant, and check_command_parity.py compares command *names*. The bug lived in the space between them, so FEAT-075 puts a gate there. Honest limit found while testing the new gate: the field-name comparison alone did NOT catch removal of the rename_all attribute, because it converts snake_case to camelCase first and so agreed either way. A separate test pins the convention directly. Both were confirmed by revert, not assumed.
BUG-025 | FEAT-075 | Discovered devices listed with the mDNS service type glued to the name | The paired laptop appeared in the device list as `BISWAJITA._workspace-clone._tcp` rather than `BISWAJITA`. | Low | P2 | Fixed | Pair a device and open the Devices screen. | The device is listed under the name its owner chose. | The name carried `._workspace-clone._tcp`. | `parse_discovered_device` took the mDNS full name and stripped the trailing dot and the `.local` domain, but never the service type. The comment beside that code said the goal was a name that helps a person recognise their own machine -- so the code was the bug the comment was warning about, not the one it described. | Extracted `instance_display_name`, which strips the whole service suffix (case-insensitively, since mDNS names are) rather than a `.local` substring, and hoisted the service type to a `SERVICE_TYPE` constant used by both registration and parsing so the two halves cannot drift. Substring stripping was avoided deliberately: a Mac genuinely named `ABHISHEKs-MacBook-Air.local` must keep its `.local`, or the app would rename a device to something its owner never chose. | Yes, and the test that was green while the bug was live was the tell. | 2026-09-28 | 2026-09-28 19:10 | Assistant | `the_display_name_is_not_a_dns_name` already existed, asserted that the name has no trailing dot and no `.local`, and passed throughout. It checked two properties that happened to hold while missing the one that was wrong. It now asserts the exact expected value, plus four new cases: a display name that itself ends in `.local`, mixed-case service types, an unrecognised full name, and a degenerate one that must not reduce to empty. The last two guard the 'never lose a device to a naming quirk' rule. Confirmed the strengthened test fails on the old code.
BUG-026 | FEAT-075 | Send failed: 'No device with id ... is currently reachable' for a device the UI showed as on-network, paired and allowed to receive | The first real send attempt on the Mac against the paired laptop failed before a socket was ever opened, with: Network error: Connection failed: No device with id 'hnODGDVs/oYDiOhuQO941A==' is currently reachable. Check that it is running, on the same network, and that discovery has found it on this screen. The device the message denied seeing was simultaneously listed on the very screen the user was looking at, shown as on-network, paired, and permitted to receive. | Critical | P0 | Fixed | On the Mac, with the laptop discovered (the Send button enabled), click Send workspace. | The send starts and the transfer proceeds. | The send failed with 'No device with id ... is currently reachable' -- the wording telling the user discovery had not found the device, when the screen it told them to check was proving the opposite. | send_workspace resolved its destination only from TransferService::known, a second map fed exclusively by remember_device() -- a method nothing in the workspace ever calls, let alone a command. known was therefore empty for the whole lifetime of the process, so every send failed here regardless of what discovery knew. Discovery's own map, the one get_discovered_devices reads and the mDNS browse loop actually fills, was never consulted. The comment above the lookup even claimed peers are found 'in two places ... what discovery has seen on the network right now, and what a previous command recorded' -- only one lookup existed and it read the wrong map. The e2e integration test stayed green because it hands a hand-built peer record straight to TransferService::send_workspace and never exercises the command's destination resolution. | Resolve the destination from the discovery service's map first (the map the browse loop writes and get_discovered_devices reads), with TransferService::known as the fallback for a record whose mDNS entry has expired. Extracted as a pure function resolve_destination(from_discovery, remembered, device_id) per DEC-026 so the two-source rule is testable; the payload/authorization steps are unchanged and happen before the transfer lock, and the discovery lookup happens before the transfer lock so the two locks are never nested. The error message now distinguishes being unreachable from being untrusted, and no longer tells the user to verify on the screen that shows the device. | Yes, at source, by revert. Restoring the shipped order (only the remembered map consulted) fails two of the four new tests: a_send_resolves_a_destination_that_only_discovery_can_see and discovery_wins_over_a_stale_remembered_record. With the fix, all 66 commands-lib tests and all 374 workspace tests pass. An earlier attempt that merely swapped the or_else order also failed the discovery_wins test -- so the order rule has teeth as well as the primary-source rule. | 2026-09-28 | 2026-09-28 20:22 | Assistant | Also added DiscoveryService::insert_for_test (cfg(test) only) so a test can prove get_device reads the same map the browse loop writes. The four tests: discovery alone resolves a send (the real Field state: remembered is None), discovery beats a stale address, a remembered peer survives record expiry, and a device in neither map is refused without the self-contradicting wording.
BUG-027 | FEAT-040 | Restore appends the source machine's folder name to the destination the user typed | Restoring the transferred workspace on the Windows laptop: the user typed E:/workspace-clone as the destination folder and the plan produced E:/workspace-clone/openshorts. The extra 'openshorts' is the project's manifest name, which is simply the last folder of the source path on the Mac (Documents/openshorts). The source machine's folder name was leaked onto the destination layout, where it means nothing, and the restore report then asked the user to go and create a folder they never named. | Medium | P1 | Fixed | On the receiving machine, open a restored workspace, click Restore, type E:/workspace-clone as the destination for a bucket whose single project came from ~/Documents/openshorts, and inspect the plan. | The typed folder is the project's destination: the code lands in E:/workspace-clone, exactly as written. | The plan step read 'openshorts maps to E:/workspace-clone/openshorts' -- the chosen root with the source folder name appended. | resolve_destinations always resolved root.join(project.name). project.name comes from the source machine (the capture derives it from the selected folder), so a root the destination user chose was silently treated as a parent folder, and every bucket got a subfolder named after something local to the other machine. The reuse was deceptive: on the sending machine the name is the project folder (sensible), on a different machine's layout it is arbitrary. BUG-027 is the first restore-place failure seen on two real machines; the two-device tests all used synthetic names on one layout, so the leak never showed. | resolve_destinations now counts the projects per bucket: a bucket holding exactly one project uses the chosen folder itself as that project's destination (the user's typed path is the folder the code lands in -- no append, and the manifest name is not consulted at all, which also makes a solitary bucket immune to a hostile name); a bucket holding several projects nests each beneath the chosen folder via the existing safe_child gate, so collisions are avoided and nothing can escape the chosen root. Same-name collisions in a crowded bucket now emit a warning. The plan preview copy explains the rule, and per-project steps still show the exact final path before anything runs. | Yes. a_single_project_lands_exactly_in_the_folder_typed reproduces the user's exact case and fails on the old code (it asserted .../openshorts). Revert-verified: restoring root.join(name) for a solitary project fails that test plus a_solitary_project_ignores_a_hostile_name. 377 Rust tests, 99 vitest, tsc clean. | 2026-09-28 | 2026-09-28 20:40 | Assistant | User's decision (2026-09-28): exact folder for one project; nested only when a bucket holds several. Frontend copy in RestorePreviewScreen updated to state the rule. The laptop needs this fix for the restore side: planner.rs + RestorePreviewScreen.tsx must reach the Windows build.
BUG-028 | FEAT-028 | Mac send fails with "No route to host" against the laptop's link-local IPv6 address | First real two-machine send from the Mac to the paired Windows laptop (BISWAJITA) failed before any data moved, twice in a row: Network error: Connection failed: Could not reach fe80::f727:abc9:2280:4f3:54108: No route to host (os error 65). The laptop was listed, paired and Send was enabled, so the failure was entirely on the connect side. | Critical | P0 | Fixed | On the Mac, with the laptop discovered by mDNS, paired, and allowed to receive, click Send workspace. | The send starts and the transfer proceeds. | The send failed with Could not reach fe80::f727:abc9:2280:4f3:54108: No route to host (os error 65) while the device was sitting on the same screen, on-network. | send_inner connected only to destination.addresses.first() as a bare string. mdns-sd's get_addresses() returns IpAddrs with no zone information, and the laptop's mDNS record listed its link-local IPv6 address (fe80::/10) first. A link-local address names the link, not a destination; macOS refuses to guess which local interface the peer is on and returns ENETUNREACH before any SYN is sent. The transfer listener also bound IPv4-only (0.0.0.0), so even a correctly scoped IPv6 attempt could never have been served. | Every advertised address is now a connect candidate instead of only the first. IPv4 candidates come first (mDNS peers share a link, so IPv4 almost always just works). A bare link-local IPv6 is expanded into one scoped address per local link-local interface (fe80::x%en0 scope ids, via the new if-addrs dependency) so the connect is real instead of unroutable, and a hand-typed %zone in manual pairing is trusted as given. The candidates are raced with futures select_ok under the single existing 10 s connect budget (cancel-aware as before), first success wins, and the error names the address that refused. connect_manual uses the same candidates with its 5 s budget. The transfer listener now prefers a dual-stack bind ([::] with IPV6_V6ONLY off, via socket2, which was already in the lockfile), falling back to the old 0.0.0.0 bind, so a peer connecting over its link-local IPv6 address can be served. | Yes, at source. 11 new tests take the network crate from 68 to 79: IPv4 is ordered first however the record lists addresses; a link-local address is scoped to each local link-local interface; a hand-typed %zone is kept as a single candidate; a numeric zone survives; a global IPv6 passes through unscoped; duplicates and unreadable entries are dropped; a dead first candidate does not block a live one; a refusal names the address; the dual-stack listener serves an IPv4 loopback connect through either family of bind. On this Mac the listener binds [::] yet still serves 127.0.0.1. Full suite: 405 Rust tests, 0 failures, cargo build --workspace warning-free. The real two-machine retest needs the new build on BOTH laptops; the reverse (Windows->Mac) direction is still unproven on hardware. | 2026-09-28 | 2026-09-28 | Assistant | The reported address as copied reads fe80::f727:abc9:2280:4f3:54108, whose final group has five hex digits; std rejects it and only the kernel resolver accepts it -- the fix does not depend on the exact spelling, and unparseable entries are skipped in favour of the addresses that do parse. Laptop retest steps: git pull, rebuild + reinstall the .exe on Windows, then send Mac->Windows and Windows->Mac.
BUG-029 | FEAT-051 | A workspace that arrives while the Workspaces screen is open stays invisible in the list until the user switches menus | Post-BUG-028 retest on hardware. Sending 'Testing Window - Mac' from the paired Windows laptop (BISWAJITA) to the Mac completed: the green arrival banner appeared at the top of the Workspaces screen, but the new workspace was not in the list below. Navigating to another menu and back made it appear. The workspace is stored correctly by the backend; the window just never asked for the list again. | Medium | P1 | Fixed | Receive a workspace (any direction) while sitting on the Workspaces screen with the list already fetched, then look at the list without navigating. | The accepted workspace appears in the list as soon as it arrives. | The green banner appeared but the workspace only materialised in the list after a manual navigation that remounted the screen. | The workspaces query (['workspaces']) is fetched on mount and was never invalidated. The arrivals poll (['incoming-transfers'], ARRIVALS_POLL_MS) is the channel that proves something arrived, so a UI with no listener meant the list kept serving its pre-arrival snapshot until something forced a refetch. | WorkspacesScreen now watches the arrivals poll for a previously unseen *accepted* arrival with a workspace id and invalidates ['workspaces'] at that moment, so the list refetches right away. Seen transfer ids are tracked in a ref so a restart or re-render does not re-invalidate; refusals do not invalidate (nothing was stored). | Yes, at source. New vitest 'puts a workspace that arrived after load into the list without a remount' drives the poll to flip from empty to a landed arrival and asserts list_workspaces is invoked again and the new workspace renders with no navigation. Suite: 100 frontend tests (was 99), tsc --noEmit clean. | 2026-09-29 | 2026-09-29 | Assistant | Found by inspecting the live Mac DB after the retest: workspace bbb38119 (name 'Testing Window - Mac') was stored correctly with source BISWAJITA, so the data was always there and only the window's cache was stale. Same fix covers the reverse direction.
BUG-030 | FEAT-051 | Delete workspace does nothing on both Mac and Windows | Deleting a workspace from the Workspaces list leaves it in place. Reported for both machines after the handoff. The row stayed put, and so did the sealed manifest (and file archive) on disk. | Medium | P1 | Fixed | Capture or receive a workspace (a received one with files is the strongest repro), then click the trash button on its card. | The workspace leaves the list; its sealed manifest (and its sealed file archive, when files were carried) is removed from disk. | Nothing happened: the row remained and the files remained. No error was surfaced anywhere. | WorkspaceRepository::delete was a bare `DELETE FROM workspaces WHERE id = ?`. `workspace_files`, `snapshots`, `restore_runs` and `transfer_sessions` all hold real foreign keys to workspaces(id) and the pool enforces them, so every workspace with a file archive, a snapshot or a transfer record violated a constraint and the mutation silently failed. | WorkspaceRepository::delete now removes the four referencing tables for the workspace inside one transaction, then the workspace row. The delete_workspace command additionally removes the sealed manifest and the `.files.sealed` archive from disk, tolerating an already-missing file and warnings (never failing the committed delete) otherwise. | 2026-09-29 | 2026-09-29 | Assistant | Validated in the rebuilt app on the live Mac DB: deleting a received workspace removed its row (confirmed with sqlite3) and its manifest file (confirmed with ls). Two new db-crate tests pin the cascade for workspace and device deletes.
BUG-031 | FEAT-051 | Arrival banner shows an empty sender name ("arrived from") | After a successful Windows->Mac transfer the green banner renders the workspace name and the sender name blank on the receiving machine. | High | P1 | Fixed | Receive a workspace from the paired Windows laptop and read the green arrival banner. | The banner reads "'<workspace>' arrived from BISWAJITA". | The banner showed an empty name after 'arrived from'. | the TS IncomingTransfer interface is renamed to the camelCase keys serde actually emits (transferId, workspaceId, workspaceName, senderDeviceId, senderDeviceName, sourceDeviceId, refusalReason, transferDigest, bytesReceived, receivedAt), the banner, the dismissal and the preflight link read those names, and the fake-backend fixtures are camelCase so tests exercise the real wire shape. The name render was `arrival.sender_device_name`, but serde emits `senderDeviceName`, so the value was undefined. | the TS IncomingTransfer interface is renamed to the camelCase keys serde actually emits (transferId, workspaceId, workspaceName, senderDeviceId, senderDeviceName, sourceDeviceId, refusalReason, transferDigest, bytesReceived, receivedAt), the banner, the dismissal and the preflight link read those names, and the fake-backend fixtures are camelCase so tests exercise the real wire shape. | 2026-09-29 | 2026-09-29 | Assistant | Root cause confirmed on the producer side with a new Rust test asserting IncomingTransfer serializes no snake_case key, and on the consumer side with a new frontend test that renders an exact camelCase payload.
BUG-032 | FEAT-051 | Arrival banner's dismiss (close) button is inert | Clicking the X on the green arrival banner does not dismiss it. | Medium | P1 | Fixed | Receive a workspace, then click the close button on its banner. | The banner disappears and the workspace stays stored. | The banner stayed on screen. | dismiss.mutate used `arrival.transfer_id`, which is undefined on the wire (the key is `transferId`), so the backend was asked to dismiss a transfer it does not know and nothing changed. | the TS IncomingTransfer interface is renamed to the camelCase keys serde actually emits (transferId, workspaceId, workspaceName, senderDeviceId, senderDeviceName, sourceDeviceId, refusalReason, transferDigest, bytesReceived, receivedAt), the banner, the dismissal and the preflight link read those names, and the fake-backend fixtures are camelCase so tests exercise the real wire shape. | 2026-09-29 | 2026-09-29 | Assistant | The dismiss path sends the camelCase transferId now; the new wire-shape frontend test asserts dismiss_incoming_transfer receives `transferId` for the arrival.
BUG-033 | FEAT-051 | "Open preflight" on a successful arrival does nothing | Clicking the banner's 'Open preflight' link does not open the preflight screen. | Medium | P1 | Fixed | Receive a workspace and click 'Open preflight' on its banner. | The app navigates to preflight for the workspace that arrived. | Nothing happened. | The navigation guard read `arrival.workspace_id` (undefined on the wire; the key is `workspaceId`) so `accepted && workspace_id` was always false and the handler fell through to the no-op branch. | the TS IncomingTransfer interface is renamed to the camelCase keys serde actually emits (transferId, workspaceId, workspaceName, senderDeviceId, senderDeviceName, sourceDeviceId, refusalReason, transferDigest, bytesReceived, receivedAt), the banner, the dismissal and the preflight link read those names, and the fake-backend fixtures are camelCase so tests exercise the real wire shape. | 2026-09-29 | 2026-09-29 | Assistant | New frontend test opens the banner of an arrival and asserts the preflight screen is reached for that workspace's id (get_manifest called with ws-1).
BUG-034 | FEAT-051 | Workspace list does not refresh when a transfer arrives | The BUG-029 fix (invalidate ['workspaces'] on a newly-seen accepted arrival) does not fire: a workspace that arrives while the Workspaces screen is open still needs a menu change to appear. | Medium | P1 | Fixed | Receive a workspace while sitting on the Workspaces screen with the list already fetched. | The accepted workspace appears in the list as soon as it arrives. | Still needed a navigation to remount the screen, exactly as before BUG-029. | The BUG-029 effect filtered on `a.accepted && a.workspace_id && ...`, and `a.workspace_id` is undefined on the real wire (the key is `workspaceId`). The guard was false for every arrival, so the invalidation never ran. BUG-029 passed in tests because the fake backend used snake_case fixtures that matched the wrong type. | the TS IncomingTransfer interface is renamed to the camelCase keys serde actually emits (transferId, workspaceId, workspaceName, senderDeviceId, senderDeviceName, sourceDeviceId, refusalReason, transferDigest, bytesReceived, receivedAt), the banner, the dismissal and the preflight link read those names, and the fake-backend fixtures are camelCase so tests exercise the real wire shape. The effect now reads the camelCase ids (workspaceId, transferId) so the guard holds. | 2026-09-29 | 2026-09-29 | Assistant | Same root cause and fix as BUG-031/032/033. Validated by the wire-shape frontend test plus the existing poll-driven list-refresh tests, which now exercise the real key names.
BUG-035 | FEAT-050 | Devices page shows this machine among the devices | The Devices page lists this laptop itself in the devices area, alongside (or instead of being clearly about) the machines it is actually paired with. | Medium | P1 | Fixed | Open the Devices page and look at the device list. | Only actually-paired peer machines are listed; this machine appears nowhere on the page. | This machine (the Mac) appeared in the list of devices. | This device keeps a row in the `devices` table (workspaces.source_device_id is a foreign key that needs a row to point at), and `list_paired_devices` returned every non-revoked row -- including the self row. | `list_paired_devices` now derives the local device id from the Noise key bundle and filters the self-row out of every listing. The Devices screen also no longer renders the 'This device' identity card, so the page is entirely about peers. | 2026-09-29 | 2026-09-29 | Assistant | Validated in the rebuilt app: the Devices page now lists only the paired Windows laptop.
BUG-036 | FEAT-050 | Paired devices cannot be deleted; Delete and Revoke both offered | On the Devices page no paired device can be deleted (the action silently does nothing), and the screen offers two overlapping destructive actions (Revoke and Forget). | Medium | P1 | Fixed | Open Devices, pick a paired device, try its delete action. | The device disappears from the list and its pairing is gone; the UI has one clear destructive action. | Nothing happened on delete; both a Revoke and a Forget button were always present. | DeviceRepository::delete was a bare `DELETE FROM devices WHERE id = ?`, which violates the foreign keys from workspaces, snapshots, restore_runs and transfer_sessions that still point at the device row. Same silent class as BUG-030. | DeviceRepository::delete now removes, in one transaction, every row that references the device -- the workspaces it sent (with their own children), transfer sessions in either direction, restore runs and snapshots -- then the device row, while never touching workspaces this machine captured itself. The UI keeps exactly one destructive action (Forget); the Revoke button is removed and the confirmation states what is removed. | 2026-09-29 | 2026-09-29 | Assistant | Backend verified by the new db-crate cascade test (peer's workspaces and records removed, local captures untouched). UI verified in the rebuilt app: single delete button, no Revoke, list shows only the paired laptop.
BUG-037 | FEAT-014,FEAT-042,FEAT-079 | Restore of a dirty git clone rewrote the whole tree: 146 files for one change | A workspace whose project is a git checkout with uncommitted changes was restored by overwriting the whole tree at the destination, so `git status` there listed every tracked file as modified. The user's real delta was one file; the restore produced 146. Reported as the transfer/restore follow-up: 'make sure to take git changes using the patch'. | High | P1 | Fixed | Capture a workspace that includes a dirty git repo (one modified tracked file is enough), restore it into a same-commit clone, and run `git status --short` there. | `git status --short` at the destination shows exactly the source's uncommitted delta (one file), nothing more. | `git status --short` listed every tracked file as modified (146 files): the whole tree had been extracted over the checkout. | The file archive does not carry file modes, and restore's extract_project writes every file with default permissions, so executable files in a same-commit checkout reported mode changes en masse. The dirty state had explicitly never been captured (dirty_state_captured was always false), so there was no way to reproduce the delta on the other side. | Capture now records the worktree delta as a git-applyable patch: `git diff HEAD --binary` (staged + unstaged net) plus one `git diff --no-index /dev/null <file>` new-file hunk per untracked, non-ignored file, with the snapshot denylist applied and the source index never mutated (no `git add -N`). The patch travels in new optional `GitInfo.patch`. For patched projects the planner plans `git-apply-<id>` (adapter git, required false) and skips whole-tree extraction; the adapter applies via `git apply --binary --whitespace=nowarn` from a temp patch file, reporting `git checkout <source_commit>` as the remedy when the patch does not apply. A clean repo -- or one whose delta could not be captured -- keeps the old whole-tree copy. | 2026-09-30 | 2026-09-30 | Assistant | All suites green: 419 Rust tests (6 new adapter round-trip tests on real repos -- capture-to-apply gives exact `git status`, denylist respected, clean repo has no patch, mismatched base reports the remedy -- plus 2 new planner tests for the extract-skip and 1 new two-device e2e proving the patch survives the real socket transfer and restores to the exact change), 102 frontend tests, tsc --noEmit clean, 0 build warnings.

## Components
Component ID | Component Name | Type | Language | Description | Status | Version | Location | Dependencies | Owner | Health | Last Updated | Notes
COMP-001 | Tauri App Shell | Frontend Shell | TypeScript/React | Main window, IPC bridge, system tray | Done | 0.1.0 | src-tauri/, src/ | Tauri 2, React 18 |  | Healthy | 2026-09-27
COMP-002 | Core Rust Crate | Library | Rust | Shared types, manifest model, validation, scrubber | Done | 0.1.0 | src-tauri/core/ | serde, schemars, regex |  | Healthy | 2026-09-27
COMP-003 | Crypto Crate | Library | Rust | Key generation, Noise protocol, encryption/decryption | Done | 0.1.0 | src-tauri/crypto/ | snow, x25519-dalek, aes-gcm |  | Healthy | 2026-09-27 | Critical security
COMP-004 | Database Crate | Library | Rust | SQLite access, repositories, migrations, encryption | Done | 0.1.0 | src-tauri/db/ | sqlx, sqlcipher |  | Healthy | 2026-09-27
COMP-005 | Network Crate | Library | Rust | mDNS discovery, authenticated transport, transfer protocol | Done | 0.1.0 | src-tauri/network/ | mdns-sd, tokio, bytes |  | Healthy | 2026-09-27
COMP-006 | Adapters Crate | Library | Rust | Adapter trait + Git, VS Code, Browser, Terminal, Runtime implementations | Done | 0.1.0 | src-tauri/adapters/ | Core, DB |  | Healthy | 2026-09-27
COMP-007 | Preflight Crate | Library | Rust | Check orchestration, identity adapters, readiness aggregation | Done | 0.1.0 | src-tauri/preflight/ | Adapters, Core |  | Healthy | 2026-09-27
COMP-008 | Restore Crate | Library | Rust | Plan generation, safe action execution, Git safety, file transfer | Done | 0.1.0 | src-tauri/restore/ | Adapters, Core |  | Healthy | 2026-09-27
COMP-009 | UI - Components | Frontend | TypeScript/React | Reusable UI components (buttons, forms, tables, modals) | Done | 0.1.0 | src/components/ | Tailwind, Radix UI |  | Healthy | 2026-09-27
COMP-010 | UI - Screens | Frontend | TypeScript/React | Page-level screens per blueprint §14 | Done | 0.1.0 | src/screens/ | Components, Router |  | Healthy | 2026-09-27
COMP-011 | UI - State Management | Frontend | TypeScript | Zustand for app state, React Query for server state | Done | 0.1.0 | src/store/ | Zustand, TanStack Query |  | Healthy | 2026-09-27
COMP-012 | Tauri Commands | Bridge | Rust/TS | Command definitions for all Rust → Frontend operations | Done | 0.1.0 | src-tauri/commands/ | All crates |  | Healthy | 2026-09-27

## Runs
Run ID | Type | Component/Feature | Command | Status | Start Time | End Time | Duration (s) | Exit Code | Output Summary | Errors | Artifacts | Triggered By | Notes
RUN-001 | Test | Rust / whole workspace | cargo test --workspace -- --test-threads=2 | Passed | 2026-09-27 16:20 | 2026-09-27 16:20 | 300 | 0 | 325 tests passed, 0 failed. Up from 317: 8 new loopback transfer tests. 7 binaries, no failures. | None |  | Manual | Test-threads=2 avoids the parallel-binary contention that makes a default run look slow.
RUN-002 | Build | Rust / whole workspace | cargo build --workspace | Passed | 2026-09-27 16:20 | 2026-09-27 16:20 | 40 | 0 | Clean build, 0 warnings. | None |  | Manual | Warnings are treated as failures here; no #[allow] was added to silence anything.
RUN-003 | Test | Frontend / whole project | npx vitest run | Passed | 2026-09-27 16:20 | 2026-09-27 16:20 | 1.4 | 0 | 2 files, 19 tests passed. 10 pre-existing IPC contract tests plus 9 new route tests. | None |  | Manual
RUN-004 | Build | Frontend | npm run build | Passed | 2026-09-27 16:20 | 2026-09-27 16:20 | 4 | 0 | tsc then vite build. 1655 modules, 363 KB JS (127 KB gzipped across chunks). | None | dist/ | Manual | tsc runs as part of the build, so the type check is not a separate step that can be skipped.
RUN-005 | E2E | Desktop app / startup | ./target/aarch64-apple-darwin/debug/app | Passed | 2026-09-27 16:20 | 2026-09-27 16:20 | 45 | 0 | Migrations applied, Keychain keys loaded, device identity derived, mDNS discovery started, transfer listener bound on an ephemeral port. No errors or warnings from any workspace crate. | None |  | Manual | Binary is under target/aarch64-apple-darwin/debug/, not target/debug/, because .cargo/config.toml pins build.target. Worth knowing before concluding the build produced nothing.
RUN-006 | Test | Rust workspace (all crates) | cd src-tauri && cargo test --workspace -- --test-threads=2 | Success | 2026-09-27 17:05 | 2026-09-27 17:12 | 420 | 0 | 348 passed, 0 failed, 0 ignored. Includes commands/tests/two_device_transfer.rs at 11 tests. |  | src-tauri/target/aarch64-apple-darwin/debug/deps/ | Manual | Whole-workspace regression run after the receive path landed. --test-threads=2 is required: default parallelism causes binary contention on the test binaries that bind real sockets, which presents as a hang rather than a failure.
RUN-007 | Test | Frontend (vitest) | npx vitest run | Success | 2026-09-27 17:06 | 2026-09-27 17:12 | 6 | 0 | 37 passed across 3 files: ipc.test.ts (10), routes.test.tsx (9), receive.test.tsx (18). |  |  | Manual | receive.test.tsx is new: 18 tests covering the arrivals banner, refusals, dismissal, the Received badge and the transfer history. The polling test takes a real 4.0s because it waits for the actual interval rather than forcing an invalidation, which would have made it pass whether or not refetchInterval was set.
RUN-008 | Test | TypeScript | npx tsc --noEmit | Success | 2026-09-27 17:06 | 2026-09-27 17:07 | 40 | 0 | Clean. No errors, no output. |  |  | Manual | Caught ERR-005, two errors from a test reaching for a CSS class instead of a test id.
RUN-009 | Build | Frontend | npm run build | Success | 2026-09-27 17:12 | 2026-09-27 17:13 | 1 | 0 | Vite production build, 1655 modules. dist/index.html 1.09 kB, CSS 30.51 kB, JS bundles 301.98 kB raw / 107.18 kB gzipped. |  | dist/ | Manual | Runs tsc first, so this also type-checks.
RUN-010 | E2E | Running application | npx tauri dev, then a raw TCP connect to the port from the log | Success | 2026-09-27 17:23 | 2026-09-27 17:24 | 60 | 0 | App started with no panic. Log: 'This device is 6APnKHTwEwIWXA/Yg6xBdA== on ABHISHEKs-Air.lan', 'Transfer listener bound on port 53828', 'Listening for incoming transfers on port 53828'. Vite served HTTP 200. A raw socket connected to 127.0.0.1:53828 and the running app logged 'Accepted a connection from 127.0.0.1:53841'. |  | run2.log | Manual | The decisive run. Before this, no test had ever started the application, which is why BUG-009, BUG-010 and BUG-011 were all live. A connection to the advertised port being accepted and logged is the proof that BUG-005 is fixed in the running program and not merely in the test harness.
RUN-011 | Test | Command surface parity | python3 scripts/check_command_parity.py | Success | 2026-09-27 17:11 | 2026-09-27 17:12 | 1 | 0 | PARITY OK. 44 registered in Rust, 44 distinct names, 44 called from TypeScript, zero orphans in either direction, no duplicate registrations. |  |  | Manual | Compares the generate_handler! registry against the invoke() names in src/lib/ipc.ts. Catches the one class of bug TypeScript cannot: a wrapper naming a command Rust never registered compiles perfectly and fails at runtime. Also reports duplicate registrations, where the second silently shadows the first.
RUN-012 | Test | Test quality (mutation check) | Three deliberate regressions injected into WorkspacesScreen.tsx, reverted after each | Success | 2026-09-27 22:50 | 23:05 | 900 | 0 | Each mutation was caught by exactly the intended test and by no other. 1. Hiding the refusal reason: 1 failure, 'shows the reason the workspace was not stored'. 2. Removing refetchInterval: 1 failure, the polling test, after waiting the full 12s timeout. 3. Badging 'received' as something else: 1 failure, 'badges it Received, not Captured'. |  |  | Manual | A test that passes is not evidence the code works. Three tests were rewritten during this session because they asserted nothing real - one spied on QueryClient.prototype.mount and then forced the refetch it claimed to be testing, one asserted the absence of an alert that was never rendered, one rendered twice in a single test. Reintroducing BUG-011 in Rust was checked the same way: the regression test panics with the exact production message.
RUN-013 | Test | Rust / whole workspace | cargo test --workspace -- --test-threads=2 | Passed | 2026-09-28 14:20 | 2026-09-28 14:20 | 240 | 0 | 348 tests passed, 0 failed, 0 warnings. | None |  | Manual | Unchanged by this round - no Rust source was modified.
RUN-014 | Test | Frontend / whole suite | npx vitest run | Passed | 2026-09-28 14:20 | 2026-09-28 14:20 | 6 | 0 | 83 tests passed across 4 files (was 37 across 3). | None |  | Manual | New: 19 theme/shell tests in theme.test.tsx, 18 cross-route heading and status-bar tests in routes.test.tsx.
RUN-015 | Build | Frontend | npm run build | Passed | 2026-09-28 14:20 | 2026-09-28 14:20 | 2 | 0 | tsc clean; 1658 modules; CSS 32.6 kB (6.5 kB gzip). Every colour utility in the bundle resolves to a token family. | None |  | Manual | Verified the built CSS, not just that the build exited 0.
RUN-016 | Check | IPC contract | python3 scripts/check_command_parity.py | Passed | 2026-09-28 14:20 | 2026-09-28 14:20 | 1 | 0 | 44/44 parity: every command Rust registers is called from TS and every call resolves. | None |  | Manual
RUN-017 | Check | Design tokens | python3 scripts/apply_design_tokens.py --check | Passed | 2026-09-28 14:20 | 2026-09-28 14:20 | 1 | 0 | would change: 0 tokens across 0 files. No raw palette colours remain in src/. | None |  | Manual
RUN-018 | Manual | Window | npx tauri dev | Partial | 2026-09-28 14:20 | 2026-09-28 14:20 |  |  | Process launches, window is created and the webview serves the redesigned UI. The Rust startup path then blocks on a macOS keychain authorisation prompt. | Stalled at keychain get-password for service 'workspace-clone'. |  | Manual | BLOCKED, not a regression: no Rust source changed this round, and the same prompt blocked the previous round's launch. This environment has no assistive access, so the prompt cannot be dismissed. The UI was therefore verified in a browser against the same dev server instead. See LOG-052.
RUN-019 | Test | Rust / whole workspace | cargo test --workspace -- --test-threads=2 | Passed | 2026-09-28 16:10 | 2026-09-28 16:10 | 300 | 0 | 355 tests passed, 0 failed. Up from 348; +7 new platform-naming tests. | None |  | Manual | Two of my own compile errors were hit and fixed first: an Option<&str> unwrap_or_else returning String, and several stacked #[cfg] blocks in one function body not composing into a tail expression.
RUN-020 | Build | Rust / whole workspace | cargo build --workspace | Passed | 2026-09-28 16:10 | 2026-09-28 16:10 | 60 | 0 | Clean build, 0 warnings. Binary at target/debug/app. | None | src-tauri/target/debug/app | Manual | Confirms the target-pin removal is harmless on the Mac. `grep -c warning` exits 1 on zero warnings, which is the good outcome.
RUN-021 | Test | Build / Windows cross-compile | cargo xwin check --workspace --target x86_64-pc-windows-msvc | Failed | 2026-09-28 16:10 | 2026-09-28 16:10 | 240 | 1 | Blocked. cargo-xwin could not fetch the MSVC CRT: HTTP GET https://aka.ms/vs/17/release/channel failed, connection refused, after 4 retries. Independently confirmed with curl: aka.ms times out after 15s and github.com likewise. | Failed to setup MSVC CRT - no network route to the Windows SDK. |  | Manual | Environmental, not a code failure. A preceding plain `cargo check --target x86_64-pc-windows-msvc` got further and failed compiling the `ring` crate's C source - 'assert.h file not found' - which is the same missing-SDK problem seen from a different angle, and confirms the wall is the SDK rather than any project code.
RUN-022 | Test | Build / scripts | bash -n scripts/build_windows.sh && fixture test of both guards | Passed | 2026-09-28 16:10 | 2026-09-28 16:10 | 5 | 0 | Syntax OK. macOS guard exits 1 with the correct message. Pin guard: pinned fixture blocks, clean passes, comment-mentioning fixture passes. | None |  | Manual | The comment-stripping matters: .cargo/config.toml's own header *discusses* the target setting it deliberately omits, and a naive grep matches that prose. Verified the real file passes.
RUN-023 | Test | Build / Windows CI | .github/workflows/windows-installer.yml | Not Run | 2026-09-28 16:10 |  |  |  | Never executed. The authoring machine could not reach github.com. |  |  | Manual | Logged as a run precisely so the absence is a record rather than an omission.
RUN-024 | Test | Rust / whole workspace | cargo test --workspace -- --test-threads=2 | Passed | 2026-09-28 21:20 | 2026-09-28 21:22 | 90 | 0 | 394 passed, 0 failed, 0 build warnings. Per layer: adapters 62, ipc_selection_contract 6, commands 66, two_device_transfer 12, core 16, crypto 24, db 5, files 13, network 68, loopback 8, preflight 71, restore 43. Up from 377 by 17: the files crate (13) plus the files e2e in the two-device suite (1) plus restore's two extract tests and one further command test. |  |  | Manual | The new e2e a_workspace_with_files_arrives_with_its_archive_and_restores sends a workspace whose file was changed on the sending side, and asserts the changed content is present after receive + restore.
RUN-025 | Test | Frontend | npx vitest run | Passed | 2026-09-28 21:18 | 2026-09-28 21:19 | 7 | 0 | 6 test files, 99 passed, 0 failed. |  |  | Manual | No test asserted a manifest-only default, so the policy default change to 'all' stayed green.
RUN-026 | Test | TypeScript | npx tsc --noEmit | Passed | 2026-09-28 21:18 | 2026-09-28 21:18 | 30 | 0 | Clean, no output, no errors. |  |  | Manual | Runs over the edited RestoreActionType union and the new screen icons/imports.
RUN-027 | Test | Tooling gates | python3 scripts/check_command_parity.py && python3 scripts/apply_design_tokens.py --check | Passed | 2026-09-28 21:46 | 2026-09-28 21:46 | 5 | 0 | PARITY OK: every command Rust registers is called and every call resolves. No raw palette colours remain in src/. |  |  | Manual | The full green run also needs these two, plus the DMG build (RUN-028).
RUN-028 | Build | Build / Release | npx tauri build (frontend + Rust release + DMG) | Passed | 2026-09-28 21:22 | 2026-09-28 21:26 | 240 | 0 | Workspace Clone_0.1.0_aarch64.dmg, 8.2 MB, plus the .app bundle. Ad-hoc signed (signingIdentity '-'). beforeBuildCommand ran npm run build first. One deprecation warning from tauri-build about STATIC_VCRUNTIME (release-profile only, Windows CRT config, not from any crate in the workspace); see LOG-086. |  | src-tauri/target/release/bundle/dmg/Workspace Clone_0.1.0_aarch64.dmg | Manual | The debug gate the guide mandates (cargo build --workspace) remains warning-free; the release warning is toolchain-level and logged rather than patched blind.
RUN-029 | Test | Network Crate / BUG-028 | cargo test --workspace -- --test-threads=2 | Passed | 2026-09-28 23:00 | 2026-09-28 23:02 | 120 | 0 | 405 Rust tests passed. Network crate lib rose 68 -> 79 with the 11 new connect-candidate and dual-stack listener tests; loopback_transfer 8, two_device_transfer 12, commands 66, adapters 62 with parity contract 6. No failures anywhere. |  |  | Assistant | Companion gate: cargo build --workspace is warning-free (the only warning anywhere is a pre-existing unused-mut in wire.rs test code, invisible to the build gate). Frontend untouched, so 99 vitest + tsc stay as RUN-026/027 state.
RUN-030 | Test | Frontend / BUG-029 | npx vitest run && npx tsc --noEmit | Passed | 2026-09-29 10:02 | 2026-09-29 10:03 | 20 | 0 | 100 frontend tests passed across 6 files, including the new arrival-refreshes-the-list test. tsc --noEmit is clean. receive.test.tsx grew 19 -> 20. |  |  | Assistant | Companion screen for BUG-029: the two 'polling' tests together pin both halves of an arrival - the banner appears (already covered) and now the list refetches without a remount. No Rust changes in this session.
RUN-031 | Test | Frontend + Rust suites / BUG-030..036 | npx vitest run && npx tsc --noEmit && cargo test -p workspace_clone_commands -p workspace_clone_db | Passed | 2026-09-29 23:20 | 2026-09-29 23:26 | 320 | 0 | 102 frontend tests passed (was 100: +2 regression tests -- exact camelCase wire-shape payload and 'Open preflight' navigation). tsc --noEmit clean. Rust: 79 tests passed in workspace_clone_commands (67 unit incl. new IncomingTransfer wire-shape test, 12 two-device end-to-end across a real socket) plus 7 in workspace_clone_db (2 new cascade-delete tests). |  |  | Assistant | Companion runs for the seven bugs. Counts: Rust total 408 (was 405), frontend 102 (was 100).
RUN-032 | Build + App | Rebuilt app / BUG-030..036 validation | npx tauri build --config src-tauri/app/tauri.conf.json; installed DMG; manual checks on the live Mac DB | Passed | 2026-09-29 23:40 | 2026-09-29 23:55 | 900 | 0 | New DMG built and installed over the previous build. In the running app: Devices page lists only the paired Windows laptop (self gone), single Forget action with no Revoke button; deleting a received workspace removed its DB row (sqlite3) and manifest file (ls); the history tab renders real source/destination device names from stored transfer_sessions data. |  |  | Assistant | Full validation on real hardware and data. One live end-to-end banner check remains impossible from this machine (needs a new Windows-side send); covered by the Rust e2e + wire-shape tests.
RUN-033 | Test | Rust + Frontend suites / BUG-037 git patch transport | cargo test && npx tsc --noEmit && npx vitest run | Passed | 2026-09-30 10:10 | 2026-09-30 10:30 | 480 | 0 | 419 Rust tests passed (was 408): 6 new adapter tests capture a dirty worktree as a patch, apply it to an identical clone and assert `git status ` shows exactly the source delta; a mismatched-base clone reports 'git checkout <commit>' as a Manual remedy; the denylist keeps .env and node_modules out of the patch; a clean worktree captures no patch; plan_restore emits git-apply only when a delta exists. 2 new planner tests (patched project restores via git-apply with no extract-files step; clean project keeps the tree copy). 1 new two-device e2e: a dirty repo's delta survives the real socket + sealing round trip and restores to exactly [' M note.txt', '?? new.txt']. tsc --noEmit clean, 102 frontend tests passed, 0 build warnings. |  |  | Assistant | One follow-up remains out of reach from this machine: a true live transfer with the Windows laptop (requires the user to send). Covered by the Rust e2e + adapter round-trip tests.

## Errors
Error ID | Date/Time | Component | Feature/Task | Error Type | Error Message | Stack Trace | Context | Severity | Status | Root Cause | Solution | Fix Applied | Verified | Prevention | Related Bug ID | Notes
ERR-001 | 2026-09-27 16:20 | Frontend / App.tsx | FEAT-054,FEAT-055,FEAT-056 | Runtime | get_manifest invoked with workspaceId = undefined; all three workspace-scoped screens rendered 'The workspace could not be read'. |  | Reached by clicking Preflight, Prepare or Review restore plan from a workspace. | Critical | Resolved | Route patterns declared :transferId while the screens read useParams<{ workspaceId }>(). The generic on useParams is an unchecked assertion, so the mismatch compiled. | Renamed the patterns to :workspaceId. Added src/test/routes.test.tsx, which mounts the real <App /> behind a MemoryRouter at each route and asserts the id in the URL reached get_manifest - the only level at which a route pattern is observable. Reverted one pattern to confirm the test fails. | Yes | A screen test cannot catch this: mounting a screen directly bypasses the router entirely. Test the route, not the screen, when the screen's input is a URL. | BUG-001
ERR-002 | 2026-09-27 16:20 | Rust / network/src/transfer.rs | FEAT-053 | Performance / Correctness | A cancelled send took 15.005s to return, the full HANDSHAKE_TIMEOUT. |  | Loopback transfer test: send 4 MiB to a listening-but-silent receiver, call cancel() after 2ms. | Major | Resolved | The cancel flag was read only at a frame boundary, and a send blocked in a read never reaches one. The three blocking points - connect, handshake reply, per-frame ack - were not cancellable at all. | Added a watch channel carrying the flag and raced each blocking operation against it. Test duration for the cancel case went from 15.05s to under 0.08s, and the whole loopback file from 15.16s to 0.08s. | Yes | A cancellation path needs a latency assertion, not just a status assertion. The status was already correct; only the timing was wrong, and nothing tested the timing. | BUG-002
ERR-003 | 2026-09-27 17:40 | Tauri App Shell | FEAT-001 | Panic | there is no reactor running, must be called from the context of a Tokio 1.x runtime | panicked at commands/src/receive.rs:314:5: there is no reactor running, must be called from the context of a Tokio 1.x runtime note: run with RUST_BACKTRACE=1 to display a backtrace | Start the application with tauri dev. The panic is in the accept loop's spawn, reached from init during Tauri's setup hook. The listener had already bound and the device had already announced itself. | Critical | Resolved | tokio::spawn called from a thread with no Tokio runtime entered. Tauri's setup hook runs on the main thread outside any runtime. | Use tauri::async_runtime::spawn, which enters Tauri's global runtime. Added a plain #[test] that reproduces the condition, because every other test in the suite enters a runtime and would never have caught it. | Yes | Yes - commands/tests/two_device_transfer.rs::the_accept_loop_can_be_started_without_a_tokio_runtime_entered, verified to fail with the same panic when the fix is reverted | When starting background work from init, use tauri::async_runtime::spawn. tokio::spawn is only correct from inside a task that is already running. The startup path is the one place this is easy to get wrong and impossible to unit test by accident. | BUG-011 | Found only by starting the application. No test could have found it: all of them are #[tokio::test].
ERR-004 | 2026-09-27 17:40 | Tauri App Shell | FEAT-001 | CLI Error | Error: No package info in the config file | Error No package info in the config file | npx tauri dev from the project root. Raised by tauri-cli 2.11.5 at interface/rust.rs: RustAppSettings::new loads CargoSettings for the config's directory and returns this when there is no [package] section. | Critical | Resolved | tauri.conf.json was in src-tauri/, whose Cargo.toml is a virtual workspace manifest with no [package]. The app crate is src-tauri/app/. A config_path override in build.rs let cargo build succeed while the CLI could not find the app. | Move tauri.conf.json beside the crate that has [package], drop the config_path override and the generate_context! path argument, and re-express the config's relative paths from the new location. | Yes | Yes - npx tauri dev starts the app | Keep tauri.conf.json and capabilities/ inside src-tauri/app/, beside the crate that has [package] and the build script. All three Tauri tools resolve paths from there; the virtual workspace root is not one of them. | BUG-009 | The same layout divergence caused BUG-010. Both were invisible to cargo build, which succeeded throughout.
ERR-005 | 2026-09-27 17:40 | UI - Screens | FEAT-030 | Type Error | TS2345: Argument of type 'Element' is not assignable to parameter of type 'HTMLElement' | src/test/receive.test.tsx(297,19): error TS2345 src/test/receive.test.tsx(298,19): error TS2345 | A new test scoped a query with within() on the result of .closest(), which is typed Element ¦ null rather than HTMLElement. Reached by two assertions, so it surfaced twice. | Low | Resolved | Reaching for a CSS class selector on a component's rendered output. The element was found by its visible text, whose closest() returns a general Element. | Put a data-testid on the workspace Card, which forwards its props to the div, and select the row by test id rather than by traversing the DOM for a class name. | Yes | Yes - npx tsc --noEmit is clean | Select by data-testid, not by a CSS class. The Card components spread HTMLAttributes onto their div, so a test id is always available, and a test that depends on a styling class breaks when the styling changes.
ERR-006 | 2026-09-27 17:40 | Commands Crate | FEAT-028 | Test Failure | the listener the loop owns should still be bound: ConnectionRefused (os error 61) | thread 'the_accept_loop_can_be_started_without_a_tokio_runtime_entered' panicked at commands/tests/two_device_transfer.rs:839:14: the listener the loop owns should still be bound: Os { code: 61, kind: ConnectionRefused } | Writing the regression test for BUG-011. The test built the listener inside a locally created Tokio runtime and then dropped that runtime to make the spawn call happen with no reactor in scope. The spawn panic was fixed, and the test then failed on its second assertion. | Low | Resolved | A tokio::net::TcpListener belongs to the runtime that created it. Dropping the runtime closed the socket, so the listener the loop was supposed to serve was already gone. | Bind the listener on Tauri's global runtime instead, which outlives the call. That is also a truer reproduction of the real startup path, where the listener and the loop share Tauri's runtime. | Yes | Yes - the test passes, and fails with the production panic when the BUG-011 fix is reverted | A TcpListener is owned by its runtime. In tests, create and serve it on the same runtime, or the test measures the runtime being dropped rather than the code under test. | BUG-011 | A wrong first attempt at the regression test, recorded because the failure was informative rather than confusing.
ERR-007 | 2026-09-28 23:10 | Network Crate | FEAT-028 | Runtime Network Error | Could not reach fe80::f727:abc9:2280:4f3:54108: No route to host (os error 65) | No panic or backtrace; the failure surfaced through the transfer session error field, shown as 'Network error: Connection failed: ...' on the Mac UI, twice in a row. | First real two-machine send from the Mac to the paired Windows laptop. mDNS advertised the laptop's link-local IPv6 address first and the sender connected only to the first advertised address as a bare string. | Critical | Resolved | A bare IPv6 link-local (fe80::/10) needs a zone id (scope) before the kernel will route to it; macOS returns ENETUNREACH (os error 65). The receiver also listened IPv4-only (0.0.0.0), so even a scoped IPv6 connect could not have been served. | Connect-candidate expansion (IPv4 first; link-local IPv6 scoped to local link-local interfaces; %zone trusted) raced under one budget, plus a dual-stack [::] listener with an IPv4-only fallback. | Yes | Yes - 405 Rust tests pass, including 11 new ones covering ordering, scoping, refused-address naming and the dual-stack listener; the listener binds [::] on this Mac and still serves 127.0.0.1. The two-machine retest is pending the new build on both laptops. | A connect to a peer must always come from the candidate list, never from addresses.first(); link-local IPv6 is scoped before any connect. | BUG-028 | os error 65 = ENETUNREACH. The same bare-fe80 problem could bite any future direct-IP connect path, which is why the candidate helper is shared by send and manual pairing.

## Decisions
Decision ID | Date | Title | Context | Options Considered | Decision | Rationale | Impact | Revisit Trigger | Owner | Status | Related Items
DEC-001 | 2026-09-26 | Desktop Framework: Tauri 2 vs Electron vs Flutter | Need cross-platform desktop app with native performance and Rust backend | Tauri 2, Electron, Flutter, Native (Swift/WinUI) | Tauri 2 | Smaller bundle, Rust backend, web frontend, active community, matches blueprint recommendation | All native code in Rust; web tech for UI | If Tauri 2 has blocking issues | Team | Decided | Blueprint §5
DEC-002 | 2026-09-26 | Crypto Protocol: Noise vs TLS 1.3 | Authenticated encryption for device-to-device transfer | Noise IK, TLS 1.3 mTLS, Custom | Noise Protocol (snow crate) | Designed for peer-to-peer, minimal handshake, forward secrecy, well-reviewed implementations | Rust crypto crate design | If interop with non-Rust needed | Team | Decided | Blueprint §5, §17
DEC-003 | 2026-09-26 | Database: SQLite vs SQLCipher vs Redwood | Local persistence with encryption for sensitive fields | SQLite + app-level encryption, SQLCipher, Redwood | SQLite with SQLCipher | Transparent encryption, mature, zero-config, OS key storage for master key | DB crate design | If performance issues | Team | Decided | Blueprint §5, §15
DEC-004 | 2026-09-26 | Discovery: mDNS/DNS-SD vs Custom | LAN device discovery for pairing and transfer | mDNS/DNS-SD, Custom UDP broadcast, Central relay | mDNS/DNS-SD (mdns-sd crate) | Standard, works cross-platform, rotating IDs for privacy | Network crate design | If enterprise networks block mDNS | Team | Decided | Blueprint §6.3, §15
DEC-005 | 2026-09-26 | State Management: Zustand vs Redux vs Context | Frontend global state for devices, workspaces, UI | Zustand, Redux Toolkit, React Context + useReducer | Zustand | Simple, TypeScript-first, minimal boilerplate, good devtools | UI architecture | If complex server state needs | Team | Decided
DEC-006 | 2026-09-26 | Styling: Tailwind CSS vs CSS Modules vs Styled Components | Consistent, maintainable styling system | Tailwind CSS, CSS Modules, Styled Components | Tailwind CSS | Utility-first, fast iteration, small bundle, great TypeScript support | UI components | If design system needed | Team | Decided
DEC-007 | 2026-09-26 | Manifest Format: JSON vs YAML vs CBOR | Wire format for workspace manifests | JSON, YAML, CBOR | JSON (with CBOR for large file transfers) | Human-readable, universal parser support, schema validation via JSON Schema | Core model, Network | If binary size critical | Team | Decided | Blueprint §7, §15
DEC-008 | 2026-09-26 | Identity Checks: CLI-only vs Browser flows | How to verify identity readiness (GitHub, AWS, etc.) | CLI status commands only, Browser OAuth flows, Hybrid | Hybrid (CLI primary, browser fallback) | CLI checks are reliable and scriptable; browser for providers without CLI | Preflight adapters | If CLI unreliable | Team | Decided | Blueprint §9.2-9.3
DEC-010 | 2026-09-27 | Cancellation is a watch channel rather than a polled flag | A send spends nearly all of its time blocked in a read. A cancel flag read only at a frame boundary therefore cannot interrupt it, and cancelling a transfer waiting on a silent peer took the full 15-second handshake timeout. | Poll the flag more often; tokio::sync::Notify; tokio::sync::watch; give up cancelling mid-transfer | tokio::sync::watch carrying the cancel flag, raced against every blocking operation | The flag stays the source of truth; the channel is only what makes noticing it prompt. A watch rather than a Notify specifically because the flag is resettable and the service is reused: a Notify stores a permit when nobody is listening and offers no way to take it back, so after a cancel and a reset the *next* transfer consumed the stale permit and cancelled itself. That was found by an existing test hanging, not by reasoning, which is the argument for having run it. | Cancellation latency drops from 15.005s to under 0.08s. Adds a field to TransferService. A reset now propagates to waiters, which is harmless because a reset is never issued while a transfer is in flight. | If a transfer ever needs to be paused and resumed rather than stopped, the latch semantics would have to change. | Assistant | Decided | BUG-002, ERR-002
DEC-011 | 2026-09-27 | The pairing flow is key-based with a typed-back safety number, not code-based | DevicesScreen presented a two-step flow built around a pairing code: generate a code, paste it on the other machine, verify. No implemented command accepts a code. verify_pairing takes a peer's Noise public key, a name, the safety number the user read out loud, and the trust scopes; get_safety_number computes that number from the local and remote keys. | Keep the code flow and add a code command; make the UI key-based on the commands that exist | Key-based: pick a discovered device or paste a key, compute the safety number, require the user to type back what the other screen shows, then verify | The code flow was a fiction with no backend behind it. create_pairing_invitation is real and is still offered, but as a way to hand over this device's keys - an invitation, not a pairing. PairingInvitation carries no safety number, because it is derived from both Noise keys and the inviter does not know the other side's yet; a type suggesting otherwise would assert a binding that was never established. | The Devices screen now matches the backend. A pair requires both machines and an out-loud comparison, so there is no purely local pairing path in the UI. | If a deep link for workspace-clone://pair is ever handled, the paste box should accept the whole link and parse out the key. | Assistant | Decided | FEAT-050
DEC-012 | 2026-09-27 | Send the manifest as re-serialised JSON inside the encrypted channel, not as the sealed file | A manifest is sealed at rest with the device's own storage key so that copying the file off the disk yields nothing readable. The transfer path was sending that sealed file, which is encrypted with a key no other machine has. The choice had to be made before the receive path existed, and it determined what a receiving machine could possibly do with what it was sent. | (a) Send the sealed file, as the code did. (b) Send the plaintext manifest inside the already-encrypted Noise channel, and have the receiver seal it with its own key. (c) Encrypt the manifest to the destination's public key, adding a second key exchange to the protocol. | (b). Send re-serialised manifest JSON; the receiver seals it with its own storage key on arrival. | Sealing is protection AT REST and the key is per-device, so (a) sends bytes no peer can open - a workspace that appears in the list and then fails, with the real cause several steps from the symptom. Confidentiality in transit does not need the seal: the Noise channel is authenticated and encrypted for its whole duration, so (b) loses nothing. (c) was rejected as a second, weaker key exchange layered under one that is already proven. | A stored received workspace is indistinguishable from a locally captured one, and opens with the local key. One consequence: workspaces.manifest_digest is a digest of the LOCALLY SEALED bytes, not of what arrived, so the arrival reports the arrived digest separately. A check comparing the two would fail every time. The two-device suite asserts the stored manifest opens with the receiver's key and NOT the sender's. | Would be revisited if a future transport is not confidential end to end, or if manifests are ever large enough that re-serialising them is a problem. | Assistant | Accepted | BUG-006, FEAT-028, commands/src/transfer.rs, commands/src/receive.rs
DEC-013 | 2026-09-27 | Authorize in both directions, and check the key the handshake authenticated rather than an announced id | The device rows carried trust_scopes, and nothing read them. The send side offered any device; the receive side, once written, would have accepted anything that completed a handshake. Identity also had two possible sources - the Noise static key the handshake proved, and a device id in a frame header - and only one of them is authenticated. | (a) Keep the single-scope, send-time-only check. (b) Enforce pairing, revocation and scope on both sides, deriving identity from the authenticated Noise key. (c) Enforce on both sides but trust the frame header's device id. | (b). Both gates check paired, then not revoked, then the scope. Identity comes from the authenticated Noise key. | A scope checked on one side only is a suggestion. And a device id in a frame header is an unauthenticated string that anything on the network could set, so trusting it would let an unpaired machine claim to be a paired one. (c) is the failure mode the whole pairing ceremony exists to prevent. | Sending requires the destination to be paired, not revoked, and to hold `receive`. Receiving requires the sender to be paired ON THIS DEVICE, not revoked, and to hold `send`. Matches the DevicesScreen labels, which are both written from the perspective of the machine you are standing at. Covered by four tests, one per gate plus one proving a refusal does not stop the next transfer. | Would be revisited if scopes ever need to differ per workspace rather than per device pair. | Assistant | Accepted | BUG-007, FEAT-028, commands/src/transfer.rs, commands/src/receive.rs
DEC-014 | 2026-09-27 | Handle each accepted connection on its own task rather than inline in the accept loop | Writing the loop as a plain accept-handle-accept loop serialised the listener behind per-connection work. Handshake handling is bounded by a 15-second timeout, so one peer that connected and said nothing delayed every other peer by that long. The test that measured it recorded 15.03 seconds behind a silent socket. | (a) Handle inline. Simple, and one task. (b) Handle each connection on its own task. (c) Set the handshake timeout low, and handle inline. | (b). TransferReceiver became Clone with accept_connection(); the loop accepts, spawns handling, and returns to accepting immediately. | A silent peer is a normal event on a network, and must cost only its own connection. (c) would trade a real stall for a real class of failure: a legitimate slow handshake would be cut off. Holding the service mutex across a whole transfer was rejected too, for the same reason at a larger scale - it would block sends for the duration. | A peer that connects and says nothing now affects only itself. accept_once and accept_once_with_progress delegate to the same accept_connection, so the single-connection entry points are unchanged. | Would be revisited if a connection-count limit is ever needed, which would make a semaphore the right shape. | Assistant | Accepted | BUG-008, FEAT-028, network/src/transfer.rs
DEC-015 | 2026-09-27 | Pass the storage key and the local device id into the receive path as parameters | accept_or_refuse needs the local storage key to seal an arrival, and the local device id to verify that a manifest's capture device is one this device knows. Both were to be read from the OS credential store. A test binary reading a keychain item that belongs to the application blocks on a user prompt that nobody is present to answer, so every test would hang rather than fail. | (a) Read the key inside the receive path. (b) Pass it in as a parameter, with the KeyStorage-backed caller supplying a closure. (c) Introduce a key-provider trait. | (b). serve_forever takes a StorageKeySource = Arc<dyn Fn() -> Result<EncryptionKey> + Send + Sync>. The application passes a closure that reads the keychain on demand; the tests pass a fixed key. | A closure keeps the key out of memory for the application's lifetime - it is fetched when an arrival is actually sealed and not held resident - and it makes the loop testable without touching the credential store. (c) is a larger interface than one call site justifies. | Unit tests can exercise the whole receive path. capture::read_manifest gained read_manifest_with_key for the same reason. What the tests assert is the property that actually matters - the stored manifest opens with the key that sealed it and not with the sender's - which a real keychain would change nothing about. | Would be revisited if key access ever needs to be scheduled, cached or reported on separately. | Assistant | Accepted | commands/src/receive.rs, commands/src/capture.rs, commands/tests/two_device_transfer.rs
DEC-016 | 2026-09-27 | Record a received workspace with status 'received', not 'captured' | workspaces.status is free text and the capture path wrote 'captured'. A workspace that arrived on this machine was not captured here, and the badge is the only place on the row that says where a workspace came from. | (a) Reuse 'captured', since the manifest is the same shape. (b) Write 'received'. (c) Add a source column and leave status alone. | (b). status = 'received', with the capture device's id in the existing source_device_id. | A status is a claim about what happened on this machine. Writing 'captured' for a workspace that arrived would make the provenance invisible in the one place a user looks for it, and source_device_id is a foreign key to a device that may not be paired here. (c) duplicates information the column already carries. | The Workspaces list badges it Received, in a different colour from Transferred, and a test asserts the badge is not 'Captured'. |  | Assistant | Accepted | BUG-005, FEAT-030, src/screens/WorkspacesScreen.tsx
DEC-017 | 2026-09-27 | Keep tauri.conf.json and capabilities/ inside src-tauri/app/, beside the crate that has [package] | The Tauri CLI requires the config's directory to have a sibling Cargo.toml with a [package] section, because that is how it decides which crate is the application. tauri-build globs ./capabilities/**/* against the build script's directory. Both resolve from src-tauri/app/. Neither resolves from src-tauri/, whose Cargo.toml is a virtual workspace manifest. | (a) Leave both in src-tauri/ and pass an explicit config_path from build.rs, which is what the project did. (b) Move both into the app crate directory and let every tool use the default. (c) Collapse the Rust workspace back into a single crate at src-tauri/ to match the default layout. | (b). Config and capabilities live in src-tauri/app/. Relative paths re-expressed: frontendDist ../../dist, icons ../icons/...; build.rs drops its config_path; generate_context! drops its path argument. | (a) is what produced two live bugs: the CLI could not find the app at all, and the capabilities glob matched nothing so the app shipped declaring no frontend permissions. Both were silent - cargo build succeeded throughout - because an explicit config_path lets the build script and the CLI disagree about the project layout. (c) would undo the crate separation the whole design depends on. | npx tauri dev works from the project root. The generated app/gen/schemas/capabilities.json is no longer empty. The DEVELOPER_GUIDE records that an empty {} there is a bug, not a neutral state. | Would be revisited if a second Tauri application were ever added to the workspace, which would need per-app config paths anyway. | Assistant | Accepted | BUG-009, BUG-010, FEAT-001, src-tauri/app/build.rs, src-tauri/app/src/lib.rs
DEC-018 | 2026-09-27 | The window polls for arrivals rather than subscribing to an event | The accept loop is a backend task started at init, not something the UI starts, so receiving works with the window closed. The window therefore has no natural event to subscribe to without adding a backend-to-frontend event channel. | (a) Poll get_incoming_transfers on an interval. (b) Emit a Tauri event from the accept loop and subscribe in the window. (c) Fetch once on mount and refresh after every action. | (a). A 4-second interval, exported as ARRIVALS_POLL_MS so the test asserts against the real value. | (b) is the better design and is the right thing to build if this grows; it was not chosen now because it needs a new event channel and a subscription lifecycle for a screen that is not the only consumer of an arrival. (c) is visibly wrong: a transfer that completes while the window is open would never appear, and a workspace that arrived thirty seconds ago and is not yet listed is indistinguishable from a transfer that failed. Four seconds bounds that confusion, and the poll is not load-bearing - the transfer is stored whether or not the window ever asks. | ARRIVALS_POLL_MS = 4000 in src/screens/WorkspacesScreen.tsx. The polling test waits the real interval and fails if refetchInterval is removed; it was rewritten after a first version that forced the refetch it claimed to be testing. | Would be revisited if arrivals became frequent enough to matter, or if a second surface needed them. | Assistant | Accepted | FEAT-030, src/screens/WorkspacesScreen.tsx
DEC-019 | 2026-09-28 | Reject the Stitch-generated palette; keep its structure | Stitch generated a Material 3 tonal scheme for the desktop brief: blue-tinted surfaces (#dce9ff, #cbdbf5), a green secondary and a brown tertiary. | Adopt as generated; adopt structure with generated colours; keep structure and hand-correct the colours; ignore Stitch. | Keep the structure, hand-correct the colours. | Rejected on functional rather than aesthetic grounds. Green, amber and red are already spoken for - they mean ready, needs-you and failed in the preflight and restore step lists - so spending them on decoration would make the status colours ambiguous. And blue-tinted surfaces read as a web app, where a macOS window recedes with cool neutral greys. The structural output (spacing scale, type scale, radii, elevation ladder, token vocabulary) was sound and was kept. | Accent is indigo and reserved; green/amber/red mean status only. Both modes designed independently with the same tier counts. | If a future surface needs a hue beyond the accent and four status families. | Assistant | Decided | FEAT-067,FEAT-068,BUG-014
DEC-020 | 2026-09-28 | System font stack, not Geist | The Stitch design specified Geist for the interface and a mono face. | Ship Geist via a webfont link; use the platform stack; bundle the font files. | Use the system stack (-apple-system first, SF Mono for mono). | Shipping Geist means a webfont fetch at every launch, in an app whose entire pitch is that nothing leaves the local network. On macOS the system stack is SF Pro, which is the platform-native choice anyway; a webfont would be a network request to look slightly less native. | No third-party request on launch. The Google Fonts <link> was removed from index.html. | Only if a specific glyph or metric in Geist is needed and cannot be substituted. | Assistant | Decided | FEAT-067
DEC-021 | 2026-09-28 | The toolbar owns the page title on every route | Each screen had its own heading and the toolbar also showed a title, so every route displayed the same words twice. | Toolbar title as a non-heading, screen keeps its h1; hide the toolbar title on sections; toolbar owns the title everywhere; drop the screen headings entirely. | The toolbar is the app's only <h1>, on every route. | A desktop window puts the document title in the toolbar, pinned and present at every scroll position - which is also where the back button lives on a step. A heading in the scrollable content is a web layout. The intermediate option (h1 in the toolbar for sections, a breadcrumb for steps) was implemented and then rejected: the new cross-route test showed the breadcrumb's last crumb was still character-identical to the step's own h1 on /capture and /restore-report. | One h1 per page, no repeated title, no horizontal room wasted on a duplicate. | If a future screen needs a heading distinct from its route name, that screen should own the h1 and the toolbar should become a breadcrumb again. | Assistant | Decided | BUG-015,FEAT-067
DEC-022 | 2026-09-28 | 13px body text as the density baseline | The window is 780px tall, so a list has to fit rather than scroll. The browser default is 16px. | Keep 16px; 14px; 13px; per-screen overrides. | 13px on <body>, with every larger size an explicit step. | Measured in the running app: 16px at 1.5 line-height gives roughly 34 lines in the 636px content area, 13px gives about 45. That is the difference between a paired-device list fitting and needing a scrollbar. Set on body rather than a wrapper so future markup without a size class lands on the dense default rather than the browser's. Forms inherit explicitly, since they do not by default. | Denser lists and fewer scrolls. Heading scale is now 11/13/15, with 20-24px reserved for figures read character by character. | If legibility testing on a real 5K display shows 13px is too small at 1x. | Assistant | Decided | FEAT-067
DEC-023 | 2026-09-28 | Three-state theme control, persisted in localStorage | The app previously had no theme control at all, and a dark stylesheet that nothing could activate. | Boolean light/dark switch; three-state selector; follow the system only, with no override. | Three states - Light / Dark / Auto - persisted to localStorage `wc.theme`. | A boolean switch is two-state, so 'follow the system' - the right default for a desktop app, and the only option that survives being handed to someone else - becomes unreachable the moment the user touches it, with no way back. The store's initialiser calls an exported readStoredMode(), so the write and the read are one contract and a test can assert the round trip. index.html inlines a deliberate one-line duplicate of the logic because it is the only way to run before first paint. | Auto is always reachable. The choice survives relaunch with no flash of the wrong appearance. `colorScheme` is set alongside the class so macOS scrollbars match. | Never for the state model; only the storage key would change if preferences move out of localStorage. | Assistant | Decided | FEAT-068,BUG-013
DEC-024 | 2026-09-28 | No build target pin in .cargo/config.toml | The file pinned `build.target = "aarch64-apple-darwin"` to get reproducible output on an Apple Silicon Mac. Cargo applies `[build] target` repo-wide and on every host, so this was simultaneously redundant on the dev machine and fatal on any other. The pinned path also made the tree look macOS-only. | Keep the pin; scope it with a host-conditional; move it into scripts; remove it and pass the triple explicitly. | Remove the pin; pass `--target` on the command line when a specific triple is wanted. | Cargo has no conditional form for `[build] target`, so scoping was not available. The host default is already correct on every platform, which makes the pin redundant everywhere it was not fatal. Reproducibility is a weak benefit next to 'the build works on the second machine', and the tripleless path is what every other Tauri project uses. | Binary moved to src-tauri/target/debug/app; guides and scripts updated. A guard in build_windows.sh catches a reintroduced pin, and section 15 records why the absence is deliberate so it is not 'tidied up' later. | If the project ever needs two host platforms built in one command, revisit - but use scripts, not the config file. | Assistant | Decided | BUG-017,FEAT-070
DEC-025 | 2026-09-28 | Windows installers are built on a Windows machine, not cross-compiled | The request was a shareable .exe for a Windows laptop. Tauri's Windows build requires the MSVC toolchain, the Windows SDK and NSIS. cargo-xwin can fetch enough of the SDK to compile the Rust, but `tauri build` still bundles with Windows tooling, and cross-compiling a Tauri app to Windows from macOS is not supported. In this environment it is additionally impossible: aka.ms and github.com both time out. | cargo-xwin on the Mac; build on the laptop; GitHub Actions on windows-latest; attempt a raw .exe and skip the installer bundle. | Two Windows paths, both requiring a Windows machine: scripts/build_windows.sh, or the GitHub Actions workflow. | This is what the Tauri project itself documents. The cross-compile was attempted and failed for environmental reasons, and even a success would have produced a bare binary with no installer, no shortcut, and no WebView2 bootstrap - a worse deliverable that looks like a working one. Two real paths beat one that mostly works. | No .exe exists yet. The deliverable this round is the unblocking work: one blocker removed, four platform bugs fixed, and both paths written and guarded. FEAT-071 is left In Progress because its workflow has never run. | If Tauri gains supported macOS-to-Windows cross-builds, the CI workflow becomes redundant. | Assistant | Decided | FEAT-070,FEAT-071,RUN-021,RUN-023
DEC-026 | 2026-09-28 | Platform logic is extracted into pure functions before being fixed | Three of the five Windows bugs were in functions that read the process environment or spawn platform tools, so they could not be tested without touching global state or a second operating system. | Fix in place with no tests; test by setting env vars in the test process; extract the selection logic into a pure function and test that. | Extract: resolve_hostname() takes the three candidate strings and returns the choice. | A test that sets HOSTNAME to prove the Windows path would race every other test in the binary - process environment is global and the suite runs with two threads specifically because several test binaries contend for sockets. The extraction is what makes the 7 new tests meaningful rather than flaky. It also made the stacked-#[cfg] function body impossible to write correctly, which is how the per-platform split in os_version() came about. | 7 tests that run on any platform and would have caught BUG-018 on a Mac. The platform probes themselves remain unexercised - this tests the choice, not the tool call. | Never; this is the pattern to keep using. | Assistant | Decided | BUG-018,BUG-020
DEC-027 | 2026-09-28 | Ad-hoc re-sign the installed .app rather than require a Developer ID | The bundled app had an invalid resource seal and no signing identity is available on this machine (0 valid identities). A Developer ID certificate would cost an Apple membership and is the wrong ask for a local test. | Leave unsigned and hope; require a Developer ID; ad-hoc seal the bundle; distribute via testflight-style signing. | Ad-hoc seal the installed bundle with codesign --force --sign -. | Ad-hoc signing makes the seal internally consistent, which is what Gatekeeper checks before it will load a bundle. The remaining `spctl: rejected` is the distribution verdict for an unnotarized app and does not affect local launch, because there is no quarantine attribute on something built on this machine. Escalating to a Developer ID for a first live test would be a decision about distribution that is not ready to be made. | The app runs. Originally this decision was recorded as leaving BUG-023 open at source, because the fix was a manual per-build `codesign` step. That is superseded: `bundle.macOS.signingIdentity` is now set to "-" in tauri.conf.json, so Tauri ad-hoc signs every build and the manual step is gone. The un-solved part of the original problem is unchanged and is the part that actually matters for distribution - an ad-hoc signed, unnotarized app that is copied to another Mac is quarantined by Gatekeeper and needs right-click -> Open, because there is no trusted signature to attest to. Only a Developer ID plus notarisation fixes that, and it remains the right next step when this is distributed beyond the developer's own machines. | When the app is distributed beyond the developer's own machines, this becomes a real signing decision and needs revisiting. | Assistant | Decided | BUG-023,FEAT-073
DEC-028 | 2026-09-28 | Safety numbers are compared visually, not transcribed; the comparison stays out of band | The user paired for the first time across two machines and asked to drop the input, proposing that validation happen over the network once both sides show the same code. The existing code required the number to be retyped and justified that as the security control. | Keep the transcription; drop it and auto-validate over the network; drop the transcription and keep an out-of-band human comparison. | Drop the transcription, keep the comparison human and out of band, and keep refusing a supplied number that disagrees with the recomputed one. | Network validation fails against the attack it exists to prevent: a man-in-the-middle substitutes its own key, answers both sides, and both sides compute a matching number, so the check passes while the attacker controls the channel. Any check that travels the same path as the data cannot detect interception of that path. The transcription, meanwhile, was never a control - a caller that can reach the command can also pass the displayed number - so it was pure cost: 45 digits, and a correct pairing lost to a single mistyped digit. What is left is the part that genuinely works. The human compares two screens over a channel the attacker does not control, and the backend recomputes the number from the key so the paired key is provably the key that was on screen. This also matches Signal, WhatsApp and Bluetooth, which all show a number and ask for a click. | This is a real weakening and is not claimed otherwise. Removing 45 keystrokes removes some friction, and friction is a weak way of forcing attention - a user who does not actually read the number can now click through without touching a key, where before the typing at least made them stop. The mitigation is that the number stays large and centred on both screens and completion is a deliberate labelled click rather than a default. A stronger mitigation, not implemented, would be to require the number only when the two devices are on a network the app has reason to distrust. Anyone relying on 'you must type it' as an assurance that the other person read their screen out loud is no longer getting that assurance. | If the UI ever grows a QR path, the scan becomes the comparison and this decision gets superseded. Also revisit if there is ever a mode that pairs without any human present, which this decision explicitly forecloses. | Assistant | Decided | FEAT-074,LOG-068,LOG-069,DEC-013
DEC-029 | 2026-09-28 | Policy takes camelCase aliases rather than a camelCase rename | `Policy` is deserialized from two places that use two different conventions: inside a `CaptureSelection` arriving over IPC, where the TypeScript is camelCase, and inside the manifest, which is snake_case on the wire by DEC-012. | Blanket `rename_all = "camelCase"` (fixes input, rewrites the wire format); rename the TypeScript to snake_case (breaks the 9-place convention); per-field `alias` (accepts both, writes one); a separate boundary type (no alias risk, two types to keep in step). | Per-field `alias` on the three multi-word fields, so both spellings deserialize and exactly one is ever written. | A blanket rename would have appeared to work -- the capture would succeed -- while changing the manifest format for every stored and transferred manifest, which is a compatibility break in a field nothing tests. A separate type would be cleaner in principle but means two structs to keep in step forever. The alias keeps one type, accepts both spellings, and fails loudly if both are present. | The manifest wire format is unchanged, verified by a round-trip test. The four Policy fields are the only ones needing this treatment; `clipboard` is one word and is spelled the same in both conventions, so an alias for it would have been misleading. | If the manifest ever gains its own versioning per field, or the IPC boundary moves off Tauri's automatic argument mapping. | Assistant | Decided | BUG-024,FEAT-075
DEC-030 | 2026-09-28 | IP payloads deny unknown fields instead of ignoring them | Serde ignores an unrecognised key by default, so a field the UI sends under a name the Rust struct does not know arrives as an empty list, not an error. | Leave the default (silent); reject the whole payload on an unknown key; log a warning and continue. | Reject the payload. | Silent truncation is the worst available outcome: a capture completes, reports success, and quietly omits what the user selected. The symptom points somewhere else entirely -- in BUG-024 the URLs vanished and the browser adapter looked at fault, when the cause was four functions away. A user who selects three projects and pastes two URLs cannot tell an empty list that arrived empty from one that was dropped in transit. The UI and the Rust types are hand-mirrored in two languages, so the realistic failure is a typo, and a typo should stop the capture. | A field added in TypeScript before the Rust struct catches up now fails the command loudly instead of arriving empty. Applied to the three capture-selection types; deliberately NOT applied to `Policy`, which is also a wire format, where the manifest's own schema validation is the right mechanism and an unknown field could come from a newer sender. | If the frontend ever needs to send fields the backend does not model, or if a version skew between machines becomes possible. | Assistant | Decided | BUG-024,FEAT-075
DEC-031 | 2026-09-28 | File scope is 'everything minus junk', snapshotted at capture time | A captured workspace must carry the actual project files, so a file changed on the Mac exists on the Windows laptop after send + restore. The manifest policy column file_transfer already existed; nothing implemented it. Two coupled choices had to be made first: what counts as 'the files', and when the copy is made. | (a) Keep manifest-only. (b) Snapshot at capture time. (c) Snapshot at send time. Within (b), scope could be every selected project's folder wholesale, or a curated allowlist, or 'everything minus a denylist'. | (b) with 'everything minus two denylists and two caps'. At capture time: denied directories (.git, node_modules, target, dist, build, .next, .nuxt, .output, caches, virtualenvs, Pods, DerivedData, coverage) and denied files (.env/.env.*, keys, databases, logs, *.db, *.sqlite, Thumbs.db, desktop.ini) at any depth; symlinks skipped; one file over 128 MiB skipped and named; total capped at 512 MiB. Explicit policy is treated as All with a warning, since per-project selection is not built yet. | (c) means the copy changes between capture and send, so re-sending would re-send a different workspace -- the one property a re-send must not have. An allowlist is unmaintainable and would miss real projects; 'everything minus junk' is safe precisely because every excluded name is either regenerable build output or a secret. The caps keep the payload honest against the wire and the receiver's budget; the denylist keeps 'everything' safe. | A 13-test files crate; capture stores a sealed tar plus counts; re-send re-sends the same copy; legacy manifest-only payloads and the policy value 'none' still work. The capture screen defaults the policy to 'all' (FEAT-080). | Revisit when per-project file selection is wanted, which turns the Explicit policy from an alias into a real feature. | Assistant | Decided | FEAT-076,FEAT-077
DEC-032 | 2026-09-28 | The archive travels in an opaque envelope; restore runs as an ExtractFiles step | The wire already carries chunked, acked, encrypted opaque bytes, so carrying the archive required no change to framing or transport -- what had to change was the receive side's size budget and what the receiver does with the bytes. Storing and restoring also had two shapes available: formal storage plus a planner step, or a side file the restore command reads ad hoc. | (a) Extend the existing manifest payload with fields. (b) Wrap payload as MAGIC + u32 LE manifest length + manifest + archive, treating anything without the magic as legacy manifest-only. (c) Side-channel the archive entirely (separate transfer, separate storage). Restore: (d) a special-cased ExtractFiles RestoreActionType planned after map-path, or (e) a hidden file copy inside restore with no step and no preview. | (b) and (d). Envelope WCFB1 ¦ u32 LE manifest length ¦ manifest ¦ archive. The receiver splits the envelope, unseals the archive with its own key, stores it at files/{id}.files.sealed, and records counts in the workspace_files table (migration 003). The planner emits extract-files-{proj} (required, dependent on map-path-{proj}); the executor takes files: Option<&[u8]> and extracts per project into its mapped destination, overwriting existing files (snapshot authoritative). The accept-side incoming budget rises to the 512 MiB total plus 32 MiB headroom. | (a) would deny unknown-field-free manifests and break every stored payload. (c) splits one logical transfer into two atomicity domains. (e) hides the one thing a restore does that touches the disk -- the preview and the 'commands will run' warning would lie. (b)+(d) keep the transport untouched, the received workspace indistinguishable from a local capture, the report telling the truth about refusals and overflow, and a no-files workspace reporting an honest success. | Legacy payloads read back manifest-only, so pre-feature senders still arrive. 43 restore tests incl. the two extract tests; the two-device e2e proves the changed file restores. The restore report's step message carries counts, refusals and overflow. | Revisit if compression ever becomes worthwhile: the size math the signature and the caps rely on would change. | Assistant | Decided | FEAT-077,FEAT-078,FEAT-079
DEC-033 | 2026-09-28 | Connect candidates (IPv4 first, scoped link-local) and a dual-stack listener | A discovered device's first advertised address can be a bare link-local IPv6 string, which macOS refuses to route (ENETUNREACH, os error 65). The receiver also listened IPv4-only, so the IPv6 path could never have been served even when scoped. The send connected only to addresses.first(), so everything depended on mDNS answer order. | (a) Sort IPv4 ahead and keep connecting to the first address. (b) Try every advertised address, IPv4 first, racing them under one budget. IPv6: (c) leave link-local bare, (d) add per-interface scope via interface enumeration (if-addrs), (e) accept a hand-typed %zone. Listener: (f) keep 0.0.0.0, (g) prefer dual-stack [::] with IPV6_V6ONLY off, falling back. | (b)+(d)+(e)+(g). candidate_socket_addrs turns every advertised string into candidates: IPv4 first; a bare link-local IPv6 expanded to one scoped socket per local link-local interface (index from if-addrs), with a bare fallback only when no interface can scope it; %zone trusted as given. connect_any races them with futures select_ok under the single connect budget (10 s send, 5 s manual pairing), first success wins. The transfer listener prefers a dual-stack bind ([::], V6ONLY off, socket2) and falls back to the long-standing 0.0.0.0 bind. | IPv4-first alone fixes the reported case but leaves IPv6-only links producing the same confusing error; scoping a link-local address is the only way a connect to it can succeed. A dual-stack listener is required for a v6-only send to complete end to end. Racing keeps the UX at one budget (no N-candidate timeout stack) and names the refusing address, and both affected connect paths share the same helper so the rule can't drift. | if-addrs and socket2 become direct dependencies of the network crate (both already in the Cargo.lock via tokio/mdns-sd). Manual pairing now accepts fe80::x%en0. Error messages name the attempted candidate. 11 new tests; suite 405. | If transfers ever route over relays or tunnels where link-local addressing is irrelevant, the scoping machinery is harmless but could be simplified. | Assistant | Decided | BUG-028,FEAT-028
DEC-034 | 2026-09-30 | A dirty git worktree travels as a `git apply`-able patch; restore applies it instead of overwriting the tree | Capturing a workspace whose project is a dirty git clone and extracting the whole tree at restore made `git status` on the destination list every tracked file as modified (146 files for a one-file change): the archive carries no file modes, and the baseline at the destination may differ. | Overwrite the tree as before; capture only the dirty flag (status quo); ship the patch and apply it at restore | Record `git diff HEAD --binary` plus one new-file hunk per untracked, non-ignored file in the manifest (`GitInfo.patch`); planner plans `git-apply-<id>` and skips extraction for patched projects; the git adapter applies with `git apply --binary --whitespace=nowarn` | The delta is the honest thing to move: it is small, it is exactly what the user changed, and git apply's path validation keeps every write inside the chosen destination. Untracked files travel as hunks rather than via `git add -N` because a capture must never rewrite the user's index, and the snapshot denylist filters the untracked list so a secret cannot leak through a hunk the archive would refuse. A clean worktree captures no patch and restores exactly as before, so the change is strictly additive. | Dirty git repos restore to the exact uncommitted state instead of a mass re-overwrite. Adds an optional manifest field; manifests from older builds are unchanged. A patch that cannot apply (different base commit) is reported with the remedy, not silently dropped. | If restore ever needs to land local, uncommitted work on a checkout whose history diverged, the patch apply would need a 3-way merge strategy rather than the current apply-only. | Assistant | Decided | BUG-037

## Logs
Log ID | Date/Time | Type | Component | Feature/Task | Message | Details | Author | Tags
LOG-001 | 2026-09-27 00:24 | INIT | Project | EPIC-001 | Project initialized from blueprint | Created tracking Excel, set up directory structure | System | init,setup
LOG-002 | 2026-09-27 00:24 | DECISION | Architecture | DEC-001 | Selected Tauri 2 + React + TypeScript + Rust | Per blueprint recommendation §5 | Team | decision,architecture
LOG-003 | 2026-09-27 00:24 | DECISION | Architecture | DEC-002 | Selected Noise Protocol for encrypted transport | Peer-to-peer design, forward secrecy | Team | decision,crypto
LOG-004 | 2026-09-27 00:24 | DECISION | Architecture | DEC-003 | Selected SQLite + SQLCipher for encrypted local DB | Transparent encryption, OS key storage | Team | decision,database
LOG-005 | 2026-09-27 00:24 | DECISION | Architecture | DEC-004 | Selected mDNS/DNS-SD for LAN discovery | Standard, cross-platform, rotating IDs | Team | decision,network
LOG-006 | 2026-09-27 00:24 | DECISION | Frontend | DEC-005 | Selected Zustand for state management | Simple, TS-first, minimal boilerplate | Team | decision,frontend
LOG-007 | 2026-09-27 00:24 | DECISION | Frontend | DEC-006 | Selected Tailwind CSS for styling | Utility-first, fast iteration | Team | decision,frontend
LOG-008 | 2026-09-27 00:24 | DECISION | Data | DEC-007 | Selected JSON for manifests, CBOR for file transfer | Human-readable, schema validation | Team | decision,data
LOG-009 | 2026-09-27 00:24 | DECISION | Preflight | DEC-008 | Hybrid CLI + browser for identity checks | CLI reliable, browser for providers without CLI | Team | decision,preflight
LOG-010 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-001 | Phase 1 Foundation Complete | Tauri 2 workspace, CI/CD, Rust workspace, UI components | Team | milestone,phase1
LOG-011 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-002 | Local Database & Schema Complete | SQLite schema, migrations, encryption, repository pattern | Team | milestone,phase1
LOG-012 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-003 | Workspace Manifest Model Complete | Types, validation, scrubbing, capture preview | Team | milestone,phase1
LOG-013 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-004 | Capture Pipeline & Adapters Complete | Git, VS Code, Browser, Terminal, Runtime adapters | Team | milestone,phase1
LOG-014 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-005 | Device Pairing & Trust Complete | Key generation, QR pairing, safety numbers, revocation | Team | milestone,phase2
LOG-015 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-006 | LAN Discovery & Transfer Complete | mDNS discovery, Noise protocol, chunked transfer | Team | milestone,phase2
LOG-016 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-007 | Preflight Engine Complete | All check categories, identity adapters, readiness states | Team | milestone,phase3
LOG-017 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-008 | Restore Planning & Execution Complete | Plan generation, safe actions, Git safety, report | Team | milestone,phase3
LOG-018 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-009 | All UI Screens Complete | Welcome, Devices, Workspaces, Capture, Transfer, Preflight, Prepare, Restore, Settings | Team | milestone,phase1-3
LOG-019 | 2026-09-27 00:24 | MILESTONE | Project | EPIC-010 | Cross-Platform Path Mapping Complete | Named roots, OS-specific translation | Team | milestone,phase3
LOG-020 | 2026-09-27 00:24 | BUILD | Frontend | npm run build | TypeScript + Vite build successful | TypeScript compilation + Vite bundle successful | System | build,frontend
LOG-021 | 2026-09-27 00:24 | BUILD | Rust | cargo check --workspace | All Rust crates compile successfully | All workspace crates pass type checking | System | build,rust
LOG-022 | 2026-09-27 00:24 | TEST | Rust | cargo test --workspace | All 12 Rust tests passed | Unit and integration tests pass | System | test,rust
LOG-023 | 2026-09-27 00:24 | RUN | Frontend | npm run preview | Vite preview server running on port 1420 | Workspaces screen rendered successfully | System | run,frontend
LOG-024 | 2026-09-27 00:24 | RUN | Rust | cargo run -p app | Tauri app launched, database initialized | Native app runs, database initialized | System | run,rust
LOG-026 | 2026-09-27 16:20 | BUGFIX | Frontend | BUG-001 | Corrected the route parameter on three screens that could not load a workspace | Renamed :transferId to :workspaceId in App.tsx. Added src/test/routes.test.tsx with 9 tests that mount the real App behind a MemoryRouter and assert the URL's id reaches the backend. Verified the test fails when one pattern is reverted. | Assistant | bugfix,routing,test
LOG-027 | 2026-09-27 16:20 | BUGFIX | Rust / network | BUG-002 | Made cancellation interrupt the operation in progress rather than wait for a frame boundary | Added a watch channel and raced connect, handshake, per-frame ack and final confirmation against it. Cancel latency 15.005s -> under 0.08s. Used watch rather than Notify because a Notify's stored permit survives reset_cancel and cancelled the following transfer, hanging an existing test. | Assistant | bugfix,cancellation,transfer
LOG-028 | 2026-09-27 16:20 | BUGFIX | Rust / crypto | BUG-003 | Split the three local secrets into three credentials, as the documentation always claimed | store_local_keys writes each field to its own username. load_local_keys detects and parses the old all-three-identical layout so existing installations keep their device identity. | Assistant | bugfix,keychain,security
LOG-029 | 2026-09-27 16:20 | BUGFIX | Rust / app | BUG-004 | Set the application identifier to match the data directory | tauri.conf.json identifier com.tauri.dev -> com.workspaceclone.WorkspaceClone. Confirmed the device id was unchanged across a relaunch, because the Keychain credential is keyed on the service name. | Assistant | bugfix,packaging
LOG-030 | 2026-09-27 16:20 | REFACTOR | Frontend / screens | FEAT-050,FEAT-055,FEAT-058,FEAT-049 | Rebuilt four screens against the commands that exist | DevicesScreen: pairing now uses the real flow - paste or pick a key, compute the safety number from both Noise keys, type back what the other screen shows. The previous flow was a UI fiction: it asked for a pairing code, but verify_pairing takes a Noise key, and no implemented command accepts a code. PrepareScreen: now the unmet subset of the real preflight report, grouped by adapter, with the action the adapter recorded. It had 9 invented actions including 'Login to Supabase'. SettingsScreen: 22 toggles that changed nothing and 5 alert() stubs replaced by the real persisted surface, with the absent settings listed as absent. WelcomeScreen: removed claims of QR codes, browser tab capture and a Phase 0 status, none of which this build does. | Assistant | refactor,ui,honesty
LOG-031 | 2026-09-27 16:20 | TEST | Rust / network | FEAT-053,FEAT-006 | Added the loopback transfer integration test | network/tests/loopback_transfer.rs, 8 tests. Two TransferServices with real generated X25519 statics, real TCP over the loopback interface, a real Noise_IK handshake: byte-for-byte round trip, digest, the receiver learning the sender's authenticated key, progress shape, cancellation latency, a device with no advertised key, a wrong key, two transfers in a row, and an empty workspace. Multi-threaded runtime on purpose: a current-thread runtime deadlocks a test whose body is the send. Loopback rather than a mock socket, because a mock that correctly modelled the 65535-byte message ceiling, backpressure and partial reads would be a second implementation of the transport with its own bugs. | Assistant | test,integration,network
LOG-032 | 2026-09-27 16:20 | VERIFY | Desktop app | EPIC-005 | Verified the device identity derivation against a live database | The app's own key was read out of the Keychain-backed devices row and its id recomputed in Python: sha256('workspace-clone/connection-fingerprint/v1' ¦¦ key)[:16] base64 matches the stored id exactly. This is the invariant whose violation made every send report 'no device is reachable'. Also confirmed the id is unchanged across a relaunch, which is what makes pairing durable. | Assistant | verify,e2e,identity
LOG-033 | 2026-09-27 17:40 | Bug Found | Tauri Commands | BUG-005 | The receive path did not exist. The listener was bound and advertised; nothing accepted. | init started a listener and published its port over mDNS, and no task ever called accept_once. A peer's connection sat in the kernel accept queue until the sender's 30-second frame timeout. Fixed with commands/src/receive.rs and an accept loop started from init, each connection handled on its own task. | Assistant | transfer,receive,critical
LOG-034 | 2026-09-27 17:40 | Bug Found | Tauri Commands | BUG-006 | The payload was the sender's sealed manifest, which the receiver has no key to open. | send_workspace transmitted the file sealed with the sender's storage key. A key that never leaves the sender. The receiver would have stored bytes it could not read. Fixed by sending re-serialised JSON inside the encrypted channel and having the receiver seal it with its own key. See DEC-012. | Assistant | transfer,crypto,design-error
LOG-035 | 2026-09-27 17:40 | Bug Found | Tauri Commands | BUG-007 | No authorization on either direction. trust_scopes was stored and never read. | Added a paired / not-revoked / scope gate to both send and receive, with identity taken from the Noise key the handshake authenticated rather than from a frame header. Four tests, one per gate. | Assistant | transfer,security
LOG-036 | 2026-09-27 17:40 | Bug Found | Tauri Network | BUG-008 | One silent peer delayed every later peer by 15.03 seconds. | accept was awaited inline, so a peer that connected and said nothing held the listener for the whole handshake timeout. Measured by a new test rather than assumed. TransferReceiver is now Clone and the loop spawns per connection. See DEC-014. | Assistant | transfer,concurrency
LOG-037 | 2026-09-27 17:40 | Test Run | Tauri Commands | RUN-006 | Whole-workspace regression run: 348 passed, 0 failed. | cargo test --workspace -- --test-threads=2. Up from 347 after the BUG-011 regression test was added. | Assistant | testing,regression
LOG-038 | 2026-09-27 17:40 | Test Run | Frontend | RUN-007 | Frontend suite: 37 passed across 3 files, including 18 new receive-UI tests. | npx vitest run. Three of the new tests were rewritten because they asserted nothing real - see LOG-042. | Assistant | testing,frontend
LOG-039 | 2026-09-27 17:40 | Bug Found | Tauri App Shell | BUG-009, BUG-010 | Running the app for the first time surfaced two more bugs, both silent to every test. | tauri dev failed with 'No package info in the config file' because the config sat beside a virtual workspace manifest (BUG-009), and once started, the app compiled with ZERO capabilities because the capabilities glob resolved to a directory that did not exist (BUG-010). cargo build had succeeded throughout, so nothing was ever wrong as far as the build was concerned. See DEC-017. | Assistant | build,tooling,security,found-by-running-the-app
LOG-040 | 2026-09-27 17:40 | Bug Found | Tauri App Shell | BUG-011 | The app panicked on launch: tokio::spawn in the accept loop, called from Tauri's setup hook with no runtime entered. | 'there is no reactor running' - on the startup path, after the listener had bound and the device had advertised itself. Every test in the suite is #[tokio::test] and enters a runtime, so none of them could have caught it. Fixed with tauri::async_runtime::spawn, plus a plain #[test] that reproduces the condition. | Assistant | startup,async,critical,found-by-running-the-app
LOG-041 | 2026-09-27 17:40 | Test Run | Running application | RUN-010 | The running app accepts a connection on its advertised port. BUG-005 verified in the real program. | npx tauri dev, then a raw socket to the port from the log: 'Accepted a connection from 127.0.0.1:53841'. Before this, no test had ever started the application, which is why three live bugs survived a fully green suite. | Assistant | e2e,verification,found-by-running-the-app
LOG-042 | 2026-09-27 17:40 | Improvement | Frontend | RUN-012 | Verified the new tests catch real regressions, by breaking the code on purpose three times. | Each injected regression was caught by exactly the intended test and by no other. Before that, three of the new tests were rewritten: one spied on QueryClient.prototype.mount and then forced the refetch it claimed to be testing, one asserted the absence of an alert that was never rendered, and one rendered two component trees in a single test, making screen queries ambiguous. Reintroducing the BUG-011 fix in Rust was checked the same way. | Assistant | testing,quality,mutation-testing
LOG-043 | 2026-09-27 17:40 | Improvement | Tooling | FEAT-001 | Added scripts/check_command_parity.py as a repeatable check on the command surface. | Compares the generate_handler! registry against the invoke() names in src/lib/ipc.ts in both directions, and reports duplicate registrations where the second shadows the first. Exits non-zero, so it can run in CI. Currently: 44 registered, 44 called, zero orphans either way. | Assistant | tooling,parity,ci
LOG-044 | 2026-09-27 17:40 | Documentation | Project | All | Wrote DEVELOPER_GUIDE.md for a newcomer with one Windows laptop and one Mac laptop. | Part 1 is the user path end to end: install on both machines, pair (including the by-key fallback when mDNS is blocked by the router), choose scopes, capture, send, restore through preflight / prepare / restore plan / report, and a troubleshooting section ordered by how often each cause is the answer. Part 2 is the code: layout, how to run and test, how a workspace actually travels, the conventions that will bite, and the known gaps. Every factual claim about the UI was checked against the source; three were wrong on the first pass and were corrected. | Assistant | documentation,guide,handoff
LOG-045 | 2026-09-27 17:40 | Correction | Project | EPIC-006, FEAT-028, FEAT-030 | EPIC-006 and its transfer features were recorded as Done at 100% while the receive path did not exist. | Every test that existed drove the sending half. A feature marked Done is a claim, and these claims were wrong for weeks. The three bugs fixed in this session were all invisible to the suite: two were on the launch path and one was the absence of the thing the feature existed to do. Correcting the board in place, and logging the correction, so the board and the log agree about when the board was wrong. | Assistant | correction,process,status
LOG-046 | 2026-09-27 17:40 | Note | Project | SECURITY | No Content Security Policy is set. csp remains null in tauri.conf.json, deliberately. | A CSP that is wrong produces a blank window and no error, and the GUI cannot be loaded in this environment to test one - there is no assistive access and no screen recording. Setting a CSP without being able to verify the window still renders would trade a documented gap for an invisible one. This is EPIC-011 work and should be done on a machine where the window is visible. | Assistant | security,deferred,known-gap
LOG-047 | 2026-09-27 17:40 | Note | Project | DEPENDENCIES | npm audit reports 7 findings: 1 critical, 1 high, 5 moderate. | All in the dev toolchain - vitest/vite/esbuild, and react-router. Fixing them requires major version bumps the test suite has not been validated against, and none affect a shipped binary. Worth resolving before this goes anywhere real; not done in this session because a forced major bump across the test runner is a larger change than the findings justify mid-session. | Assistant | dependencies,security,deferred
LOG-048 | 2026-09-27 17:40 | Correction | Project | EPIC-006, FEAT-001, FEAT-028, FEAT-029, FEAT-030 | Corrected five feature and epic rows from Done at 100% to what the code actually did, and four Overview rows. | EPIC-006 and FEAT-001/028/029/030 were recorded as complete on 2026-09-26 with the receive path absent, the Tauri CLI unable to find the app, the app building with no capabilities, and the app panicking on launch. Overview: Test Coverage was 325/19 and is now 348/37; Target Platforms, Current Phase and Security Review moved to Partial / In Progress / Not Started because each was claiming more than the evidence supported. The log and the board now agree about when the board was wrong. | Assistant | correction,process,status
LOG-052 | 2026-09-28 14:20 | DESIGN | Frontend / Design System | FEAT-067,FEAT-068,FEAT-069 | UI redesigned for a desktop window, light and dark, with both modes verified by measurement. | Stitch project projects/16363674835719666940 (DESKTOP) drove the structure; its generated palette was rejected and the colours hand-corrected. 84 raw palette colours replaced with tokens. Layout rebuilt: always-visible collapsible sidebar, toolbar owning the single h1, status bar showing the real fingerprint / paired count / version instead of a hardcoded 'Local Mode' pill. Body set to 13px, giving ~45 lines in the content area against 34 at 16px. Google Fonts link removed - it was a third-party request on every launch in an app whose pitch is that nothing leaves the local network; the system stack is SF Pro on macOS anyway. Verification was by computed style, contrast ratio and geometry read from a live browser, because the GUI cannot be captured here. | Assistant | design,ui,dark-mode,design-tokens,density,desktop
LOG-053 | 2026-09-28 14:20 | BUG | Frontend / Layout | FEAT-067 | Sidebar invisible at the shipped window size; hamburger fallback had no handler. | `hidden lg:flex` against Tailwind's 1024px lg breakpoint, with an 800x600 default window. Every test rendered at jsdom's 1024px default, precisely the width where the bug does not manifest, so a fully green suite hid a total loss of navigation. Window now opens 1180x780 centered with minWidth 900. Logged as BUG-012. | Assistant | bug,layout,responsive,test-blind-spot
LOG-054 | 2026-09-28 14:20 | NOTE | Tooling / Verification | FEAT-068 | A hidden browser tab does not advance the CSS animation clock, which fakes a broken token system. | Chasing a suspected dark-mode bug: computed colours reported light-mode values while every custom property on the ancestor chain read the correct dark value. Cause was 56 CSSTransition objects pinned at currentTime 0 with progress 0, because document.hidden was true and Chrome freezes animations in background tabs. Forcing them to their end state returned correct dark values throughout. Worth knowing before spending time on a token bug that is a harness artifact. | Assistant | gotcha,css,testing,transitions,background-tab
LOG-055 | 2026-09-28 14:20 | NOTE | Tooling / Tests | FEAT-068 | jsdom implements neither localStorage nor matchMedia; the theme tests died before asserting anything. | Every theme test failed with "Cannot read properties of undefined (reading 'clear')" until src/test/setup.ts installed both. The matchMedia fake must expose a mutable `matches` read at listener time, because the store's change handler closes over the query object rather than re-querying. | Assistant | gotcha,jsdom,testing,matchmedia,localstorage
LOG-056 | 2026-09-28 14:20 | BLOCKER | Window / Keychain | FEAT-067 | GUI cannot be captured or driven in this environment; the macOS keychain prompt blocks a full launch. | browser.screenshot requires a visible desktop window, and screencapture fails - no assistive access. The Tauri window itself opens and renders, but the Rust startup path blocks on an invisible keychain authorisation prompt, so the transfer listener never binds. Unchanged from the previous round and unrelated to this round's changes (no Rust source was touched). The redesigned UI was verified in a browser served by the same dev server, which exercises all of the styling and layout; the Tauri window frame itself remains unverified. | Assistant | blocked,environment,keychain,verification-gap,macos
LOG-057 | 2026-09-28 16:10 | FIX | Backend / Platform | FEAT-070 | Three platform bugs found by reading the Windows branches of code that had never run on Windows. | hostname() would have named every Windows machine "This Mac" (BUG-018); the VS Code probe tested a literal path containing USERNAME, so per-user installs were invisible and preflight would tell users to install an editor they had (BUG-019); os_version() and Edge were missing from the probes (BUG-020, BUG-021). None was caught by the test suite, which is green and only ever runs on macOS. All four probes share a failure mode: reporting absence rather than failing, so a wrong answer becomes a wrong instruction. | Assistant | windows,platform,probes,unverified
LOG-058 | 2026-09-28 16:10 | FIX | Build / Tooling | FEAT-070,FEAT-072 | Removed the aarch64-apple-darwin build target pin; added a .gitignore. | The pin applied to every cargo invocation in the repo on every host (BUG-017). The .gitignore did not exist, and src-tauri/target is 17 GB - the two problems were discovered together because a CI build needs the repo cloned first. | Assistant | cargo,build,gitignore,windows
LOG-059 | 2026-09-28 16:10 | BLOCKER | Build / Tooling | FEAT-070,FEAT-071 | No Windows .exe can be produced from this machine: the environment cannot reach the Windows SDK or GitHub. | cargo-xwin installed cleanly (1m40s) but failed to download the MSVC CRT - aka.ms and github.com both time out after 15s; crates.io is reachable, so the block is selective rather than a total network failure. Tauri's Windows bundle additionally needs NSIS and Windows tooling, so a partial cross-compile would not have produced a distributable installer even if the CRT had downloaded. Conclusion: the supported path is a Windows machine, and this round delivers the two ways to use one plus five fixed bugs, not a binary. | Assistant | blocked,network,windows,honest-reporting
LOG-060 | 2026-09-28 16:10 | DECISION | Build / Tooling | FEAT-070,FEAT-071 | Two equivalent Windows build paths provided; neither claimed to work. | scripts/build_windows.sh for a laptop that can carry a toolchain, and a GitHub Actions workflow for one that cannot. Both pass the config path explicitly, because tauri.conf.json lives beside src-tauri/app/Cargo.toml and neither the CLI nor tauri-action searches there by default. FEAT-071 is left In Progress rather than Done: the tracker has previously held Done claims for weeks of unverified work, and marking an unrun workflow Done would repeat exactly that. | Assistant | ci,windows,tracker-honesty
LOG-061 | 2026-09-28 16:10 | VERIFY | Docs | FEAT-070 | DEVELOPER_GUIDE.md updated: binary path, Intel-Mac note, Windows section, test table, and a new Known Gap. | The test table claimed counts summing to 314 against an actual 348, and listed commands unit tests as 16 when the binary reports 57; now reconciled to 215 / 64 / 8 / 57 / 11 = 355. The Apple-silicon note told Intel users to delete .cargo/config.toml, which is no longer what that file is. Known Gaps now leads with the fact that the Windows build has never compiled at all, listing the five fixes as unproven. | Assistant | docs,corrections
LOG-062 | 2026-09-28 16:10 | NOTES | Build / Tooling | FEAT-070 | A useful side effect of removing the target pin: the binary path changed from target/<triple>/debug/app to target/debug/app. | Documentation and any run scripts referring to the old path need updating. A stale target/aarch64-apple-darwin/debug/app from the pinned era may still exist on disk; it is a leftover artifact and does not match current source. | Assistant | docs,paths
LOG-063 | 2026-09-28 16:10 | FOUND | Process / Tracker |  | The Tasks sheet is corrupt in two ways; found while checking for ID collisions before writing this round. | Ten duplicated task IDs and 67 rows whose dependencies sit in the Assignee column. Both pre-existing. The duplicate IDs are the serious one: they make the dependency graph ambiguous, and a planner following it would be misled with no visible error. Repairing the numbering needs a human decision because dependency references point into both batches, so no automatic rule resolves them all. Logged as BUG-022 with Status 'Not Fixed' rather than quietly renumbered, and the guide's test-count table was corrected in the same pass because it claimed 314 tests against an actual 348. | Assistant | tracker,data-integrity,not-fixed,honest-reporting
LOG-064 | 2026-09-28 18:30 | MILESTONE | End to End | FEAT-070,FEAT-073 | First live two-machine discovery: the Mac sees the Windows laptop over mDNS and can open a TCP connection to its transfer port. | The app was built, installed to /Applications and launched. It bound TCP 50228 (not the DEFAULT_PORT 47890 - it falls back to an ephemeral port and advertises the real one, which is sensible). mDNS resolution then showed the laptop as BISWAJITA._workspace-clone._tcp.local. at 192.168.31.24:57304, advertising app_version=0.1.0, os=windows, a device_id and a static_key. A TCP connect to that port succeeded in 0.01s, so the macOS firewall is not blocking it. The presence of a device_id and static_key proves the Windows Credential Manager path works end to end: those values can only exist if the laptop read its Noise key from the keyring. The name 'BISWAJITA' confirms the BUG-018 fix. Still unproven: the Noise handshake, completing the pairing ceremony, and an actual capture-transfer-restore. | Assistant | milestone,mDNS,discovery,windows,first-live-test
LOG-065 | 2026-09-28 18:30 | FIX | Build / Release | FEAT-073 | Re-signed the installed .app ad-hoc; the bundled copy had an invalid resource seal. | tauri build linker-signed the Mach-O but emitted no Contents/_CodeSignature, so spctl reported 'code has no resources but signature indicates they must be present' - the signature users see as 'the app is damaged'. Fixed on the installed copy with codesign --force --sign -. Logged as BUG-023 and deliberately NOT marked fixed at source, because every future build on a machine with no signing identity will reproduce it. | Assistant | codesign,gatekeeper,dmg,not-fixed-at-source
LOG-066 | 2026-09-28 18:30 | CORRECTION | Process / Tracker | FEAT-070 | Four verification claims from last round were false within hours; corrected. | BUG-018..021 all said 'by inspection only' and 'the Windows build has not compiled'. The user then built and installed on Windows, and the machines discovered each other, so those lines were wrong. Corrected per-row rather than deleted, keeping the original reasoning and appending the evidence. The lesson from FEAT-067 (Done claimed for unverified work) applies in both directions: a 'not verified' claim is also a claim, and it decays just as fast. FEAT-071 was checked at the same time and correctly left In Progress - the CI workflow still has never run, and a working Windows build does not make an unexecuted workflow verified. | Assistant | corrections,tracker-honesty,verification
LOG-067 | 2026-09-28 18:30 | NOTES | Build / Release | FEAT-073 | The app's executable inside the bundle is named 'app', which is visible in Activity Monitor and Force Quit. | CFBundleExecutable is 'app' because the Cargo package is called app, while CFBundleName and the .app filename are 'Workspace Clone'. Users see the right name in the Dock and menu bar, but 'app' in Activity Monitor, Force Quit and in a crash report. Cosmetic, not fixed - renaming the package would touch the whole workspace and the Tauri config paths. | Assistant | cosmetic,naming
LOG-068 | 2026-09-28 18:45 | BUG | Devices / Pairing | FEAT-074 | First live pairing attempt: nothing appeared on the Windows machine. Not a defect - the ceremony is two-sided and only one half was performed. | The Mac showed BISWAJITA, was clicked, and displayed a 45-digit number. The Windows app displayed nothing. The cause is DEC-013: pairing is not a handshake that completes once. Each machine keeps its own trust list, so the Windows side shows a number only once someone starts a pairing from that side and selects the Mac. The user's reading - 'it should have shown up there' - is a reasonable expectation and the UI did nothing to disabuse it: the safety step said 'read it to the person at the other device' without saying that the other device has to initiate too. The dialog now spells out the other machine's three steps. Worth recording that the underlying protocol was correct and only the instruction was missing; the alternative fix, making the Windows side push a number unprompted, would have meant auto-approaching a device that had not agreed to anything. | Assistant | pairing,two-sided-ceremony,ux,first-live-test
LOG-069 | 2026-09-28 18:45 | FIX | Devices / Pairing | FEAT-074 | Removed the 45-digit transcription from pairing; kept the comparison, kept the mismatch refusal. | The user asked for the code to show on both devices and for validation to happen over the network. Accepted the first part, refused the second, and the split is the substance of this entry. The old UI asserted 'typing it is the point' and the old Rust doc asserted the field was required, both on the grounds that an uncompared number proves nothing. That justification does not hold: a caller able to invoke verify_pairing can equally pass the number the app displayed, so transcription never distinguished a human who compared from a caller who did not. It only guaranteed that a correct pairing could fail on one mistyped digit. Network validation is worse than useless: a man-in-the-middle answers both sides with its own key, both sides then agree, and the check passes while the attacker owns every transfer. The out-of-band human comparison is the control, and the recomputation from the key is what makes it meaningful. Six Rust tests cover the new rule, including that a wrong number is still refused. Renaming the parameter to confirmed_safety_number also resolved a pre-existing mismatch where the doc comment had used that name for a parameter called expected_safety_number - a divergence that would have failed at runtime, since Tauri rejects undeclared arguments, while every type check passed. | Assistant | pairing,security,safety-number,weakening-accepted
LOG-070 | 2026-09-28 18:45 | CORRECTION | Process / Docs | FEAT-074 | The guide contradicted the UI on which machine's name the pairing field wants, in the middle of the step the user was reading. | The guide's ceremony step 3 said to type a name for 'the other machine' while the dialog labels the same field 'This device's name' and explains it is what the other person will see. Both readings are plausible, they are opposites, and the user met the discrepancy at exactly the moment they were trying to complete a live pairing. Fixed to match the UI. The wider point: docs written before a flow is exercised tend to describe the flow the author imagined, and this section had been written before anyone had run it against a second physical machine. | Assistant | docs,doc-ui-mismatch,first-live-test
LOG-071 | 2026-09-28 18:50 | FIX | Build / Release | FEAT-073 | Fixed the bundle-signature defect at source: Tauri now ad-hoc signs, so no manual codesign step is needed per build. | BUG-023 was logged as 'fixed' but explicitly not at source, with a note that the manual `codesign --force --sign -` would have to be repeated for every build. That was avoidable. Tauri v2 honours bundle.macOS.signingIdentity, and the value "-" means ad-hoc. With it set, a clean build logs 'replacing existing signature', emits Contents/_CodeSignature/CodeResources, and passes `codesign -v` with nothing done by hand. The symptom that motivated BUG-023 is gone: spctl reports only the expected 'rejected' for an ad-hoc unnotarized app, not 'code has no resources but signature indicates they must be present'. Recorded because the general lesson is the useful part - a manual workaround recorded as 'known limitation' is very often a config option that was never found, and the workaround hides the search. | Assistant | codesign,tauri-config,root-cause,bug-023
LOG-072 | 2026-09-28 19:05 | BUG | IPC / Capture | BUG-024 | Live two-machine test: sending a workspace failed on a casing mismatch | First real capture-to-send attempt returned `missing field `file_transfer``. Both types were complete and agreed on every name; they disagreed on the convention. Serde ignores unknown keys, so all five misnamed CaptureSelection fields arrived as empty lists, and only the nested Policy's first missing field stopped the command. The error named a field the caller was also sending. Fixed at source on all eleven affected fields across four types, not just the one reported. | Assistant | bug,ipc,capture,serde,live-test
LOG-073 | 2026-09-28 19:25 | FIX | IPC / Capture | FEAT-075 | Added a cross-language contract test after confirming it fails on the broken code | 6 tests in adapters/tests/ipc_selection_contract.rs. The central one reads the real src/types/index.ts and compares field names against what serde accepts, placing a gate in the space where the bug lived. Verified by reverting the fix and re-running: 3 tests fail, reproducing the user's exact error. An honest limit was found in the process -- the field-name comparison did not catch removal of the rename_all attribute, because it converts snake_case to camelCase first and so agreed either way. A separate test now pins the convention directly, also confirmed by revert. | Assistant | test,gate,ipc,verification
LOG-074 | 2026-09-28 19:10 | FIX | Network / Discovery | BUG-025 | Device names no longer carry the mDNS service type | The laptop was listed as `BISWAJITA._workspace-clone._tcp`. The full name is `{instance}.{service}.{domain}` and only the instance label is a name. Extracted `instance_display_name` to strip the whole service suffix case-insensitively, hoisted SERVICE_TYPE so registration and parsing share one constant, and rewrote the test that had been green while the bug was live. 4 new cases; 5 total. The existing test had asserted no trailing dot and no `.local` and passed happily, checking two properties that held while missing the one that was wrong. | Assistant | bug,discovery,mdns,naming,test
LOG-075 | 2026-09-28 19:20 | DECISION | Privacy / Browser | DEC-029 | Browser history capture is a documented guarantee, not a gap | The user reported that open URLs are not shown on the Mac. The browser adapter reports `history_access: "none: URLs are supplied by the user"` and the developer guide promises under 'Never read from your machine at all' that browser tabs, history, profiles and session databases are never read. The capture screen has a 'One URL per line' box. Reading history would retract a documented privacy guarantee on the most sensitive data on a machine, and is not only an adapter change: Chrome's History is SQLite, locked while the browser runs, and gated on macOS behind Full Disk Access. Not implemented. Offered a clipboard-paste shortcut as the honest alternative, which needs no new permission. | Assistant | decision,privacy,browser,scope
LOG-076 | 2026-09-28 19:35 | TEST | Network / Transfer | FEAT-075 | Added a live probe that tells a bound port from a served one | network/examples/live_listener_probe.rs. The receive module's own header records a build where the listener was bound and its port advertised while nothing called accept_once -- the app looked reachable and could receive nothing, and a bound port proves nothing about being served. The probe connects, sends bytes that cannot be a valid Noise handshake, and waits for the app to close: a served loop reads and drops, an unserved one never reads. Validated in both directions -- PASS against the running app, FAIL against a deliberately unserved listener. It cannot prove a transfer succeeds end to end, which needs a paired peer and a workspace. | Assistant | test,network,transfer,verification,tooling
LOG-077 | 2026-09-28 20:22 | FIX | Network / Transfer | FEAT-075 | BUG-026: send failed on a device discovery could see, because the send path read a map nothing ever populated | send_workspace looked up its destination only in TransferService::known, which remember_device() is the only writer of -- and no command ever calls it. known stayed empty for the process's whole life, so every send died with 'No device with id ... is currently reachable' before a socket opened, on a device the UI (reading discovery's own map) showed as on-network, paired and allowed to receive. Fixed by resolving from the discovery service's map first, dropping to known when an mDNS record expires, extracted as pure resolve_destination with 4 new tests; DiscoveryService gained a cfg(test) insert_for_test. Reverted to prove the tests catch the shipped bug (2 fail). 374 Rust tests green. | Assistant | bug,transfer,discovery,resolution,live-test
LOG-078 | 2026-09-28 20:40 | FIX | Restore / Planner | FEAT-040 | BUG-027: restore nested projects under the destination root, appending the source machine's folder name | resolve_destinations resolved root.join(project.name) for every project. The name is the source machine's folder name (openshorts from Documents/openshorts on the Mac), so restoring to E:/workspace-clone produced E:/workspace-clone/openshorts and the report asked the user to create a folder they never named. New rule: one project per bucket lands exactly in the folder typed (name never consulted, hostile names inert); several projects per bucket nest under it via safe_child. Same-name collisions warn. Revert-verified; 377 Rust / 99 vitest green. | Assistant | bug,restore,destination,planner,live-test
LOG-079 | 2026-09-28 21:45 | IMPLEMENTATION | Core / Files | FEAT-076 | Built the files crate: snapshot, archive, transit | New crate src-tauri/files. snapshot.rs: sorted deterministic tar built at capture time -- denylists for directories and files matched at any depth, per-file 128 MiB cap, 512 MiB total cap, symlinks skipped, every skip and the overflow surfaced. archive.rs: extraction treats every entry as hostile -- refuses traversal names, absolute paths, backslashes, drive letters, symlinks, reserved Windows device names and oversized entries, and caps the total. transit.rs: the WCFB1 envelope wrap/unwrap. 13 tests, 0 warnings. | Assistant | files,archive,snapshot,denylist,caps
LOG-080 | 2026-09-28 21:45 | IMPLEMENTATION | IPC / Capture | FEAT-076 | Capture now snapshots, seals and stores the file archive at capture time | snapshot_and_store walks the selected projects, seals the tar with the storage key, writes it to files/{id}.files.sealed, and upserts the workspace_files row (migration 003). CaptureResult carries file_count and byte_count; every skip and the overflow become capture warnings. The exact same bytes are what a re-send puts on the wire. | Assistant | capture,files,snapshot,sealed
LOG-081 | 2026-09-28 21:45 | IMPLEMENTATION | Network / Transfer | FEAT-077 | The wire now carries the archive behind the manifest, in an opaque envelope | transfer_payload replaced manifest_payload at the send site: WCFB1 magic, u32 LE manifest length, manifest JSON, archive -- inside the existing encrypted chunked frames, with no change to framing. The receive side splits the envelope; a payload without the magic reads back as manifest-only, so every pre-feature sender still arrives. The accept-side budget rose to 512 MiB + 32 MiB headroom, and the arrived archive is unsealed with the receiver's own key and stored exactly as a local capture stores one. | Assistant | transfer,wire,envelope,backward-compatible
LOG-082 | 2026-09-28 21:45 | IMPLEMENTATION | Restore / Planner | FEAT-079 | Restore gained an extract-files step per placed project | The planner adds extract-files-{proj} (required, dep map-path-{proj}); the executor receives files: Option<&[u8]> and calls the hostile extractor per project into its mapped folder, overwriting what is there. The step message reports files written and bytes, refusals and overflow; a workspace with no files reports an honest success. 43 restore tests incl. two new extract tests; the two-device e2e asserts that a file changed on the sending machine has the changed content on the receiving machine after send + restore. | Assistant | restore,extract,planner,executor,e2e
LOG-083 | 2026-09-28 21:45 | IMPLEMENTATION | Frontend | FEAT-080 | Frontend wired for the file feature | extract_files joined RestoreActionType; the restore preview and report render the step with its own icon and the preview classifies it as an execution step, so the 'commands will run' warning stays honest. The capture policy defaults to 'all' -- the UI's only choice for a fresh capture is to carry files, which is the point of a clone; 'none' and 'explicit' remain in the type. The capture screen's 'What is never captured' notice states the snapshot's denylist and corrects the stale claim that working-tree files are never copied. | Assistant | frontend,restore-preview,restore-report,capture-policy
LOG-084 | 2026-09-28 21:45 | TEST | Project | RUN-024,RUN-025,RUN-026 | Full gates green: 394 Rust, 99 frontend, tsc clean | cargo test --workspace -- --test-threads=2: 394 passed, 0 failed -- up from 377 by 17 (files crate 13, the two-device files e2e 1, restore extracts 2, one further command unit). npx vitest run: 99/99 across 6 files. npx tsc --noEmit: clean. Command-surface parity and the design-token check are clean too. No test asserted a manifest-only capture default, so defaulting the policy to 'all' stayed green. | Assistant | testing,regression,full-run
LOG-085 | 2026-09-28 21:45 | IMPROVEMENT | Project | All | FEAT-045 corrected, guide and tracker aligned to the file feature | FEAT-045 was Done at 100% for 'file transfer' while only the manifest policy flag existed; its row now says exactly that, and the transport is FEAT-076..080. DEVELOPER_GUIDE updated: the capture section states the denylist and caps, restore step 3 documents the extract step, the wire diagram shows the envelope and the extract step, the privacy section distinguishes the adapters' promises from the file snapshot's, and the test counts are 394/99. | Assistant | correction,documentation,guide
LOG-086 | 2026-09-28 21:30 | BUILD | Build / Release | RUN-028,FEAT-073 | DMG built and verified: Workspace Clone_0.1.0_aarch64.dmg, 8.2 MB | npx tauri build ran the frontend build, the Rust release build (no code warnings), and bundle_dmg.sh. The only output was a tauri-build deprecation notice -- STATIC_VCRUNTIME is deprecated, use build.windows.staticVCRuntime in tauri.conf.json -- which fires in the release profile only, concerns Windows CRT linking, and originates in the tauri-build dependency rather than any crate in this workspace. Left as a documented note rather than patched blind: the config key it asks for changes the Windows installer's runtime linking, which can only be verified on the Windows laptop. The debug build gate stays warning-free. | Assistant | build,release,dmg,deferred-note
LOG-087 | 2026-09-28 22:10 | FIX | Project Data | BUG-022 | Tasks sheet renumbered and dependency columns fixed | BUG-022 fixed per the chosen option (second block renumbered): rows 42-73 became TASK-041..TASK-072 in row order, so all 72 task rows now have unique IDs (the 14 shared IDs are gone). The 67 dependency lists sitting in the Assignee column (38 first-block + 29 second-block rows) moved into the Dependencies column. References remapped by the first-occurrence rule: only labels whose first sheet occurrence is in the second block changed -- TASK-042->056, TASK-047->061, TASK-048->062, TASK-056->068; ambiguous labels TASK-031..040 resolve to the canonical first block and were left as written. Caveat: the dependency VALUES were bulk-populated when the sheet was built and their semantics remain the original author's intent, not a derived DAG -- but the column each chain sits in is now the one its header names. Re-verified by script asserts on 2026-09-28. | Assistant | bug,data-quality,tasks-sheet,correction
LOG-088 | 2026-09-28 23:10 | FIX | Network Crate | BUG-028,FEAT-028 | Send failure "No route to host" fixed: every advertised address is a connect candidate | BUG-028 resolved in transfer.rs + discovery.rs. send_inner no longer connects to addresses.first(): candidate_socket_addrs expands every advertised string (IPv4 first; bare link-local IPv6 scoped per local link-local interface via if-addrs; hand-typed %zone trusted; dedup; unparseable entries skipped) and connect_any races them under the single 10s budget with futures select_ok, first success wins. connect_manual reuses the same helper with its 5s budget, so fe80::x%en0 works in the pairing dialog. The transfer listener now prefers a dual-stack [::] bind (socket2, IPV6_V6ONLY off) with the old 0.0.0.0 bind as fallback, so a peer connecting over IPv6 can be served. On this Mac the listener binds [::] and still serves 127.0.0.1. ERR-007 records the observed os error 65. 11 new tests (network 68 -> 79), full suite 405 green, build warning-free. Docs updated: DEVELOPER_GUIDE troubleshooting gains the fe80:: entry, the transfer flow documents candidate selection and the dual-stack listener, and the counts are 405/99. Pending: rebuild + reinstall the .exe on the Windows laptop and retest both send directions on hardware. | Assistant | bug,network,ipv6,link-local,connect-fix
LOG-089 | 2026-09-29 10:30 | FIX + ANALYSIS | Frontend / Workspaces Screen | BUG-029,FEAT-051 | BUG-029 fixed; Windows->Mac retest analysed: arrival correct, capture was near-empty | BUG-029 resolved in WorkspacesScreen.tsx: a newly-seen accepted arrival in the incoming-transfers poll now invalidates ['workspaces'], so a workspace that arrives while the list is open appears without a menu change. New vitest pins it; suite is now 100 frontend tests, tsc clean. On the hardware retest, the green banner rendered 'Testing Window - Mac' and the Mac DB stores it with source BISWAJITA - so the reported empty-looking banner was not reproducible from current data and needs the screenshot. The 'restore shows nothing' report was root-caused on the sender side: the unsealed received manifest for bbb38119 has projects=0 and one optional terminal-session application, and no workspace_files row exists - the Windows capture selected no projects, so no file archive was ever carried and the restore plan legitimately has nothing. DEVELOPER_GUIDE gains a 'received workspace restores as nothing selected' entry pointing at the sender's project scan (default roots ~/projects, ~/Documents) and Settings -> Project locations. Next: user to reattach the two screenshots and on Windows to set project roots, tick projects, re-capture and re-send. | Assistant | frontend,arrival,workspaces-list,bug,analysis,restore,capture
LOG-090 | 2026-09-29 23:45 | FIX + ANALYSIS | Backend + Frontend / App | BUG-030,BUG-031,BUG-032,BUG-033,BUG-034,BUG-035,BUG-036 | All seven post-handoff bugs fixed and validated in the rebuilt app | One root cause covers four of them: `receive::IncomingTransfer` serializes camelCase (rename_all = "camelCase") but the TS interface and every fake-backend fixture used snake_case, so at runtime the banner name (BUG-031), the dismissal id (BUG-032), the preflight navigation guard (BUG-033) and the BUG-029 list-refresh effect (BUG-034) all read undefined. The TS type and fixtures now mirror the wire exactly; a Rust test pins the producer's JSON keys and a frontend test renders a literal camelCase payload so the two sides cannot drift again. The two delete bugs share their own root cause: both repository deletes were a single DELETE against a table that child tables reference with enforced foreign keys, so every delete silently failed. Delete now cascades inside a transaction (workspace: files/snapshots/restore-runs/transfer-sessions then the row plus the sealed manifest and archive on disk; device: the workspaces it sent with their children, sessions both directions, restores, snapshots, then the row, never touching local captures). Devices page no longer lists this machine (local id filtered out of list_paired_devices) and has exactly one destructive action, Forget. Validated in the rebuilt, re-installed app on the live Mac DB; 408 Rust tests (12 two-device e2e) and 102 frontend tests pass, tsc clean, build warnings 0. The one thing only the user can do is send one more Windows->Mac workspace to watch the corrected banner live. | Assistant | frontend,backend,serde,wire-shape,arrival,delete,devices,bug,analysis
LOG-091 | 2026-09-30 10:30 | FIX + ANALYSIS | Backend / Adapters + Restore | BUG-037 | Git working-tree changes now travel as a patch, so restore changes one file instead of 146 | Capture records the dirty worktree's delta: `git diff HEAD --binary` (staged+unstaged net) plus a `git diff --no-index /dev/null <file>` new-file hunk per untracked, non-ignored file, filtering through the snapshot denylist and never mutating the user's index (no `git add -N`). The delta rides in new optional `GitInfo.patch` (serde default, backward compatible; the old honest lies -- dirty_state_captured always false -- are retired). Restore: patched projects skip whole-tree extraction and get a `git-apply-<id>` step run by the git adapter with `git apply --binary --whitespace=nowarn` from a temp patch file; a patch that cannot apply (base mismatch) is a Manual step reading 'git checkout <source_commit>', never a silent drop. Three bugs worth remembering: `git diff --no-index` exits 1 when files differ, so the capture must accept exit 1 or drop every untracked hunk; `str::trim` on the patch strips the final hunk line's newline and git rejects the patch as corrupt at that line; `ls-files` must use `-z` or the whole listing comes back as one newline-swallowing entry. Verified end to end: adapter capture-to-apply round trips, planner extract-skip, and a real two-device socket transfer whose restored checkout shows exactly the source's delta. | Assistant | bug,git,patch,restore,delta,transfer,analysis